## Main Sheet
Updated Job Spreadsheet
Job Number | Job Name | Job Owner | Contract Signed & Returned. Retention % loaded correctly into Katipolt | Warranty Signed & Returned | Construction Programme Received | Into Work Calculator 2 Weekly | Temp Application Done | Mains Connection Application | POs Sent to Sub contractors | Switchboard Drawing Sent for Approval | Email Sent to QS/Builder to Confirm Order Gear | Long Lead Time Materials Ordered |  | Client Walk Through | Pre Job Meeting Completed with Staff Job Pack Made | O&M Manual underway (notes for what's needed) | QA Completed By Others |  | Job Completion Paperwork Completed | All V.Os captured | Last toolbox date
[12 empty] | Ordered | Lead Times Comm. |  |  |  | 1st Fix | 2nd Fix
7658 | Charity Hospital | Cameron Skilton | Yes |  | Yes | Yes | N/A | N/A | Yes | Yes | Yes | Yes |  |  | Yes
8142 | Fisher Developements | Cameron Skilton | Yes |  | Yes |  | Yes | Yes | Yes | Yes |  | Yes
8824 | 3 Innovation Road | Cameron Skilton |  |  | Yes | N/A | N/A | Yes | Yes | Yes | Yes | N/A | N/A | Yes |  | Yes | Yes | Yes |  | Yes
8127 | Rolly Autowash | Cameron Skilton | Yes |  | Yes | No | Yes | Yes | N/A | Yes |  | Yes
8183 | Murney - 1 Freight Drive + 109 Iport | Cameron Skilton | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes |  | Yes
8886 | Monkey Toe - Fisher fit out | Cameron Skilton |  |  | Yes | No | N/A | Yes | Yes | Yes
8887 | Tenancy 2 - Fisher Fit out | Cameron Skilton |  |  | Yes | No | N/A | Yes | Yes | Yes
8670 | Studio DB - tautara fit out | Cameron Skilton | Yes
8907 | 35 Mania | Cameron Skilton | Yes
9065 | Cooltranz stage 4 | Cameron Skilton | Yes |  | Yes | Yes | N/A | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Yes | Yes | N/A |  | Yes
9259 | Andrew Reeve Stage 2 | Cameron Skilton | Yes |  | Yes | Yes | N/A | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | N/A |  | Yes
8352 | 5 Sanscrit Place | Tom Price | Yes | N/A | Yes |  | N/A | N/A |  | N/A | Yes |  |  | Yes
8234 | Melhuish House | Tom Price
8214 | 6 Tiroroa Lane | Tom Price | Yes | N/A | [5 empty] | N/A
6792 | Major Hornbrook | Tom Price | Yes | Yes | Yes | Yes | N/A | Yes | Yes | Yes | Yes | N/A | Yes | Yes |  | NA |  |  |  | Yes
8840 | Inline Architecture | Tom Price
8769 | Percival Bach | Tom Price
7901 | St Albans Street | Tom Price
8923 | 4 Perry St | Tom Price
7864 | Ryans House
7912 | 71A Fendalton Road | Tom Price | Yes | N/A |  | 2025-11-18 |  |  | N/A | N/A |  |  |  | No
8360 | Dixon House | Tom Price | Yes | N/A | Yes | 2025-11-18 | N/A | Yes | N/A | N/A | N/A | N/A |  | Yes
8337 | Waimak Dairys | Tom Price
9240 | Daves Twizel Shack
7428 | FAB Pegasus Lakeside | Tom Price | Yes | N/A | Yes | 2025-11-18 | Yes |  | N/A | Yes | N/A | Yes |  | No
9351 | Harewood Golf Club | Tom Price
7429 | Taggart House | Tom Price | Yes | N/A | Yes | 2025-11-18 | N/A | N/A | N/A | N/A | N/A |  |  | No
9508 | St Barnabas Church | Tom Price |  | N/A | Yes | 2025-11-18 | N/A | N/A | N/A | N/A | N/A |  |  | No
|  |  |  | N/A | Yes |  | N/A |  | N/A
Contracting
8946 | Westcoast Vaults | Cameron Skilton | Yes | N/A | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes |  |  | Yes | Yes | Yes |  | Yes
8308 | Roydvale | Tom Price |  | N/A | Yes |  | N/A |  | N/A
8530 | 224 Cashel St - Eastern WC Block Reno | Charles Roselier
8386 | Bach in Kaikoura | Tom Price
8829 | Resi Reno at 124 Chapter Street | Tom Price
7480 | New Build | Tom Price
9437 | 65A Belfast Road (Revised)

## Deliverables Sheet
Updated Job Spreadsheet
Job Number | Job Name | Week | Quoted Price | Claim to date | Remaining to claim | % Claim remaining | Total quoted cost | Total actual cost | Quoted material cost | Actual material cost | Material cost remaining | Material % remaining | Estimated % of materials recieved | Quoted labour cost | Actual labour cost | Labour cost remaining | Labour cost % remaining | Quoted labour hours | Actual labour hours | Labour hours remaining | Labour hour % remaining | Estimated % of job complete | GP $ Per Hour | Quoted GP $ Per Hour | Margin to date | Quoted margin
[29 empty] | Hours calcs | Materials calcs
7658 | Charity Hospital | Start of month | 245679.5 | 216530.08 | 29149.42 | 11.86% | 208360.5 | 167957.68 | 180366.49 | 138548.02 | 41818.47 | 23.19% | 90% | 27994.01 | 29409.66 | -1415.65 | -5.057% | 565.45 | 588.25 | -22.8 | -4.032% |  | 82.571 | 65.9988 | 22.43% | 15.19% | Hours calc for monthly claims | -418 | -418 | -92952.56
|  | Week 1 | 245679.5 | 216530.08 | 29149.42 | 11.86% | 208360.5 | 168361.6 | 180366.49 | 138438.46 | 41928.03 | 23.25% |  | 27994.01 | 29923.14 | -1929.13 | -6.891% | 565.45 | 600.25 | -34.8 | -6.154% |  | 80.2474 | 65.9988 | 22.25% | 15.19% | Materials calc for monthly claims | -92952.56
|  | Week 2 | 245679.5 | 216530.08 | 29149.42 | 11.86% | 208360.5 | 168361.6 | 180366.49 | 138438.46 | 41928.03 | 23.25% |  | 27994.01 | 29923.14 | -1929.13 | -6.891% | 565.45 | 600.25 | -34.8 | -6.154% |  | 80.2474 | 65.9988 | 22.25% | 15.19%
|  | Week 3 | 267886.85 | 216530.08 | 51356.77 | 19.17% | 225410.55 | 167992.78 | 193787.25 | 138051.32 | 55735.93 | 28.76% |  | 31623.3 | 29941.46 | 1681.84 | 5.318% | 638.02 | 600.25 | 37.77 | 5.92% |  | 80.8618 | 66.5752 | 22.42% | 15.86% | Estimated months claim | 0
|  | Week 4 | 267886.8488 | 238732.97 | 29153.8788 | 10.88% | 225410.5455 | 188979.91 | 193787.2413 | 158312.05 | 35475.1913 | 18.31% |  | 31623.3042 | 30667.86 | 955.4442 | 3.021% | 638.02 | 616.75 | 21.27 | 3.334% |  | 80.6697 | 66.5752 | 20.84% | 15.86%
|  | Week 5 | 267886.8488 | 238732.97 | 29153.8788 | 10.88% | 225410.5455 | 189455.97 | 193787.2413 | 158286.35 | 35500.8913 | 18.32% |  | 31623.3042 | 31169.62 | 453.6842 | 1.435% | 638.02 | 625.25 | 12.77 | 2.002% |  | 78.8117 | 66.5752 | 20.64% | 15.86% |  |  | -418 | -92952.56
8142 | Fisher Developements | Start of month | 129074.86 | 85864.08 | 43210.78 | 33.48% | 101420.72 | 74137.32 | 83645.65 | 69538.04 | 14107.61 | 16.87% |  | 17775.07 | 4599.28 | 13175.79 | 74.13% | 356.07 | 93.25 | 262.82 | 73.81% | 30% | 125.7561 | 77.6649 | 13.66% | 21.42% | Hours calc for monthly claims | -52.5 | -52.5 | -45701.86
|  | Week 1 | 129074.86 | 85864.08 | 43210.78 | 33.48% | 101420.72 | 79791.03 | 83645.65 | 71604.5 | 12041.15 | 14.4% |  | 17775.07 | 8186.53 | 9588.54 | 53.94% | 356.07 | 168.25 | 187.82 | 52.75% |  | 36.0954 | 77.6649 | 7.07% | 21.42% | Materials calc for monthly claims | -45701.86
|  | Week 2 | 129996.92 | 85864.08 | 44132.84 | 33.95% | 101885.52 | 79853.63 | 83735.42 | 71667.1 | 12068.32 | 14.41% |  | 18150.1 | 8186.53 | 9963.57 | 54.9% | 363.57 | 168.25 | 195.32 | 53.72% |  | 35.7233 | 77.3204 | 7% | 21.62%
|  | Week 3 | 129996.92 | 85864.08 | 44132.84 | 33.95% | 101885.52 | 77983.94 | 83735.42 | 69781.5 | 13953.92 | 16.66% |  | 18150.1 | 8202.44 | 9947.66 | 54.81% | 363.57 | 168.25 | 195.32 | 53.72% |  | 46.8359 | 77.3204 | 9.18% | 21.62% | Estimated months claim | 0
|  | Week 4 | 132076.0882 | 127883.98 | 4192.1082 | 3.174% | 103822.9739 | 92794.34 | 85672.8749 | 80310.8 | 5362.0749 | 6.259% |  | 18150.099 | 12483.54 | 5666.559 | 31.22% | 363.57 | 272.5 | 91.07 | 25.05% |  | 128.7693 | 77.7102 | 27.44% | 21.39%
|  | Week 5 | 132076.0882 | 127883.98 | 4192.1082 | 3.174% | 103822.9739 | 95219.95 | 85672.8749 | 80502.31 | 5170.5649 | 6.035% |  | 18150.099 | 14717.64 | 3432.459 | 18.91% | 363.57 | 331.25 | 32.32 | 8.89% |  | 98.6084 | 77.7102 | 25.54% | 21.39% |  |  | -52.5 | -45701.86
8824 | 3 Innovation Road | Start of month | 27500.32 | 11999.08 | 15501.24 | 56.37% | 19565.83 | 7621.92 | 13767.34 | 5911.24 | 7856.1 | 57.06% |  | 5798.49 | 1710.68 | 4087.81 | 70.5% | 125.39 | 34.75 | 90.64 | 72.29% | 25% | 125.9614 | 63.2785 | 36.48% | 28.85% | Hours calc for monthly claims | -34.75 | -34.75 | -5911.24
|  | Week 1 | 27500.32 | 11999.08 | 15501.24 | 56.37% | 19565.83 | 7921.92 | 13767.34 | 6211.24 | 7556.1 | 54.88% |  | 5798.49 | 1710.68 | 4087.81 | 70.5% | 125.39 | 34.75 | 90.64 | 72.29% |  | 117.3283 | 63.2785 | 33.98% | 28.85% | Materials calc for monthly claims | -5911.24
|  | Week 2 | 27500.32 | 11999.08 | 15501.24 | 56.37% | 19565.83 | 7921.92 | 13767.34 | 6211.24 | 7556.1 | 54.88% |  | 5798.49 | 1710.68 | 4087.81 | 70.5% | 125.39 | 34.75 | 90.64 | 72.29% |  | 117.3283 | 63.2785 | 33.98% | 28.85%
|  | Week 3 | 27500.32 | 11999.08 | 15501.24 | 56.37% | 19565.83 | 7921.92 | 13767.34 | 6211.24 | 7556.1 | 54.88% |  | 5798.49 | 1710.68 | 4087.81 | 70.5% | 125.39 | 34.75 | 90.64 | 72.29% |  | 117.3283 | 63.2785 | 33.98% | 28.85% | Estimated months claim | 0
|  | Week 4 | 27500.3157 | 11999.08 | 15501.2357 | 56.37% | 19565.829 | 8083.92 | 13767.3372 | 6373.24 | 7394.0972 | 53.71% |  | 5798.4918 | 1710.68 | 4087.8118 | 70.5% | 125.39 | 34.75 | 90.64 | 72.29% |  | 112.6665 | 63.2785 | 32.63% | 28.85%
|  | Week 5 | 27500.3157 | 11999.08 | 15501.2357 | 56.37% | 19565.829 | 8083.92 | 13767.3372 | 6373.24 | 7394.0972 | 53.71% |  | 5798.4918 | 1710.68 | 4087.8118 | 70.5% | 125.39 | 34.75 | 90.64 | 72.29% |  | 112.6665 | 63.2785 | 32.63% | 28.85% |  |  | -34.75 | -5911.24
8127 | Rolly Autowash | Start of month | 150850.82 | 144370.8 | 6480.02 | 4.296% | 102178.42 | 85848.41 | 62464.86 | 57454 | 5010.86 | 8.022% | 90% | 39713.56 | 28394.41 | 11319.15 | 28.5% | 795.22 | 577.75 | 217.47 | 27.35% | 60% | 101.2936 | 61.2062 | 40.54% | 32.27% | Hours calc for monthly claims | -388.25 | -388.25 | -56964.81
|  | Week 1 | 150850.82 | 144370.8 | 6480.02 | 4.296% | 102178.42 | 89222.05 | 62464.86 | 58984 | 3480.86 | 5.573% |  | 39713.56 | 30238.05 | 9475.51 | 23.86% | 795.22 | 615 | 180.22 | 22.66% |  | 89.6728 | 61.2062 | 38.2% | 32.27% | Materials calc for monthly claims | -56964.81
|  | Week 2 | 153553.67 | 144370.8 | 9182.87 | 5.98% | 104026.09 | 90387.67 | 63812.49 | 59529.82 | 4282.67 | 6.711% |  | 40213.6 | 30857.85 | 9355.75 | 23.27% | 805.22 | 625 | 180.22 | 22.38% |  | 86.373 | 61.5081 | 37.39% | 32.25%
|  | Week 3 | [24 empty] | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -388.25 | -56964.81
8183 | Murney - 1 Freight Drive + 109 Iport | Start of month | 396422.03 | 259347.71 | 137074.32 | 34.58% | 327431.12 | 216344.6 | 271519.78 | 195955.93 | 75563.85 | 27.83% |  | 55911.34 | 20388.67 | 35522.67 | 63.53% | 1120.27 | 476.25 | 644.02 | 57.49% | 40% | 90.2952 | 61.5842 | 16.58% | 17.4% | Hours calc for monthly claims | -387.5 | -387.5 | -132316.71
|  | Week 1 | 396422.03 | 259347.71 | 137074.32 | 34.58% | 327431.12 | 223659.54 | 271519.78 | 197370.72 | 74149.06 | 27.31% |  | 55911.34 | 26288.82 | 29622.52 | 52.98% | 1120.27 | 607.75 | 512.52 | 45.75% |  | 58.7218 | 61.5842 | 13.76% | 17.4% | Materials calc for monthly claims | -132316.71
|  | Week 2 | 397238.61 | 259347.71 | 137890.9 | 34.71% | 328046.93 | 224540.22 | 271925.57 | 197386.58 | 74538.99 | 27.41% |  | 56121.36 | 27153.64 | 28967.72 | 51.62% | 1124.47 | 627.75 | 496.72 | 44.17% |  | 55.448 | 61.5327 | 13.42% | 17.42%
|  | Week 3 | 397238.61 | 259347.71 | 137890.9 | 34.71% | 328046.93 | 228092.96 | 271925.57 | 199320.36 | 72605.21 | 26.7% |  | 56121.36 | 28772.6 | 27348.76 | 48.73% | 1124.47 | 667.75 | 456.72 | 40.62% |  | 46.8061 | 61.5327 | 12.05% | 17.42% | Estimated months claim | 0
|  | Week 4 | 397238.6107 | 352623.79 | 44614.8207 | 11.23% | 328046.9322 | 277449.99 | 271925.5722 | 243603.26 | 28322.3122 | 10.42% |  | 56121.36 | 33846.73 | 22274.63 | 39.69% | 1124.47 | 783 | 341.47 | 30.37% |  | 96.0074 | 61.5327 | 21.32% | 17.42%
|  | Week 5 | 397238.6107 | 352623.79 | 44614.8207 | 11.23% | 328046.9322 | 279095.37 | 271925.5722 | 243619.32 | 28306.2522 | 10.41% |  | 56121.36 | 35476.05 | 20645.31 | 36.79% | 1124.47 | 821.5 | 302.97 | 26.94% |  | 89.5051 | 61.5327 | 20.85% | 17.42% |  |  | -387.5 | -132316.71
8886 | Monkey Toe - Fisher fit out | Start of month | 128258.5 | 53944.83 | 74313.67 | 57.94% | 94098.32 | 42273.69 | 69042.09 | 35075.75 | 33966.34 | 49.2% |  | 25056.23 | 7197.94 | 17858.29 | 71.27% | 501.83 | 143 | 358.83 | 71.5% | 40% | 81.6164 | 68.0712 | 21.64% | 26.63% | Hours calc for monthly claims | -112 | -112 | -26847.46
|  | Week 1 | 128258.5 | 53944.83 | 74313.67 | 57.94% | 94098.32 | 49261.61 | 69042.09 | 35683.74 | 33358.35 | 48.32% |  | 25056.23 | 13577.87 | 11478.36 | 45.81% | 501.83 | 299.5 | 202.33 | 40.32% |  | 15.6368 | 68.0712 | 8.68% | 26.63% | Materials calc for monthly claims | -26847.46
|  | Week 2 | 128258.5 | 53944.83 | 74313.67 | 57.94% | 94098.32 | 50255.78 | 69042.09 | 35683.74 | 33358.35 | 48.32% |  | 25056.23 | 14572.04 | 10484.19 | 41.84% | 501.83 | 325.75 | 176.08 | 35.09% |  | 11.3248 | 68.0712 | 6.84% | 26.63%
|  | Week 3 | 128258.5 | 53944.83 | 74313.67 | 57.94% | 94098.32 | 51662.71 | 69042.09 | 35998.79 | 33043.3 | 47.86% |  | 25056.23 | 15663.92 | 9392.31 | 37.48% | 501.83 | 354.75 | 147.08 | 29.31% |  | 6.433 | 68.0712 | 4.23% | 26.63% | Estimated months claim | 0
|  | Week 4 | 128258.4993 | 115314.55 | 12943.9493 | 10.09% | 94098.3169 | 56767.07 | 69042.0889 | 40878.83 | 28163.2588 | 40.79% |  | 25056.228 | 15888.24 | 9167.988 | 36.59% | 501.83 | 358.75 | 143.08 | 28.51% |  | 163.1986 | 68.0712 | 50.77% | 26.63%
|  | Week 5 | 128258.4993 | 115314.55 | 12943.9493 | 10.09% | 94098.3169 | 58294.37 | 69042.0889 | 42068.63 | 26973.4588 | 39.07% |  | 25056.228 | 16225.74 | 8830.488 | 35.24% | 501.83 | 366.25 | 135.58 | 27.02% |  | 155.6865 | 68.0712 | 49.45% | 26.63% |  |  | -112 | -26847.46
8887 | Tenancy 2 - Fisher Fit out | Start of month | 65693.36 | 33326.49 | 32366.87 | 49.27% | 50582.37 | 25211.58 | 39438.99 | 20456.64 | 18982.35 | 48.13% | 0% | 11143.38 | 4754.94 | 6388.44 | 57.33% | 223.22 | 104.25 | 118.97 | 53.3% | 40% | 77.8409 | 67.6955 | 24.35% | 23% | Hours calc for monthly claims | -86.75 | -86.75 | -15639.05
|  | Week 1 | 65693.36 | 33326.49 | 32366.87 | 49.27% | 50582.37 | 25196.36 | 39438.99 | 20036.42 | 19402.57 | 49.2% |  | 11143.38 | 5159.94 | 5983.44 | 53.7% | 223.22 | 113.25 | 109.97 | 49.27% |  | 71.7892 | 67.6955 | 24.4% | 23% | Materials calc for monthly claims | -15639.05
|  | Week 2 | 65693.36 | 33326.49 | 32366.87 | 49.27% | 50582.37 | 25196.36 | 39438.99 | 20036.42 | 19402.57 | 49.2% |  | 11143.38 | 5159.94 | 5983.44 | 53.7% | 223.22 | 113.25 | 109.97 | 49.27% |  | 71.7892 | 67.6955 | 24.4% | 23%
|  | Week 3 | 65693.36 | 33326.49 | 32366.87 | 49.27% | 50582.37 | 25764.18 | 39438.99 | 20036.42 | 19402.57 | 49.2% |  | 11143.38 | 5727.76 | 5415.62 | 48.6% | 223.22 | 129 | 94.22 | 42.21% |  | 58.6226 | 67.6955 | 22.69% | 23% | Estimated months claim | 0
|  | Week 4 | 65693.3585 | 61277.97 | 4415.3885 | 6.721% | 50582.3679 | 29601.04 | 39438.9903 | 20244.31 | 19194.6803 | 48.67% |  | 11143.3776 | 9356.73 | 1786.6476 | 16.03% | 223.22 | 216.5 | 6.72 | 3.01% |  | 146.3138 | 67.6955 | 51.69% | 23%
|  | Week 5 | 65693.3585 | 61277.97 | 4415.3885 | 6.721% | 50582.3679 | 29601.04 | 39438.9903 | 20244.31 | 19194.6803 | 48.67% |  | 11143.3776 | 9356.73 | 1786.6476 | 16.03% | 223.22 | 216.5 | 6.72 | 3.01% |  | 146.3138 | 67.6955 | 51.69% | 23% |  |  | -86.75 | -15639.05
8670 | Studio DB - tautara fit out | Start of month | 155296.79 | 127814.48 | 27482.31 | 17.7% | 109364.97 | 95320.51 | 75135.01 | 71614.55 | 3520.46 | 4.686% |  | 34229.96 | 23705.96 | 10524 | 30.74% | 685.48 | 502.25 | 183.23 | 26.73% | 30% | 64.6968 | 67.0068 | 25.42% | 29.58% | Hours calc for monthly claims | -269 | -269 | -66399.88
|  | Week 1 | 155296.79 | 127814.48 | 27482.31 | 17.7% | 109364.97 | 96483.38 | 75135.01 | 71221.34 | 3913.67 | 5.209% |  | 34229.96 | 25262.04 | 8967.92 | 26.2% | 685.48 | 533.75 | 151.73 | 22.13% |  | 58.7 | 67.0068 | 24.51% | 29.58% | Materials calc for monthly claims | -66399.88
|  | Week 2 | 155296.79 | 127814.48 | 27482.31 | 17.7% | 109364.97 | 98837.32 | 75135.01 | 71357.43 | 3777.58 | 5.028% |  | 34229.96 | 27479.89 | 6750.07 | 19.72% | 685.48 | 578.5 | 106.98 | 15.61% |  | 50.0902 | 67.0068 | 22.67% | 29.58%
|  | Week 3 | 155296.79 | 127814.48 | 27482.31 | 17.7% | 109364.97 | 100761.26 | 75135.01 | 71552.81 | 3582.2 | 4.768% |  | 34229.96 | 29208.45 | 5021.51 | 14.67% | 685.48 | 610 | 75.48 | 11.01% |  | 44.3495 | 67.0068 | 21.17% | 29.58% | Estimated months claim | 0
|  | Week 4 | 155296.7901 | 155296.8 | -0.0098725 | -6.357e-06% | 109364.9721 | 110254.03 | 75135.0159 | 78269.58 | -3134.5641 | -4.172% |  | 34229.9562 | 31984.45 | 2245.5062 | 6.56% | 685.48 | 669 | 16.48 | 2.404% |  | 67.3285 | 67.0068 | 29% | 29.58%
|  | Week 5 | 155296.7901 | 155296.8 | -0.0098725 | -6.357e-06% | 109364.9721 | 114553.44 | 75135.0159 | 81185.24 | -6050.2241 | -8.052% |  | 34229.9562 | 33368.2 | 861.7562 | 2.518% | 685.48 | 699.75 | -14.27 | -2.082% |  | 58.2256 | 67.0068 | 26.24% | 29.58% |  |  | -269 | -66399.88
8907 | 35 Mania | Start of month | 20420.56 | 20420.56 | 0 | 0% | 15859.68 | 13435.12 | 12689.1 | 11478.25 | 1210.85 | 9.542% |  | 3170.58 | 1956.87 | 1213.71 | 38.28% | 63.5 | 48.25 | 15.25 | 24.02% | 40% | 144.776 | 71.825 | 34.21% | 22.33% | Hours calc for monthly claims | -26.75 | -26.75 | -11159.14
|  | Week 1 | 20420.56 | 20420.56 | 0 | 0% | 15859.68 | 13435.12 | 12689.1 | 11478.25 | 1210.85 | 9.542% |  | 3170.58 | 1956.87 | 1213.71 | 38.28% | 63.5 | 48.25 | 15.25 | 24.02% |  | 144.776 | 71.825 | 34.21% | 22.33% | Materials calc for monthly claims | -11159.14
|  | Week 2 | 20420.56 | 20420.56 | 0 | 0% | 15859.68 | 13435.12 | 12689.1 | 11478.25 | 1210.85 | 9.542% |  | 3170.58 | 1956.87 | 1213.71 | 38.28% | 63.5 | 48.25 | 15.25 | 24.02% |  | 144.776 | 71.825 | 34.21% | 22.33%
|  | Week 3 | [24 empty] | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -26.75 | -11159.14
9065 | Cooltranz stage 4 | Start of month | 47801.68 | 10650.43 | 37151.25 | 77.72% | 35572.59 | 9981.43 | 27136.55 | 9832.65 | 17303.9 | 63.77% |  | 8436.04 | 148.78 | 8287.26 | 98.24% | 169.32 | 2.75 | 166.57 | 98.38% |  | 243.2727 | 72.2248 | 6.28% | 25.58% | Hours calc for monthly claims |  |  | -5397.27
|  | Week 1 | 47801.68 | 10650.43 | 37151.25 | 77.72% | 35572.59 | 10547.08 | 27136.55 | 10398.3 | 16738.25 | 61.68% |  | 8436.04 | 148.78 | 8287.26 | 98.24% | 169.32 | 2.75 | 166.57 | 98.38% |  | 37.5818 | 72.2248 | 0.97% | 25.58% | Materials calc for monthly claims | -5397.27
|  | Week 2 | 53029.71 | 10650.43 | 42379.28 | 79.92% | 39055.78 | 16807.92 | 29537.29 | 16659.14 | 12878.15 | 43.6% |  | 9518.49 | 148.78 | 9369.71 | 98.44% | 193.32 | 2.75 | 190.57 | 98.58% |  | -2239.0873 | 72.284 | -57.81% | 26.35%
|  | Week 3 | 53029.71 | 10650.43 | 42379.28 | 79.92% | 39055.78 | 17736.52 | 29537.29 | 17587.74 | 11949.55 | 40.46% |  | 9518.49 | 148.78 | 9369.71 | 98.44% | 193.32 | 2.75 | 190.57 | 98.58% |  | -2576.76 | 72.284 | -66.53% | 26.35% | Estimated months claim | 0
|  | Week 4 | 53029.7146 | 10650.43 | 42379.2846 | 79.92% | 39055.7783 | 22176.82 | 29537.2898 | 19672.02 | 9865.2698 | 33.4% |  | 9518.4885 | 2504.8 | 7013.6885 | 73.68% | 193.32 | 52.75 | 140.57 | 72.71% |  | -218.5098 | 72.284 | -108.2% | 26.35%
|  | Week 5 | 53029.7146 | 29715.67 | 23314.0446 | 43.96% | 39055.7783 | 30684.03 | 29537.2898 | 26364.31 | 3172.9798 | 10.74% |  | 9518.4885 | 4319.72 | 5198.7685 | 54.62% | 193.32 | 90.75 | 102.57 | 53.06% |  | -10.6706 | 72.284 | -3.26% | 26.35% |  |  |  | -5397.27
9259 | Andrew Reeve Stage 2 | Start of month | 77166.16 | 44764.99 | 32401.17 | 41.99% | 54302.66 | 31918.93 | 31383.39 | 27205.52 | 4177.87 | 13.31% |  | 22919.27 | 4713.41 | 18205.86 | 79.43% | 470.62 | 96.25 | 374.37 | 79.55% | 0% | 133.4656 | 48.5817 | 28.7% | 29.63% | Hours calc for monthly claims
|  | Week 1 | 77166.16 | 44764.99 | 32401.17 | 41.99% | 54302.66 | 29696.65 | 31383.39 | 23592.6 | 7790.79 | 24.82% |  | 22919.27 | 6104.05 | 16815.22 | 73.37% | 470.62 | 120.25 | 350.37 | 74.45% |  | 125.3084 | 48.5817 | 33.66% | 29.63% | Materials calc for monthly claims
|  | Week 2 | 77408.3 | 44764.99 | 32643.31 | 42.17% | 54446.73 | 31669.14 | 31451.7 | 23876.59 | 7575.11 | 24.08% |  | 22995.03 | 7792.55 | 15202.48 | 66.11% | 472.14 | 156 | 316.14 | 66.96% |  | 83.9478 | 48.633 | 29.25% | 29.66%
|  | Week 3 | 78753.07 | 44764.99 | 33988.08 | 43.16% | 55589.78 | 32417.98 | 32594.75 | 24016.8 | 8577.95 | 26.32% |  | 22995.03 | 8401.18 | 14593.85 | 63.47% | 472.14 | 167.25 | 304.89 | 64.58% |  | 73.8237 | 49.0602 | 27.58% | 29.41% | Estimated months claim | 0
|  | Week 4 | 78753.0664 | 44764.99 | 33988.0764 | 43.16% | 55589.7822 | 41600.05 | 32594.7534 | 33198.87 | -604.1166 | -1.853% |  | 22995.0288 | 8401.18 | 14593.8488 | 63.47% | 472.14 | 167.25 | 304.89 | 64.58% |  | 18.9234 | 49.0602 | 7.07% | 29.41%
|  | Week 5 | 78753.0664 | 61764.82 | 16988.2464 | 21.57% | 55589.7822 | 47207.1 | 32594.7534 | 35050.6 | -2455.8466 | -7.534% |  | 22995.0288 | 12156.5 | 10838.5288 | 47.13% | 472.14 | 237.25 | 234.89 | 49.75% |  | 61.3603 | 49.0602 | 23.57% | 29.41%
8352 | 5 Sanscrit Place | Start of month | 25467.84 | 19598.41 | 5869.43 | 23.05% | 16606.83 | 12958.24 | 9659.99 | 5354.12 | 4305.87 | 44.57% | 0% | 6946.84 | 7604.12 | -657.28 | -9.462% | 139.07 | 147.75 | -8.68 | -6.241% |  | 44.9419 | 63.7162 | 33.88% | 34.79% | Hours calc for monthly claims | -143.25 | -143.25 | -5569.48
|  | Week 1 | 25467.84 | 19598.41 | 5869.43 | 23.05% | 16606.83 | 12958.24 | 9659.99 | 5354.12 | 4305.87 | 44.57% |  | 6946.84 | 7604.12 | -657.28 | -9.462% | 139.07 | 147.75 | -8.68 | -6.241% |  | 44.9419 | 63.7162 | 33.88% | 34.79% | Materials calc for monthly claims | -5569.48
|  | Week 2 | 25467.84 | 19598.41 | 5869.43 | 23.05% | 16606.83 | 11832.36 | 9659.99 | 4228.24 | 5431.75 | 56.23% |  | 6946.84 | 7604.12 | -657.28 | -9.462% | 139.07 | 147.75 | -8.68 | -6.241% |  | 52.5621 | 63.7162 | 39.63% | 34.79%
|  | Week 3 | 25467.84 | 19598.41 | 5869.43 | 23.05% | 16606.83 | 12517.98 | 9659.99 | 4823.58 | 4836.41 | 50.07% |  | 6946.84 | 7694.4 | -747.56 | -10.76% | 139.07 | 147.75 | -8.68 | -6.241% |  | 47.9217 | 63.7162 | 36.13% | 34.79% | Estimated months claim | 0
|  | Week 4 | 25467.8441 | 19598.41 | 5869.4341 | 23.05% | 16606.8299 | 14118.07 | 9659.9867 | 5298.48 | 4361.5067 | 45.15% |  | 6946.8432 | 8819.59 | -1872.7468 | -26.96% | 139.07 | 167.75 | -28.68 | -20.62% |  | 32.6697 | 63.7162 | 27.96% | 34.79%
|  | Week 5 | 25467.8441 | 19598.41 | 5869.4341 | 23.05% | 16606.8299 | 14118.07 | 9659.9867 | 5298.48 | 4361.5067 | 45.15% |  | 6946.8432 | 8819.59 | -1872.7468 | -26.96% | 139.07 | 167.75 | -28.68 | -20.62% |  | 32.6697 | 63.7162 | 27.96% | 34.79% |  |  | -143.25 | -5569.48
8234 | Melhuish House | Start of month | 37083.03 | 36381.33 | 701.7 | 1.892% | 27002.93 | 26005.99 | 15440.32 | 14988.44 | 451.88 | 2.927% | 0% | 11562.61 | 11017.55 | 545.06 | 4.714% | 231.75 | 224.25 | 7.5 | 3.236% |  | 46.2668 | 43.4956 | 28.52% | 27.18% | Hours calc for monthly claims | -148.5 | -148.5 | -14143.19
|  | Week 1 | 37083.03 | 36381.33 | 701.7 | 1.892% | 27002.93 | 25060.53 | 15440.32 | 13974.73 | 1465.59 | 9.492% |  | 11562.61 | 11085.8 | 476.81 | 4.124% | 231.75 | 225.5 | 6.25 | 2.697% |  | 50.2031 | 43.4956 | 31.12% | 27.18% | Materials calc for monthly claims | -14143.19
|  | Week 2 | 37083.03 | 36381.33 | 701.7 | 1.892% | 27002.93 | 25060.53 | 15440.32 | 13974.73 | 1465.59 | 9.492% |  | 11562.61 | 11085.8 | 476.81 | 4.124% | 231.75 | 225.5 | 6.25 | 2.697% |  | 50.2031 | 43.4956 | 31.12% | 27.18%
|  | Week 3 | 37083.03 | 36381.33 | 701.7 | 1.892% | 27002.93 | 25060.53 | 15440.32 | 13974.73 | 1465.59 | 9.492% |  | 11562.61 | 11085.8 | 476.81 | 4.124% | 231.75 | 225.5 | 6.25 | 2.697% |  | 50.2031 | 43.4956 | 31.12% | 27.18% | Estimated months claim | 0
|  | Week 4 | 37083.0314 | 36381.33 | 701.7014 | 1.892% | 27002.9329 | 25103.82 | 15440.3245 | 13974.73 | 1465.5945 | 9.492% |  | 11562.6084 | 11129.09 | 433.5184 | 3.749% | 231.75 | 225.5 | 6.25 | 2.697% |  | 50.0111 | 43.4956 | 31% | 27.18%
|  | Week 5 | 37083.0314 | 36381.33 | 701.7014 | 1.892% | 27002.9329 | 25103.82 | 15440.3245 | 13974.73 | 1465.5945 | 9.492% |  | 11562.6084 | 11129.09 | 433.5184 | 3.749% | 231.75 | 225.5 | 6.25 | 2.697% |  | 50.0111 | 43.4956 | 31% | 27.18% |  |  | -148.5 | -14143.19
8214 | 6 Tiroroa Lane | Start of month | 26186.14 | 5762.27 | 20423.87 | 77.99% | 19428.98 | 7925.81 | 12051.32 | 7679.91 | 4371.41 | 36.27% | 0% | 7377.66 | 245.9 | 7131.76 | 96.67% | 147.9 | 5 | 142.9 | 96.62% |  | -432.708 | 45.6874 | -37.55% | 25.8% | Hours calc for monthly claims | -5 | -5 | -7679.91
|  | Week 1 | 26186.14 | 5762.27 | 20423.87 | 77.99% | 19428.98 | 7925.81 | 12051.32 | 7679.91 | 4371.41 | 36.27% |  | 7377.66 | 245.9 | 7131.76 | 96.67% | 147.9 | 5 | 142.9 | 96.62% |  | -432.708 | 45.6874 | -37.55% | 25.8% | Materials calc for monthly claims | -7679.91
|  | Week 2 | 26186.14 | 5762.27 | 20423.87 | 77.99% | 19428.98 | 7925.81 | 12051.32 | 7679.91 | 4371.41 | 36.27% |  | 7377.66 | 245.9 | 7131.76 | 96.67% | 147.9 | 5 | 142.9 | 96.62% |  | -432.708 | 45.6874 | -37.55% | 25.8%
|  | Week 3 | 26186.14 | 5762.27 | 20423.87 | 77.99% | 19428.98 | 7925.81 | 12051.32 | 7679.91 | 4371.41 | 36.27% |  | 7377.66 | 245.9 | 7131.76 | 96.67% | 147.9 | 5 | 142.9 | 96.62% |  | -432.708 | 45.6874 | -37.55% | 25.8% | Estimated months claim | 0
|  | Week 4 | 26186.1354 | 5762.27 | 20423.8654 | 77.99% | 19428.976 | 8019.36 | 12051.3142 | 7687.13 | 4364.1842 | 36.21% |  | 7377.6618 | 332.23 | 7045.4318 | 95.5% | 147.9 | 6.5 | 141.4 | 95.61% |  | -347.2446 | 45.6874 | -39.17% | 25.8%
|  | Week 5 | 26186.1354 | 5762.27 | 20423.8654 | 77.99% | 19428.976 | 8019.36 | 12051.3142 | 7687.13 | 4364.1842 | 36.21% |  | 7377.6618 | 332.23 | 7045.4318 | 95.5% | 147.9 | 6.5 | 141.4 | 95.61% |  | -347.2446 | 45.6874 | -39.17% | 25.8% |  |  | -5 | -7679.91
6792 | Major Hornbrook | Start of month | 32473.02 | 33188.03 | -715.01 | -2.202% | 23075.07 | 30925.21 | 12691.21 | 15184.27 | -2493.06 | -19.64% | 0% | 10383.86 | 15740.94 | -5357.08 | -51.59% | 208.2 | 317.25 | -109.05 | -52.38% |  | 7.1326 | 45.1391 | 6.82% | 28.94% | Hours calc for monthly claims | -317.25 | -317.25 | -16562.52
|  | Week 1 | 32473.02 | 33188.03 | -715.01 | -2.202% | 23075.07 | 30925.21 | 12691.21 | 15184.27 | -2493.06 | -19.64% |  | 10383.86 | 15740.94 | -5357.08 | -51.59% | 208.2 | 317.25 | -109.05 | -52.38% |  | 7.1326 | 45.1391 | 6.82% | 28.94% | Materials calc for monthly claims | -16562.52
|  | Week 2 | 32473.02 | 32473.03 | -0.01 | -3.079e-05% | 23075.07 | 31170.94 | 12691.21 | 15089.13 | -2397.92 | -18.89% |  | 10383.86 | 16081.81 | -5697.95 | -54.87% | 208.2 | 324.25 | -116.05 | -55.74% |  | 4.0157 | 45.1391 | 4.01% | 28.94%
|  | Week 3 | [24 empty] | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -317.25 | -16562.52
8840 | Inline Architecture | Start of month | 58902.56 | 0 | 58902.56 | 100% | 37601.88 | 44893.89 | 21415.85 | 23634.19 | -2218.34 | -10.36% | 0% | 16186.03 | 21259.7 | -5073.67 | -31.35% | 324.19 | 461.5 | -137.31 | -42.35% | 0% | -20.4539 | 65.7043 | -26.62% | 36.16% | Hours calc for monthly claims | -204.75 | -204.75 | -12155.27
|  | Week 1 | 58902.56 | 0 | 58902.56 | 100% | 37601.88 | 45817.77 | 21415.85 | 23939.39 | -2523.54 | -11.78% |  | 16186.03 | 21878.38 | -5692.35 | -35.17% | 324.19 | 472.75 | -148.56 | -45.82% |  | 48.9732 | 65.7043 | 33.57% | 36.16% | Materials calc for monthly claims | -12155.27
|  | Week 2 | 58902.56 | 0 | 58902.56 | 100% | 37601.88 | 45817.77 | 21415.85 | 23939.39 | -2523.54 | -11.78% |  | 16186.03 | 21878.38 | -5692.35 | -35.17% | 324.19 | 472.75 | -148.56 | -45.82% |  | 48.9732 | 65.7043 | 33.57% | 36.16%
|  | Week 3 | [24 empty] | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -204.75 | -12155.27
8769 | Percival Bach | Start of month | 21404.82 | 0 | 21404.82 | 100% | 17514.09 | 0 | 13318.88 | 0 | 13318.88 | 100% | 0% | 4195.21 | 0 | 4195.21 | 100% | 84.05 | 0 | 84.05 | 100% | 0% | 0 | 46.2906 | 0% | 18.18% | Hours calc for monthly claims
|  | Week 1 | 21404.82 | 0 | 21404.82 | 100% | 17514.09 | 0 | 13318.88 | 0 | 13318.88 | 100% |  | 4195.21 | 0 | 4195.21 | 100% | 84.05 | 0 | 84.05 | 100% |  | 0 | 46.2906 | 0% | 18.18% | Materials calc for monthly claims
|  | Week 2 | 21404.82 | 0 | 21404.82 | 100% | 17514.09 | 0 | 13318.88 | 0 | 13318.88 | 100% |  | 4195.21 | 0 | 4195.21 | 100% | 84.05 | 0 | 84.05 | 100% |  | 0 | 46.2906 | 0% | 18.18%
|  | Week 3 | 21404.82 | 0 | 21404.82 | 100% | 17514.09 | 0 | 13318.88 | 0 | 13318.88 | 100% |  | 4195.21 | 0 | 4195.21 | 100% | 84.05 | 0 | 84.05 | 100% |  | 0 | 46.2906 | 0% | 18.18% | Estimated months claim | 0
|  | Week 4 | 21978.6562 | 0 | 21978.6562 | 100% | 17872.7669 | 0 | 13579.6367 | 0 | 13579.6367 | 100% |  | 4293.1302 | 0 | 4293.1302 | 100% | 86.01 | 0 | 86.01 | 100% |  | 0 | 47.7373 | 0% | 18.68%
|  | Week 5 | 20278.4568 | 0 | 20278.4568 | 100% | 16648.0568 | 58.32 | 12536.9828 | 58.32 | 12478.6628 | 99.53% |  | 4111.074 | 0 | 4111.074 | 100% | 82.37 | 0 | 82.37 | 100% |  | 0 | 44.0743 | 0% | 17.9%
7901 | St Albans Street | Start of month | 100987.51 | 15366.74 | 85620.77 | 84.78% | 82694.87 | 56237.25 | 68214.25 | 51549.24 | 16665.01 | 24.43% |  | 14480.62 | 4688.01 | 9792.61 | 67.63% | 290.15 | 102.5 | 187.65 | 64.67% |  | -398.7367 | 63.0455 | -266% | 18.11% | Hours calc for monthly claims |  |  | -12186.08
|  | Week 1 | 100987.51 | 67407.3 | 33580.21 | 33.25% | 82694.87 | 56763.31 | 68214.25 | 51957.8 | 16256.45 | 23.83% |  | 14480.62 | 4805.51 | 9675.11 | 66.81% | 290.15 | 105 | 185.15 | 63.81% |  | 101.3713 | 63.0455 | 15.79% | 18.11% | Materials calc for monthly claims | -12186.08
|  | Week 2 | 105896.96 | 67407.3 | 38489.66 | 36.35% | 85934.2 | 56814.23 | 70065.72 | 51957.8 | 18107.92 | 25.84% |  | 15868.48 | 4856.43 | 11012.05 | 69.4% | 317.92 | 106 | 211.92 | 66.66% |  | 99.9346 | 62.7918 | 15.72% | 18.85%
|  | Week 3 | 105896.96 | 67407.3 | 38489.66 | 36.35% | 85934.2 | 56814.97 | 70065.72 | 51957.8 | 18107.92 | 25.84% |  | 15868.48 | 4857.17 | 11011.31 | 69.39% | 317.92 | 106 | 211.92 | 66.66% |  | 99.9276 | 62.7918 | 15.71% | 18.85% | Estimated months claim | 0
|  | Week 4 | 105896.9568 | 79457.73 | 26439.2268 | 24.97% | 85934.2 | 66541.03 | 70065.7156 | 61659.44 | 8406.2756 | 12% |  | 15868.4844 | 4881.59 | 10986.8944 | 69.24% | 317.92 | 106 | 211.92 | 66.66% |  | 121.8557 | 62.7918 | 16.26% | 18.85%
|  | Week 5 | 105896.9568 | 79457.73 | 26439.2268 | 24.97% | 85934.2 | 64275.8 | 70065.7156 | 59394.21 | 10671.5056 | 15.23% |  | 15868.4844 | 4881.59 | 10986.8944 | 69.24% | 317.92 | 106 | 211.92 | 66.66% |  | 143.2258 | 62.7918 | 19.11% | 18.85% |  |  |  | -12186.08
8923 | 4 Perry St | Start of month | 31802.41 | 14370.83 | 17431.58 | 54.81% | 23448.14 | 12360.83 | 15632.03 | 11772.08 | 3859.95 | 24.69% |  | 7816.11 | 588.75 | 7227.36 | 92.47% | 156.69 | 11.5 | 145.19 | 92.66% | 0% | 174.7826 | 53.3172 | 13.99% | 26.27% | Hours calc for monthly claims | -2 | -2 | -11154.51
|  | Week 1 | 31802.41 | 16498.64 | 15303.77 | 48.12% | 23448.14 | 12360.83 | 15632.03 | 11772.08 | 3859.95 | 24.69% |  | 7816.11 | 588.75 | 7227.36 | 92.47% | 156.69 | 11.5 | 145.19 | 92.66% |  | 359.8096 | 53.3172 | 25.08% | 26.27% | Materials calc for monthly claims | -11154.51
|  | Week 2 | 31802.41 | 16498.64 | 15303.77 | 48.12% | 23448.14 | 12360.83 | 15632.03 | 11772.08 | 3859.95 | 24.69% |  | 7816.11 | 588.75 | 7227.36 | 92.47% | 156.69 | 11.5 | 145.19 | 92.66% |  | 359.8096 | 53.3172 | 25.08% | 26.27%
|  | Week 3 | 31802.41 | 16498.64 | 15303.77 | 48.12% | 23448.14 | 12360.83 | 15632.03 | 11772.08 | 3859.95 | 24.69% |  | 7816.11 | 588.75 | 7227.36 | 92.47% | 156.69 | 11.5 | 145.19 | 92.66% |  | 359.8096 | 53.3172 | 25.08% | 26.27% | Estimated months claim | 0
|  | Week 4 | 31802.4137 | 16498.64 | 15303.7737 | 48.12% | 23448.1426 | 12360.83 | 15632.0284 | 11772.08 | 3859.9484 | 24.69% |  | 7816.1142 | 588.75 | 7227.3642 | 92.47% | 156.69 | 11.5 | 145.19 | 92.66% |  | 359.8096 | 53.3172 | 25.08% | 26.27%
|  | Week 5 | 31802.4137 | 16498.64 | 15303.7737 | 48.12% | 23448.1426 | 12360.83 | 15632.0284 | 11772.08 | 3859.9484 | 24.69% |  | 7816.1142 | 588.75 | 7227.3642 | 92.47% | 156.69 | 11.5 | 145.19 | 92.66% |  | 359.8096 | 53.3172 | 25.08% | 26.27% |  |  | -2 | -11154.51
7864 | Ryans House | Start of month | 30749.24 | 30749.24 | 0 | 0% | 22587.89 | 25905.23 | 12565.06 | 11805.46 | 759.6 | 6.045% | 0% | 10022.83 | 14099.77 | -4076.94 | -40.68% | 200.82 | 283.75 | -82.93 | -41.3% |  | 17.0714 | 40.6401 | 15.75% | 26.54% | Hours calc for monthly claims | -266.75 | -266.75 | -11702.32
|  | Week 1 | 30749.24 | 30749.24 | 0 | 0% | 22587.89 | 25905.23 | 12565.06 | 11805.46 | 759.6 | 6.045% |  | 10022.83 | 14099.77 | -4076.94 | -40.68% | 200.82 | 283.75 | -82.93 | -41.3% |  | 17.0714 | 40.6401 | 15.75% | 26.54% | Materials calc for monthly claims | -11702.32
|  | Week 2 | 30749.24 | 30749.24 | 0 | 0% | 22587.89 | 25891.86 | 12565.06 | 11792.09 | 772.97 | 6.152% |  | 10022.83 | 14099.77 | -4076.94 | -40.68% | 200.82 | 283.75 | -82.93 | -41.3% |  | 17.1185 | 40.6401 | 15.8% | 26.54%
|  | Week 3 | [24 empty] | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -266.75 | -11702.32
7912 | 71A Fendalton Road | Start of month | 268228.26 | 9034.53 | 259193.73 | 96.63% | 238611.58 | 6362.08 | 214154.25 | 3465.35 | 210688.9 | 98.38% |  | 24457.33 | 2896.73 | 21560.6 | 88.16% | 497.55 | 58.25 | 439.3 | 88.29% |  | 45.879 | 59.525 | 29.58% | 11.04% | Hours calc for monthly claims
|  | Week 1 | 268228.26 | 9034.53 | 259193.73 | 96.63% | 238611.58 | 6362.08 | 214154.25 | 3465.35 | 210688.9 | 98.38% |  | 24457.33 | 2896.73 | 21560.6 | 88.16% | 497.55 | 58.25 | 439.3 | 88.29% |  | 45.879 | 59.525 | 29.58% | 11.04% | Materials calc for monthly claims
|  | Week 2 | 268228.26 | 9034.53 | 259193.73 | 96.63% | 238611.58 | 6362.08 | 214154.25 | 3465.35 | 210688.9 | 98.38% |  | 24457.33 | 2896.73 | 21560.6 | 88.16% | 497.55 | 58.25 | 439.3 | 88.29% |  | 45.879 | 59.525 | 29.58% | 11.04%
|  | Week 3 | [24 empty] | Estimated months claim | 0
Week 4
Week 5
8360 | Dixon House | Start of month | 32773.41 | 32773.41 | 0 | 0% | 22750.99 | 22254.11 | 12243.41 | 9324.41 | 2919 | 23.84% |  | 10507.58 | 12929.7 | -2422.12 | -23.05% | 210.6 | 260.75 | -50.15 | -23.81% |  | 40.3425 | 47.5898 | 32.1% | 30.58% | Hours calc for monthly claims | -260.75 | -260.75 | -9324.41
|  | Week 1 | 32773.41 | 32773.41 | 0 | 0% | 22750.99 | 22254.11 | 12243.41 | 9324.41 | 2919 | 23.84% |  | 10507.58 | 12929.7 | -2422.12 | -23.05% | 210.6 | 260.75 | -50.15 | -23.81% |  | 40.3425 | 47.5898 | 32.1% | 30.58% | Materials calc for monthly claims | -9324.41
|  | Week 2 | 32773.41 | 32773.41 | 0 | 0% | 22750.99 | 22254.11 | 12243.41 | 9324.41 | 2919 | 23.84% |  | 10507.58 | 12929.7 | -2422.12 | -23.05% | 210.6 | 260.75 | -50.15 | -23.81% |  | 40.3425 | 47.5898 | 32.1% | 30.58%
|  | Week 3 | [24 empty] | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -260.75 | -9324.41
8337 | Waimak Dairys | Start of month | 17899.33 | 13424.5 | 4474.83 | 25% | 13919.4 | 10402.37 | 8410.93 | 7278.38 | 1132.55 | 13.47% |  | 5508.47 | 3123.99 | 2384.48 | 43.29% | 110.44 | 60.75 | 49.69 | 44.99% |  | 49.747 | 36.037 | 22.51% | 22.24% | Hours calc for monthly claims | -44.75 | -44.75
|  | Week 1 | 17899.33 | 13424.5 | 4474.83 | 25% | 13919.4 | 10402.37 | 8410.93 | 7278.38 | 1132.55 | 13.47% |  | 5508.47 | 3123.99 | 2384.48 | 43.29% | 110.44 | 60.75 | 49.69 | 44.99% |  | 49.747 | 36.037 | 22.51% | 22.24% | Materials calc for monthly claims
|  | Week 2 | 17899.33 | 13424.5 | 4474.83 | 25% | 13919.4 | 10402.37 | 8410.93 | 7278.38 | 1132.55 | 13.47% |  | 5508.47 | 3123.99 | 2384.48 | 43.29% | 110.44 | 60.75 | 49.69 | 44.99% |  | 49.747 | 36.037 | 22.51% | 22.24%
|  | Week 3 | 17899.33 | 13424.5 | 4474.83 | 25% | 13919.4 | 12130.47 | 8410.93 | 7623.43 | 787.5 | 9.363% |  | 5508.47 | 4507.04 | 1001.43 | 18.18% | 110.44 | 87 | 23.44 | 21.22% |  | 14.8739 | 36.037 | 9.64% | 22.24% | Estimated months claim | 0
|  | Week 4 | 17899.3331 | 13424.5 | 4474.8331 | 25% | 13919.4013 | 12620.62 | 8410.9273 | 7749.86 | 661.0673 | 7.86% |  | 5508.474 | 4870.76 | 637.714 | 11.58% | 110.44 | 95.5 | 14.94 | 13.53% |  | 8.4176 | 36.037 | 5.99% | 22.24%
|  | Week 5 | 19505.5189 | 19505.52 | -0.0011032 | -5.656e-06% | 14923.5904 | 14052.73 | 8915.0764 | 8190.78 | 724.2964 | 8.124% |  | 6008.514 | 5861.95 | 146.564 | 2.439% | 120.44 | 116.25 | 4.19 | 3.479% |  | 46.9057 | 38.0432 | 27.96% | 23.49% |  |  | -44.75
9240 | Daves Twizel Shack | Start of month | 10827.2 |  | 10827.2 | 100% | 7619.53 |  | 4388.87 | [object Object] | 4388.87 | 100% |  | 3230.66 |  | 3230.66 | 100% | 64.71 |  | 64.71 | 100% |  |  | 49.5699 |  | 29.63% | Hours calc for monthly claims
|  | Week 1 | 10827.2 | 0 | 10827.2 | 100% | 7687.77 | 853.55 | 4437.14 | 853.55 | 3583.59 | 80.76% |  | 3250.63 | 0 | 3250.63 | 100% | 65.13 | 0 | 65.13 | 100% |  | 0 | 48.2026 | 0% | 29% | Materials calc for monthly claims
|  | Week 2 | 10827.2 | 0 | 10827.2 | 100% | 7687.77 | 2116.21 | 4437.14 | 1029.51 | 3407.63 | 76.8% |  | 3250.63 | 1086.7 | 2163.93 | 66.57% | 65.13 | 24.33 | 40.8 | 62.64% |  | -86.9794 | 48.2026 | 0% | 29%
|  | Week 3 | 10827.2 | 0 | 10827.2 | 100% | 7687.77 | 2116.21 | 4437.14 | 1029.51 | 3407.63 | 76.8% |  | 3250.63 | 1086.7 | 2163.93 | 66.57% | 65.13 | 24.33 | 40.8 | 62.64% |  | -86.9794 | 48.2026 | 0% | 29% | Estimated months claim | 0
|  | Week 4 | 10827.2026 | 0 | 10827.2026 | 100% | 7687.7651 | 2116.21 | 4437.1337 | 1029.51 | 3407.6237 | 76.8% |  | 3250.6314 | 1086.7 | 2163.9314 | 66.57% | 65.13 | 24.33 | 40.8 | 62.64% |  | -86.9794 | 48.2026 | 0% | 29%
|  | Week 5 | 10827.2026 | 0 | 10827.2026 | 100% | 7687.7651 | 2097.39 | 4437.1337 | 1010.69 | 3426.4437 | 77.22% |  | 3250.6314 | 1086.7 | 2163.9314 | 66.57% | 65.13 | 24.33 | 40.8 | 62.64% |  | 53.1825 | 48.2026 | 38.15% | 29%
7428 | FAB Pegasus Lakeside | Start of month | 146237.11 | 125386.21 | 20850.9 | 14.26% | 114651.87 | 102882.12 | 82888.08 | 77739.84 | 5148.24 | 6.211% |  | 31763.79 | 25142.28 | 6621.51 | 20.85% | 659.73 | 505.25 | 154.48 | 23.42% |  | 44.5405 | 47.876 | 17.95% | 21.6% | Hours calc for monthly claims | -304.75 | -304.75
|  | Week 1 | 146237.11 | 125386.21 | 20850.9 | 14.26% | 114651.87 | 105511.63 | 82888.08 | 78161.06 | 4727.02 | 5.703% |  | 31763.79 | 27350.57 | 4413.22 | 13.89% | 659.73 | 548.75 | 110.98 | 16.82% |  | 36.2179 | 47.876 | 15.85% | 21.6% | Materials calc for monthly claims
|  | Week 2 | 146237.11 | 125386.21 | 20850.9 | 14.26% | 114651.87 | 105655.21 | 82888.08 | 78304.64 | 4583.44 | 5.53% |  | 31763.79 | 27350.57 | 4413.22 | 13.89% | 659.73 | 548.75 | 110.98 | 16.82% |  | 35.9563 | 47.876 | 15.74% | 21.6%
|  | Week 3 | 146237.11 | 125386.21 | 20850.9 | 14.26% | 114651.87 | 105657.8 | 82888.08 | 78304.64 | 4583.44 | 5.53% |  | 31763.79 | 27353.16 | 4410.63 | 13.89% | 659.73 | 548.75 | 110.98 | 16.82% |  | 35.9515 | 47.876 | 15.73% | 21.6% | Estimated months claim | 0
|  | Week 4 | 146237.1072 | 125386.21 | 20850.8972 | 14.26% | 114651.8654 | 105824.3 | 82888.0784 | 78304.64 | 4583.4384 | 5.53% |  | 31763.787 | 27519.66 | 4244.127 | 13.36% | 659.73 | 548.75 | 110.98 | 16.82% |  | 35.6481 | 47.876 | 15.6% | 21.6%
|  | Week 5 | 146237.1072 | 125386.21 | 20850.8972 | 14.26% | 114651.8654 | 105507.56 | 82888.0784 | 77881.66 | 5006.4184 | 6.04% |  | 31763.787 | 27625.9 | 4137.887 | 13.03% | 659.73 | 550.75 | 108.98 | 16.52% |  | 36.0938 | 47.876 | 15.85% | 21.6% |  |  | -304.75
0
9351 | Harewood Golf Club | Start of month | 16897.53 | 5491.7 | 11405.83 | 67.5% | 9226.27 | 3702.78 | 2977.11 | 2335.97 | 641.14 | 21.54% |  | 6249.16 | 1366.81 | 4882.35 | 78.13% | 125.17 | 23.75 | 101.42 | 81.03% |  | 75.3229 | 61.2867 | 32.57% | 45.4% | Hours calc for monthly claims | -11.25 | -11.25 | -2298.71
|  | Week 1 | 16897.53 | 5491.7 | 11405.83 | 67.5% | 9226.27 | 3702.78 | 2977.11 | 2335.97 | 641.14 | 21.54% |  | 6249.16 | 1366.81 | 4882.35 | 78.13% | 125.17 | 23.75 | 101.42 | 81.03% |  | 75.3229 | 61.2867 | 32.57% | 45.4% | Materials calc for monthly claims | -2298.71
|  | Week 2 | 16897.53 | 5491.7 | 11405.83 | 67.5% | 9226.27 | 3702.78 | 2977.11 | 2335.97 | 641.14 | 21.54% |  | 6249.16 | 1366.81 | 4882.35 | 78.13% | 125.17 | 23.75 | 101.42 | 81.03% |  | 75.3229 | 61.2867 | 32.57% | 45.4%
|  | Week 3 | 16897.53 | 5491.7 | 11405.83 | 67.5% | 9226.27 | 3702.78 | 2977.11 | 2335.97 | 641.14 | 21.54% |  | 6249.16 | 1366.81 | 4882.35 | 78.13% | 125.17 | 23.75 | 101.42 | 81.03% |  | 75.3229 | 61.2867 | 32.57% | 45.4% | Estimated months claim | 0
|  | Week 4 | 16897.5298 | 5491.7 | 11405.8298 | 67.5% | 9226.2731 | 5421.03 | 2977.1135 | 2842.28 | 134.8335 | 4.529% |  | 6249.1596 | 2578.75 | 3670.4096 | 58.73% | 125.17 | 49.25 | 75.92 | 60.65% |  | 1.4349 | 61.2867 | 1.29% | 45.4%
|  | Week 5 | 16897.5298 | 9293.64 | 7603.8898 | 45% | 9226.2731 | 6976.46 | 2977.1135 | 3448.13 | -471.0165 | -15.82% |  | 6249.1596 | 3528.33 | 2720.8296 | 43.54% | 125.17 | 65.75 | 59.42 | 47.47% |  | 35.2423 | 61.2867 | 24.93% | 45.4% |  |  | -11.25 | -2298.71
7429 | Taggart House | Start of month | 20992.12 | 14169.68 | 6822.44 | 32.5% | 16299.09 | 9699.51 | 9784.33 | 8137.88 | 1646.45 | 16.83% |  | 6514.76 | 1561.63 | 4953.13 | 76.03% | 130.62 | 34.75 | 95.87 | 73.4% |  | 128.638 | 35.9289 | 31.55% | 22.36% | Hours calc for monthly claims | -32.25 | -32.25
|  | Week 1 | 20992.12 | 14169.68 | 6822.44 | 32.5% | 16299.09 | 9699.51 | 9784.33 | 8137.88 | 1646.45 | 16.83% |  | 6514.76 | 1561.63 | 4953.13 | 76.03% | 130.62 | 34.75 | 95.87 | 73.4% |  | 128.638 | 35.9289 | 31.55% | 22.36% | Materials calc for monthly claims
|  | Week 2 | 20992.12 | 14169.68 | 6822.44 | 32.5% | 16299.09 | 9699.51 | 9784.33 | 8137.88 | 1646.45 | 16.83% |  | 6514.76 | 1561.63 | 4953.13 | 76.03% | 130.62 | 34.75 | 95.87 | 73.4% |  | 128.638 | 35.9289 | 31.55% | 22.36%
|  | Week 3 | 20992.12 | 14169.68 | 6822.44 | 32.5% | 16299.09 | 9699.51 | 9784.33 | 8137.88 | 1646.45 | 16.83% |  | 6514.76 | 1561.63 | 4953.13 | 76.03% | 130.62 | 34.75 | 95.87 | 73.4% |  | 128.638 | 35.9289 | 31.55% | 22.36% | Estimated months claim | 0
|  | Week 4 | 20992.1153 | 14169.68 | 6822.4353 | 32.5% | 16299.0852 | 9699.51 | 9784.3248 | 8137.88 | 1646.4448 | 16.83% |  | 6514.7604 | 1561.63 | 4953.1304 | 76.03% | 130.62 | 34.75 | 95.87 | 73.4% |  | 128.638 | 35.9289 | 31.55% | 22.36%
|  | Week 5 | 20992.1153 | 14169.68 | 6822.4353 | 32.5% | 16299.0852 | 9699.51 | 9784.3248 | 8137.88 | 1646.4448 | 16.83% |  | 6514.7604 | 1561.63 | 4953.1304 | 76.03% | 130.62 | 34.75 | 95.87 | 73.4% |  | 128.638 | 35.9289 | 31.55% | 22.36% |  |  | -32.25
9508 | St Barnabas Church | Start of month | 23770.95 | 10204.54 | 13566.41 | 57.07% | 14310.96 | 6935.96 | 7389.34 | 6605.05 | 784.29 | 10.61% |  | 6921.62 | 330.91 | 6590.71 | 95.22% | 140.15 | 5.75 | 134.4 | 95.9% |  | 568.4487 | 67.499 | 32.03% | 39.8% | Hours calc for monthly claims
|  | Week 1 | 23770.95 | 10204.54 | 13566.41 | 57.07% | 14310.96 | 6935.96 | 7389.34 | 6605.05 | 784.29 | 10.61% |  | 6921.62 | 330.91 | 6590.71 | 95.22% | 140.15 | 5.75 | 134.4 | 95.9% |  | 568.4487 | 67.499 | 32.03% | 39.8% | Materials calc for monthly claims
|  | Week 2 | 23770.95 | 10204.54 | 13566.41 | 57.07% | 14310.96 | 7114.14 | 7389.34 | 6605.05 | 784.29 | 10.61% |  | 6921.62 | 509.09 | 6412.53 | 92.64% | 140.15 | 9.25 | 130.9 | 93.4% |  | 334.0973 | 67.499 | 30.28% | 39.8%
|  | Week 3 | 23770.95 | 10204.54 | 13566.41 | 57.07% | 14310.96 | 7116.73 | 7389.34 | 6605.05 | 784.29 | 10.61% |  | 6921.62 | 511.68 | 6409.94 | 92.61% | 140.15 | 9.25 | 130.9 | 93.4% |  | 333.8173 | 67.499 | 30.26% | 39.8% | Estimated months claim | 0
|  | Week 4 | 23770.9462 | 10204.54 | 13566.4062 | 57.07% | 14310.9577 | 7116.73 | 7389.3355 | 6605.05 | 784.2855 | 10.61% |  | 6921.6222 | 511.68 | 6409.9422 | 92.61% | 140.15 | 9.25 | 130.9 | 93.4% |  | 333.8173 | 67.499 | 30.26% | 39.8%
|  | Week 5 | 23770.9462 | 10204.54 | 13566.4062 | 57.07% | 14310.9577 | 7116.73 | 7389.3355 | 6605.05 | 784.2855 | 10.61% |  | 6921.6222 | 511.68 | 6409.9422 | 92.61% | 140.15 | 9.25 | 130.9 | 93.4% |  | 333.8173 | 67.499 | 30.26% | 39.8%
|  | Start of month | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | [7 empty] | Hours calc for monthly claims
|  | Week 1 | [6 empty] | 0 | 0 | [16 empty] | Materials calc for monthly claims
|  | Week 2 | [6 empty] | 0 | 0
|  | Week 3 | [6 empty] | 0 | 0 | [16 empty] | Estimated months claim | 0
|  | Week 4 | [6 empty] | 0 | 0
|  | Week 5 | [6 empty] | 0 | 0
| Contracting | Start of month | [6 empty] | 0 | 0 | [16 empty] | Hours calc for monthly claims
|  | Week 1 | [6 empty] | 0 | 0 | [16 empty] | Materials calc for monthly claims
|  | Week 2 | [6 empty] | 0 | 0
|  | Week 3 | [6 empty] | 0 | 0 | [16 empty] | Estimated months claim | 0
|  | Week 4 | [6 empty] | 0 | 0
|  | Week 5 | [6 empty] | 0 | 0
8946 | Westcoast Vaults | Start of month | 137109.56 | 30174.75 | 106934.81 | 77.99% | 117394.57 | 26124 | 99479.62 | 26124 | 73355.62 | 73.74% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  | 0 | 54.9378 | 13.42% | 14.38% | Hours calc for monthly claims
|  | Week 1 | 137109.56 | 30174.75 | 106934.81 | 77.99% | 117394.57 | 30594.96 | 99479.62 | 30594.96 | 68884.66 | 69.24% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  | 0 | 54.9378 | -1.39% | 14.38% | Materials calc for monthly claims
|  | Week 2 | 137109.56 | 30174.75 | 106934.81 | 77.99% | 117394.57 | 30594.96 | 99479.62 | 30594.96 | 68884.66 | 69.24% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  | 0 | 54.9378 | -1.39% | 14.38%
|  | Week 3 | 137109.56 | 30174.75 | 106934.81 | 77.99% | 117394.57 | 30594.96 | 99479.62 | 30594.96 | 68884.66 | 69.24% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  | 0 | 54.9378 | -1.39% | 14.38% | Estimated months claim | 0
|  | Week 4 | 137109.5605 | 30174.75 | 106934.8105 | 77.99% | 117394.5692 | 37161.14 | 99479.615 | 37161.14 | 62318.475 | 62.64% |  | 17914.9542 | 0 | 17914.9542 | 100% | 358.86 | 0 | 358.86 | 100% |  | 0 | 54.9378 | -23.15% | 14.38%
|  | Week 5 | 137109.5605 | 42368.33 | 94741.2305 | 69.1% | 117394.5692 | 37161.14 | 99479.615 | 37161.14 | 62318.475 | 62.64% |  | 17914.9542 | 0 | 17914.9542 | 100% | 358.86 | 0 | 358.86 | 100% |  | 0 | 54.9378 | 12.29% | 14.38%
8308 | Roydvale | Start of month | 396453.46 | 271388.15 | 125065.31 | 31.55% | 295569.99 | 234322.81 | 178700.37 | 177071.48 | 1628.89 | 0.9115% |  | 116869.62 | 57251.33 | 59618.29 | 51.01% | 2344.68 | 1212 | 1132.68 | 48.31% |  | 30.582 | 43.0265 | 13.66% | 25.45% | Hours calc for monthly claims | -1014.25 | -1014.25
|  | Week 1 | 396453.46 | 306038.55 | 90414.91 | 22.81% | 295569.99 | 241753.24 | 178700.37 | 178956.15 | -255.78 | -0.1431% |  | 116869.62 | 62797.09 | 54072.53 | 46.27% | 2344.68 | 1335 | 1009.68 | 43.06% |  | 48.1538 | 43.0265 | 21.01% | 25.45% | Materials calc for monthly claims
|  | Week 2 | 408794.64 | 306038.55 | 102756.09 | 25.14% | 304310.08 | 249180.5 | 185072.6 | 182215.95 | 2856.65 | 1.544% |  | 119237.48 | 66964.55 | 52272.93 | 43.84% | 2397.2 | 1427.42 | 969.78 | 40.45% |  | 39.8327 | 43.5861 | 18.58% | 25.56%
|  | Week 3 | 412300.73 | 306038.55 | 106262.18 | 25.77% | 306356.28 | 250902.09 | 186357.49 | 183091.73 | 3265.76 | 1.752% |  | 119998.79 | 67810.36 | 52188.43 | 43.49% | 2412.45 | 1444.92 | 967.53 | 40.11% |  | 38.1588 | 43.9157 | 18.02% | 25.7% | Estimated months claim | 0
|  | Week 4 | 412300.7326 | 353667.87 | 58632.8626 | 14.22% | 306356.2787 | 256729.4 | 186357.4889 | 184765.38 | 1592.1089 | 0.8543% |  | 119998.7898 | 71964.02 | 48034.7698 | 40.03% | 2412.45 | 1535.92 | 876.53 | 36.33% |  | 63.1143 | 43.9157 | 27.41% | 25.7%
|  | Week 5 | 412300.7326 | 353667.87 | 58632.8626 | 14.22% | 306356.2787 | 252680.7 | 186357.4889 | 180716.68 | 5640.8089 | 3.027% |  | 119998.7898 | 71964.02 | 48034.7698 | 40.03% | 2412.45 | 1535.92 | 876.53 | 36.33% |  | 65.7503 | 43.9157 | 28.55% | 25.7% |  |  | -1014.25
8530 | 224 Cashel St - Eastern WC Block Reno | Start of month | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0% | 0%
|  | Week 1 | 8795.03 | 0 | 8795.03 | 100% | 6369.12 | 0 | 4527.89 | 0 | 4527.89 | 100% |  | 1841.23 | 0 | 1841.23 | 100% | 36.92 | 0 | 36.92 | 100% |  | 0 | 65.7071 | 0% | 27.58%
|  | Week 2 | 8795.03 | 0 | 8795.03 | 100% | 6369.12 | 0 | 4527.89 | 0 | 4527.89 | 100% |  | 1841.23 | 0 | 1841.23 | 100% | 36.92 | 0 | 36.92 | 100% |  | 0 | 65.7071 | 0% | 27.58%
|  | Week 3 | 8795.03 | 0 | 8795.03 | 100% | 6369.12 | 0 | 4527.89 | 0 | 4527.89 | 100% |  | 1841.23 | 0 | 1841.23 | 100% | 36.92 | 0 | 36.92 | 100% |  | 0 | 65.7071 | 0% | 27.58%
|  | Week 4 | 8795.0284 | 0 | 8795.0284 | 100% | 6369.1218 | 397 | 4527.894 | 397 | 4130.894 | 91.23% |  | 1841.2278 | 0 | 1841.2278 | 100% | 36.92 | 0 | 36.92 | 100% |  | 0 | 65.7071 | 0% | 27.58%
|  | Week 5 | 8795.0284 | 1740.2 | 7054.8284 | 80.21% | 6369.1218 | 584.85 | 4527.894 | 239.55 | 4288.344 | 94.71% |  | 1841.2278 | 345.3 | 1495.9278 | 81.25% | 36.92 | 6 | 30.92 | 83.75% |  | 192.5583 | 65.7071 | 66.39% | 27.58%
8386 | Bach in Kaikoura | Start of month | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0% | 0%
Week 1
|  | Week 2 | 27503.14 | 0 | 27503.14 | 100% | 19683.28 | 0 | 10693.53 | 0 | 10693.53 | 100% |  | 8989.75 | 0 | 8989.75 | 100% | 180.16 | 0 | 180.16 | 100% |  | 0 | 43.4051 | 0% | 28.43%
|  | Week 3 | 27503.14 | 0 | 27503.14 | 100% | 19683.28 | 0 | 10693.53 | 0 | 10693.53 | 100% |  | 8989.75 | 0 | 8989.75 | 100% | 180.16 | 0 | 180.16 | 100% |  | 0 | 43.4051 | 0% | 28.43%
|  | Week 4 | 27503.1366 | 0 | 27503.1366 | 100% | 19683.2806 | 0 | 10693.5316 | 0 | 10693.5316 | 100% |  | 8989.749 | 0 | 8989.749 | 100% | 180.16 | 0 | 180.16 | 100% |  | 0 | 43.4051 | 0% | 28.43%
|  | Week 5 | 27503.1366 | 0 | 27503.1366 | 100% | 19683.2806 | 0 | 10693.5316 | 0 | 10693.5316 | 100% |  | 8989.749 | 0 | 8989.749 | 100% | 180.16 | 0 | 180.16 | 100% |  | 0 | 43.4051 | 0% | 28.43%
8829 | Resi Reno at 124 Chapter Street | Start of month | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0% | 0%
Week 1
|  | Week 2 | 40670.15 | 0 | 40670.15 | 100% | 29498.31 | 0 | 24964.33 | 0 | 24964.33 | 100% |  | 4533.98 | 0 | 4533.98 | 100% | 90.88 | 0 | 90.88 | 100% |  | 0 | 122.9296 | 0% | 27.47%
|  | Week 3 | 40670.15 | 0 | 40670.15 | 100% | 29498.31 | 0 | 24964.33 | 0 | 24964.33 | 100% |  | 4533.98 | 0 | 4533.98 | 100% | 90.88 | 0 | 90.88 | 100% |  | 0 | 122.9296 | 0% | 27.47%
|  | Week 4 | 40670.1518 | 0 | 40670.1518 | 100% | 29498.3117 | 0 | 24964.3289 | 0 | 24964.3289 | 100% |  | 4533.9828 | 0 | 4533.9828 | 100% | 90.88 | 0 | 90.88 | 100% |  | 0 | 122.9296 | 0% | 27.47%
|  | Week 5 | 40670.1518 | 0 | 40670.1518 | 100% | 29498.3117 | 0 | 24964.3289 | 0 | 24964.3289 | 100% |  | 4533.9828 | 0 | 4533.9828 | 100% | 90.88 | 0 | 90.88 | 100% |  | 0 | 122.9296 | 0% | 27.47%
7480 | New Build | Start of month | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0% | 0%
Week 1
|  | Week 2 | 21396.5 | 0 | 21396.5 | 100% | 15378.24 | 0 | 8344.6 | 0 | 8344.6 | 100% |  | 7033.64 | 0 | 7033.64 | 100% | 140.9 | 0 | 140.9 | 100% |  | 0 | 42.713 | 0% | 28.13%
|  | Week 3 | 21396.5 | 0 | 21396.5 | 100% | 15378.24 | 0 | 8344.6 | 0 | 8344.6 | 100% |  | 7033.64 | 0 | 7033.64 | 100% | 140.9 | 0 | 140.9 | 100% |  | 0 | 42.713 | 0% | 28.13%
|  | Week 4 | 21396.5004 | 0 | 21396.5004 | 100% | 15378.2444 | 0 | 8344.6088 | 0 | 8344.6088 | 100% |  | 7033.6356 | 0 | 7033.6356 | 100% | 140.9 | 0 | 140.9 | 100% |  | 0 | 42.713 | 0% | 28.13%
|  | Week 5 | 21396.5004 | 0 | 21396.5004 | 100% | 15378.2444 | 0 | 8344.6088 | 0 | 8344.6088 | 100% |  | 7033.6356 | 0 | 7033.6356 | 100% | 140.9 | 0 | 140.9 | 100% |  | 0 | 42.713 | 0% | 28.13%
9437 | 65A Belfast Road (Revised) | Start of month | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% |  | 0 | 0 | 0% | 0%
Week 1
|  | Week 2 | 239296.88 | 10598.48 | 228698.4 | 95.57% | 203192.69 | 18229.7 | 175849.53 | 16839.61 | 159009.92 | 90.42% |  | 27343.16 | 1390.09 | 25953.07 | 94.92% | 547.57 | 27.84 | 519.73 | 94.92% |  | -274.1099 | 65.9353 | -72% | 15.09%
|  | Week 3 | 239296.88 | 10598.48 | 228698.4 | 95.57% | 203192.69 | 18229.7 | 175849.53 | 16839.61 | 159009.92 | 90.42% |  | 27343.16 | 1390.09 | 25953.07 | 94.92% | 547.57 | 27.84 | 519.73 | 94.92% |  | -274.1099 | 65.9353 | -72% | 15.09%
|  | Week 4 | 239296.8838 | 10598.48 | 228698.4038 | 95.57% | 203192.6919 | 18235.02 | 175849.5297 | 16839.61 | 159009.9197 | 90.42% |  | 27343.1622 | 1395.41 | 25947.7522 | 94.9% | 547.57 | 27.84 | 519.73 | 94.92% |  | -274.301 | 65.9353 | -72.05% | 15.09%
|  | Week 5 | 239296.8838 | 19872.16 | 219424.7238 | 91.7% | 203192.6919 | 18292.87 | 175849.5297 | 16897.46 | 158952.0697 | 90.39% |  | 27343.1622 | 1395.41 | 25947.7522 | 94.9% | 547.57 | 27.84 | 519.73 | 94.92% |  | 56.7274 | 65.9353 | 7.95% | 15.09%

## Claim Calculator By Month
Updated Job Spreadsheet
Job Number | Job Name | Claim | Costs | Profit | Retention | Margin | Quoted Margin | Hours to complete before E.O.M | Costs to come before E.O.M | Total cost to come before E.O.M | Estimated margin E.O.M | GP End of month | Hours this month | GP $ per hour this month
7658 | Charity Hospital | 22202.89 | 21498.29 | 704.6 | 0 | 3.173% | 21.49% | 50 | 5000 | 7000 | -28.35% | -6295.4 | 20 | -89.9343
8142 | Fisher Developements | 42019.9 | 21082.63 | 20937.27 | 7 | 49.84% | 23.92% | 500 | 272.6 | 20272.6 | 1.598% | 671.67 | -52.5 | 1.5009 | 14 Mirrors and 49 Downlights have been ordered
8824 | 3 Innovation Road | 0 | 462 | -462 |  | 0% | 28.85% | 16 |  | 640 | 0% | -1102 | -34.75 | 58.7733
8127 | Rolly Autowash | 0 | 4539.26 | -4539.26 | 0 | 0% | 32.27% | 48 | 3000 | 4920 | 0% | -9459.26 | -388.25 | 27.8009
8183 | Murney Custodian - 1 Freight Drive | 93276.08 | 62750.77 | 30525.31 | 3 | 32.73% | 17.63% | 16 | 2000 | 2640 | 29.9% | 27888.31 | 53 | 404.1784 | Couldnt get this rite because of ers but they re claiming 30%
8886 | Monkey Toe - Fisher fit out | 61369.72 | 16020.68 | 45349.04 | 0 | 73.89% | 26.63% | 0 | 3000 | 3000 | 69.01% | 42349.04 | -112 | -378.1164
8887 | Tenancy 2 - Fisher Fit out | 27951.48 | 4389.46 | 23562.02 |  | 84.3% | 22.64% | 0 | 3000 | 3000 | 73.56% | 20562.02 | -86.75 | -237.0262
8670 | Studio DB - tautara fit out | 27482.32 | 19232.93 | 8249.39 | 0 | 30.02% | 29.65% | 80 | 5000 | 8200 | 0.1797% | 49.39 | -269 | -0.26132 | 48 Hours need to be made non Billable
8907 | 35 Mania | 0 | 0 | 0 |  | 0% | 22.33% |  |  | 0 | 0% | 0 |  | 0
9065 | Cooltranz stage 4 | 19065.24 | 20702.6 | -1637.36 | 3 | -8.572% | 25.25% |  |  | 0 | -8.572% | -1634.36 |  | 0
9259 | Andrew Reeve Stage 2 | 16999.83 | 15288.17 | 1711.66 | 3 | 10.09% |  |  |  | 0 | 10.09% | 1714.66 |  | 0
8352 | 5 Sanscrit Place | 0 | 1159.83 | -1159.83 | 0 | 0% | 34.79% |  | 0 | 0 | 0% | -1159.83 | -143.25 | 8.0965
8234 | Melhuish House | 0 | -902.17 | 902.17 | 0 | 0% | 27.18% |  |  | 0 | 0% | 902.17 | -148.5 | -6.0752
8214 | 6 Tiroroa Lane | 0 | 93.55 | -93.55 | 0 | 0% | 25.8% |  |  | 0 | 0% | -93.55 | -5 | 18.71
6792 | Major Hornbrook | -715 | 245.73 | -960.73 | 0 | 134.4% | 28.32% | 64 | 0 | 2560 | 492.4% | -3520.73 | -317.25 | 13.9022
8840 | Inline Architecture | 0 | 923.88 | -923.88 | 0 | 0% | 36.42% |  | 0 | 0 | 0% | -923.88 | -204.75 | 4.5122
8769 | Percival Bach | 0 | 58.32 | -58.32 | 0 | 0% |  | 80 | 0 | 3200 | 0% | -3258.32 |  | -40.729
7901 | St Albans Street | 64090.99 | 8038.55 | 56052.44 | 0 | 87.46% | 17.51% |  |  | 0 | 87.46% | 56052.44 |  | 0
8923 | 4 Perry St | 2127.81 | 0 | 2127.81 | 0 | 100% | 26.27% |  | 0 | 0 | 100% | 2127.81 | -2 | -1063.905
7864 | Ryans House | 0 | -13.37 | 13.37 |  | 0% | 25.72% | 0 |  | 0 | 0% | 13.37 | -266.75 | -0.050122
7912 | 71A Fendalton Road | 0 | 0 | 0 |  | 0% |  |  |  | 0 | 0% | 0 |  | 0
8360 | Dixon House | 0 | 0 | 0 |  | 0% | 30.58% |  |  | 0 | 0% | 0 | -260.75 | 0
8337 | Waimak Dairys | 6081.02 | 3650.36 | 2430.66 |  | 39.97% | 22.24% |  | 2530 | 2530 | -1.634% | -99.34 | -44.75 | 2.2199
9240 | Daves Twizel Shack | 0 | 2097.39 | -2097.39 |  | 0% |  | 0 |  | 0 | 0% | -2097.39 |  | 0 | $18627.12 from Sharp Electrical
7428 | FAB Pegasus Lakeside | 0 | 2625.44 | -2625.44 |  | 0% | 21.6% | 32 | 0 | 1280 | 0% | -3905.44 | -304.75 | 14.3188
9351 | Harewood Golf Club | 3801.94 | 3273.68 | 528.26 |  | 13.89% | 45.4% | 16 | 0 | 640 | -2.939% | -111.74 | -11.25 | -23.5242
7429 | Taggart House | 0 | 0 | 0 |  | 0% | 22.36% | 10 | 5000 | 5400 | 0% | -5400 | -32.25 | 242.6966
9508 | St Barnabas Church | 0 | 180.77 | -180.77 |  | 0% |  |  |  | 0 | 0% | -180.77 |  | 0
| Contracting | [6 empty] | 0
8946 | Westcoast Vaults | 12193.58 | 11037.14 | 1156.44 |  | 9.484% | 14.38% |  | 1750 | 1750 | -4.868% | -593.56 |  | 0
8308 | Roydvale | 82279.72 | 18357.89 | 63921.83 |  | 77.69% | 25.63% | 80 | 0 | 3200 | 73.8% | 60721.83 | -1014.25 | -64.9953
9437 | 65A Belfast Road (Revised) | 19872.16 | 18292.87 | 1579.29 |  | 7.947% |  |  |  | 0 | 7.947% | 1579.29 |  | 0
7480 | New Build | 0 | 0 | 0 |  | 0% |  |  |  | 0 | 0% | 0 |  | 0
8829 | Resi Reno at 124 Chapter Street | 0 | 0 | 0 |  | 0% |  |  |  | 0 | 0% | 0 |  | 0
8386 | Bach in Kaikoura | 0 | 0 | 0 |  | 0% |  |  |  | 0 | 0% | 0 |  | 0
8530 | 224 Cashel St - Eastern WC Block Reno | 1740.2 | 584.85 | 1155.35 |  | 66.39% |  |  |  | 0 | 66.39% | 1155.35 |  | 0
Totals | Total | 501839.88 | 255671.5 | 246168.38 | GP% | 49.05% | E.O.M GP% | 35.06%
| Residential | -22865.6 | 32774.04 | -55639.64 |  | 243.3% | E.O.M GP% | 268.5%

## Upcoming Work Calculator
Updated Job Spreadsheet
| Job | Quoted Hours | Hours Used | Hours Remaining | January | February | March | April | May | June | July | August | September | October | November | December
Servicing | Servicing work any job under 30 hours |  |  |  | 500 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 500
7658 | Charity Hospital | 638.02 | 625.25 | 12.77 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | Programme Checked 24/03/26
8142 | Fisher Developements | 363.57 | 331.25 | 32.32 | [8 empty] | 0 | 60 |  |  | Cant find a Programme for this.
8824 | 3 Innovation Road | 125.39 | 34.75 | 90.64 | [8 empty] | 0 | 58 |  |  | Programme Checked 24/03/26
8127 | Rolly Autowash | 805.22 | 625 | 180.22 | [7 empty] | 0 | 0 | 0 |  |  | Programme Checked 24/03/26
8183 | Murney Custodian - 1 Freight Drive | 1124.47 | 821.5 | 302.97 | [7 empty] | 0 | 0 | 80 | 0
8886 | Monkey Toe - Fisher fit out | 501.83 | 366.25 | 135.58 | [6 empty] | 0 | 0 | 0 | 30 |  |  | Programme Checked 24/03/26
8887 | Tenancy 2 - Fisher Fit out | 223.22 | 216.5 | 6.72 | [7 empty] | 0 | 0
8670 | Studio DB - tautara fit out | 685.48 | 699.75 | -14.27 | [7 empty] | 0 | 0
8907 | 35 Mania | 63.5 | 48.25 | 15.25 | [7 empty] | 0
9065 | Cooltranz stage 4 | 193.32 | 90.75 | 102.57 | [7 empty] | 0 | 0 | 160 | 30
9259 | Andrew Reeve Stage 2 | 472.14 | 237.25 | 234.89 | [7 empty] | 0 | 0 | 80
8352 | 5 Sanscrit Place | 139.07 | 167.75 | -28.68 | [7 empty] | 0
8234 | Melhuish House | 231.75 | 225.5 | 6.25 | [7 empty] | 0
8214 | 6 Tiroroa Lane | 147.9 | 6.5 | 141.4 | [8 empty] | 0 | 0 | 48 | 16
6792 | Major Hornbrook | 208.2 | 324.25 | -116.05
8840 | Inline Architecture | 324.19 | 472.75 | -148.56 | [7 empty] | 0
8769 | Percival Bach | 82.37 | 0 | 82.37 | [7 empty] | 0 | 0 | 30 | 50
7901 | St Albans Street | 317.92 | 106 | 211.92 | [7 empty] | 0 | 0 | 170
8923 | 4 Perry St | 156.69 | 11.5 | 145.19 | 60 | 15 | 90 | [6 empty] | 58 | 16 | 72
7864 | Ryans House | 200.82 | 283.75 | -82.93
7912 | 71A Fendalton Road | 497.55 | 58.25 | 439.3 | 80 | [7 empty] | 0 | 0 | 0 | 0
8360 | Dixon House | 210.6 | 260.75 | -50.15
8337 | Waimak Dairys | 120.44 | 116.25 | 4.19 | [7 empty] | 0 | 0 | 18
9240 | Daves Twizel Shack | 65.13 | 24.33 | 40.8 | [7 empty] | 0 | 0 | 40
7428 | FAB Pegasus Lakeside | 659.73 | 550.75 | 108.98 | [7 empty] | 0 | 0 | 110
9351 | Harewood Golf Club | 125.17 | 65.75 | 59.42 | [6 empty] | 0 | 0 | 0 | 60
7429 | Taggart House | 130.62 | 34.75 | 95.87 | [7 empty] | 0 | 0 | 16 | 70
9508 | St Barnabas Church | 140.15 | 9.25 | 130.9 | [9 empty] | 52 | 13 | 69
Contracting
8946 | Westcoast Vaults | 358.86 | 0 | 358.86 | [8 empty] | 0 | 140 | 40 | 178
8308 | Roydvale | 2412.45 | 1535.92 | 876.53 | [7 empty] | 0 | 0 | 320 | 80 | 80
9437 | 65A Belfast Road (Revised) | 547.57 | 27.84 | 519.73 | 240 | [8 empty] | 0 | 0 | 240
7480 | New Build | 140.9 | 0 | 140.9 | [9 empty] | 56 | 16 | 68
8829 | Resi Reno at 124 Chapter Street | 90.88 | 0 | 90.88 | [9 empty] | 56 |  | 16
8386 | Bach in Kaikoura | 180.16 | 0 | 180.16 | [9 empty] | 72 | 18 | 90
8530 | 224 Cashel St - Eastern WC Block Reno | 36.92 | 6 | 30.92 | [9 empty] | 20 | 16
| Total Hours |  |  |  | 640 | 715 | 790 | 700 | 700 | 700 | 716 | 2520 | 3060 | 1316 | 914 | 650
| Residential Hours |  |  |  | 140 | 15 | 90 |  |  |  | 16 | 800 | 858 | 476 | 214 | 150
| Commercial Hours | 4490.26 | [9 empty] | 1020 | 1502 | 140
| Hours Available |  |  |  | 1488 | 2112 | 1984 | 1884.8 | 1948.8 | 2083.2 | 2604.8 | 2486.4 | 2604.8 | 2217.6 | 2112 | 1478.4
| Balance Hours |  |  |  | -848 | -1397 | -1194 | -1184.8 | -1248.8 | -1383.2 | -1888.8 | 33.6 | 455.2 | -901.6 | -1198 | -828.4
| Working Days In Month | Check Staff Numbers |  |  | 15 | 20 | 20 | 19 | 21 | 21 | 22 | 21 | 22 | 21 | 20 | 14
| No - Staff On Tools |  |  |  | 15.5 | 16.5 | 15.5 | 15.5 | 14.5 | 15.5 | 18.5 | 18.5 | 18.5 | 16.5 | 16.5 | 16.5
| Staff | [9 empty] | 2 x PPLguys here for July and August
| Turbo | 1
| Sean | 1
| Jacob | 1
| Hayden | 1
| Doug | 1
| Kyle | 0.5
| Jack | 1
| Andy | 1
| Ben Ruffles | 1
| Ben Dyer | 0
| Jake | 1
0
0
0
0
0
0
0
| Ethan | 1
| Rhod | 1
| George | 1
| Jasper | 1
| Logan | 1
| Quin | 1
| Regan | 1
| Total Staff (enter in above spreadsheet) | 16.5

## Note Cam (To Do)
Cams Notes
Koawa:
New job meeting set up for 8am wednesday - Tim, Dylan, VD, Cam - Perhaps bring in Jacob once back from leave??
Tray shop drawings into engineers - waiting on geoff to send back multidraw drawings.
DB dates for sites (livening 11 July)
Confirm Warrenties agreement
Go to tech submissions meeting on Wednesday 12th March
Start getting orders in, (so far PDL gear ordered through rads) need to look at lights beign ordered that we can - confirm process.
Tru Hire:
Temp should be on Monday morning 14.04.25
Craig would like an export/list for me please mate that captures all of the costs to date from you guys and ILS?
Riccarton High:
1x pits to repair
Follow up VO’s (Light pole to loop off date TBC,
Arrange PS3 & PS4 (PS3 filled in)
Start O&M manuals early - started; PS3 and board schedule in.
Check Strawberry sound hardware in swbd – report back to pete
From southbase deliverables register - Provide lifting handles for pits,
Missing 3x J lights (external wall lights)
EM's only have lights no drivers/batteries?
Strip light for under cabinets 2520mm
Spare light pole and head on site,was deleted from scope when landscaping changed
Gills:
Follow up sensor return/outcome (waiting to hear back)
Lunns:
Tidy up mains/ conduits coming out building
finish external lights (tuesday 15.04.25)
Unit 2 roller door no limits (V.O)
Rosiez unhappy with level of tidy up and removal of old cables, need to clarify what we actually scoped to what we did.
Kingsford Smith Drive
Main 100A unit 1 approved, ready for livening date. - Had a phone call from genesis regarding wheather this would need CT's?
Mains 2nd application is on hold until we get load breakdown for 160A - probably need to sort this asap.
Confirm start date with Wolfy, and order materials lifter
Te Aratai
Ellesmere College (Temp power)
Live
Cooltranz
Confirm correct data logger, depending on incoming size 1500A or 6kA then confirm price with cooltranz for hire rates etc.
Other:
Comes up with hours tracking solution

## Note Tom (To Do)
Tom's Notes:
Other:
Comes up with hours tracking solution

## Deliverables_RR_Test_Sheet (2)
Updated Job Spreadsheet
Job Number | Job Name | Week | Quoted Price | Claim to date | Remaining to claim | % Claim remaining | Total quoted cost | Total actual cost | Quoted material cost | Actual material cost | Material cost remaining | Material % remaining | Estimated % of materials recieved | Contractor Quoted Cost | Contractor Actual Cost | Contractor Balance | Quoted labour cost | Actual labour cost | Labour cost remaining | Labour cost % remaining | Quoted labour hours | Actual labour hours | Labour hours remaining | Labour hour % remaining | Estimated % of job complete | GP $ Per Hour | Quoted GP $ Per Hour | Margin to date | Quoted margin
[32 empty] | Hours calcs | Materials calcs
7658 | Charity Hospital | Start of month | 1914143.52 | 1667392.4 | 246751.12 | 12.89% | 1675577.99 | 1406264.78 | 1511021.45 | 1215391.45 | 295630 | 19.56% |  | 5 | 4 | 1 | 164551.54 | 190869.33 | -26317.79 | -15.99% | 3296.1 | 4599 | -1302.9 | -39.53% |  | 56.7801 | 72.3796 | 15.66% | 12.46% | Hours calc for monthly claims | -4599 | 415.49 | 48650.89
|  | Week 1 | 1922479.92 | 1667392.4 | 255087.52 | 13.27% | 1681960.61 | 1474477.14 | 1516687.43 | 1264042.34 | 252645.09 | 16.66% |  |  |  |  | 165273.18 | 210434.8 | -45161.62 | -27.33% | 3312.1 | 5014.49 | -1702.39 | -51.4% |  | 38.4716 | 72.6184 | 11.57% | 12.51% | Materials calc for monthly claims | -1215391.45 | 134.5 | 24752.67
|  | Week 2 | 1922479.92 | 1667392.4 | 255087.52 | 13.27% | 1681960.61 | 1505572.21 | 1516687.43 | 1288795.01 | 227892.42 | 15.03% | 90% |  |  |  | 165273.18 | 216777.2 | -51504.02 | -31.16% | 3312.1 | 5148.99 | -1836.89 | -55.46% | 90% | 31.4276 | 72.6184 | 9.705% | 12.51% |  |  | -5148.99 | -1288795.01
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -4599 | -1215391.45
8142 | Fisher Developements | Start of month | 381671.63 | 144223.4 | 237448.23 | 62.21% | 329257.09 | 168819.17 | 288248.16 | 158648.53 | 129599.63 | 44.96% |  |  |  |  | 41008.93 | 10170.64 | 30838.29 | 75.2% | 821.2 | 241 | 580.2 | 70.65% |  | -102.0571 | 63.8268 | -17.05% | 13.73% | Hours calc for monthly claims | -241 | 96.25 | 30474.42
|  | Week 1 | 382219.49 | 240065.55 | 142153.94 | 37.19% | 329585.81 | 202828.2 | 288352.94 | 189122.95 | 99229.99 | 34.41% |  |  |  |  | 41232.87 | 13705.25 | 27527.62 | 66.76% | 825.68 | 337.25 | 488.43 | 59.15% |  | 110.4147 | 63.7459 | 15.51% | 13.77% | Materials calc for monthly claims | -158648.53 | 101.75 | 7119.32
|  | Week 2 | 382219.49 | 240065.55 | 142153.94 | 37.19% | 329585.81 | 213730.54 | 288352.94 | 196242.27 | 92110.67 | 31.94% |  |  |  |  | 41232.87 | 17488.27 | 23744.6 | 57.59% | 825.68 | 439 | 386.68 | 46.83% |  | 59.9886 | 63.7459 | 10.97% | 13.77% |  |  | -439 | 23228
|  | Week 3 | 383409.63 | 240065.55 | 143344.08 | 37.39% | 330537 | 246817.11 | 289155.03 | 219470.27 | 69684.76 | 24.1% | 75% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 8.579% | 13.79% | Estimated months claim | 0 | 0 | -219470.27
|  | Week 4 | 383409.63 |  | 383409.63 | 100% |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% |  |  | 0 | 0
|  | Week 5 | 383409.63 |  | 383409.63 | 100% |  |  | 0 | 0 | 0 | #DIV/0! | 55% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 35% | #DIV/0! | #REF! | #DIV/0! | #REF! |  |  | -241 | -158648.53
7104 | 3 Innovation Road | Start of month | 449818.08 | 246538.95 | 203279.13 | 45.19% | 329858.1 | 251921.97 | 255282.19 | 219103.38 | 36178.81 | 14.17% | 0% |  |  |  | 74575.91 | 32818.59 | 41757.32 | 55.99% | 1493.36 | 799.5 | 693.86 | 46.46% | 0% | -6.733 | 80.3289 | -2.183% | 26.67% | Hours calc for monthly claims | -799.5 | 57.75 | -918.26
|  | Week 1 | 449818.08 | 364039.73 | 85778.35 | 19.07% | 329858.1 | 253347.64 | 255282.19 | 218185.12 | 37097.07 | 14.53% |  |  |  |  | 74575.91 | 35162.52 | 39413.39 | 52.85% | 1493.36 | 857.25 | 636.11 | 42.6% | 10% | 129.1246 | 80.3289 | 30.41% | 26.67% | Materials calc for monthly claims | -219103.38 | 93.75 | 5813.69
|  | Week 2 | 449818.08 | 364039.73 | 85778.35 | 19.07% | 329858.1 | 262942.02 | 255282.19 | 223998.81 | 31283.38 | 12.25% |  |  |  |  | 74575.91 | 38943.21 | 35632.7 | 47.78% | 1493.36 | 951 | 542.36 | 36.32% | 15% | 106.3067 | 80.3289 | 27.77% | 26.67% |  |  | -951 | -223998.81
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 3% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 3% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 90% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 65% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -799.5 | -219103.38
8127 | Rolly Autowash | Start of month | 38856.96 | 0 | 38856.96 | 100% | 27050.88 | 1129.12 | 16492.08 | 1129.12 | 15362.96 | 93.15% | 0% |  |  |  | 10558.8 | 0 | 10558.8 | 100% | 213 | 0 | 213 | 100% | 0% | #DIV/0! | 55.4276 | #DIV/0! | 30.38% | Hours calc for monthly claims | 0 | 9.25 | 5779.58
|  | Week 1 | 38856.96 | 0 | 38856.96 | 100% | 27050.88 | 7293.59 | 16492.08 | 6908.7 | 9583.38 | 58.11% | 0% |  |  |  | 10558.8 | 384.89 | 10173.91 | 96.35% | 213.13 | 9.25 | 203.88 | 95.66% | 0% | -788.4962 | 55.3938 | #DIV/0! | 30.38% | Materials calc for monthly claims | -1129.12 | 101.75 | 6796.13
|  | Week 2 | 38856.96 | 0 | 38856.96 | 100% | 27050.88 | 18431.21 | 16492.08 | 13704.83 | 2787.25 | 16.9% | 0% |  |  |  | 10558.8 | 4726.38 | 5832.42 | 55.24% | 213.13 | 111 | 102.13 | 47.92% | 0% | -166.0469 | 55.3938 | #DIV/0! | 30.38% |  |  | -111 | -13704.83
|  | Week 3 |  | 0 | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  | 0 | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  | 0 | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | -1129.12
8183 | Murney - 1 Freight Drive + 109 Iport | Start of month | 69191.71 | 0 | 69191.71 | 100% | 53243.87 | 641.28 | 41588.94 | 171.84 | 41417.1 | 99.59% |  |  |  |  | 11654.93 | 469.44 | 11185.49 | 95.97% | 233.59 | 12.5 | 221.09 | 94.65% | 0% | -51.3024 | 68.2728 | #DIV/0! | 23.05% | Hours calc for monthly claims | -12.5 | 4.5 | 13.95
|  | Week 1 | 69191.71 | 1364.78 | 67826.93 | 98.03% | 53243.87 | 844.77 | 41588.94 | 185.79 | 41403.15 | 99.55% |  |  |  |  | 11654.93 | 658.98 | 10995.95 | 94.35% | 233.59 | 17 | 216.59 | 92.72% |  | 30.5888 | 68.2728 | 38.1% | 23.05% | Materials calc for monthly claims | -171.84 | 3 | 3907.37
|  | Week 2 | 69191.71 | 1364.78 | 67826.93 | 98.03% | 53243.87 | 4850.24 | 41588.94 | 4093.16 | 37495.78 | 90.16% |  |  |  |  | 11654.93 | 757.08 | 10897.85 | 93.5% | 233.59 | 20 | 213.59 | 91.44% |  | -174.273 | 68.2728 | -255.4% | 23.05% |  |  | -20 | -4093.16
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -12.5 | -171.84
8886 | Monkey Toe - Fisher fit out | Start of month | 44956.29 |  | 44956.29 | 100% | 30585.67 | 0 | 19268.79 | 0 | 19268.79 | 100% |  |  |  |  | 11316.88 |  | 11316.88 | 100% | 234.28 | 0 | 234.28 | 100% | 80% | #DIV/0! | 61.3395 | #DIV/0! | 31.97% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 44956.29 |  | 44956.29 | 100% | 30585.67 |  | 19268.79 | 0 | 19268.79 | 100% |  |  |  |  | 11316.88 |  | 11316.88 | 100% | 234.28 | 0 | 234.28 | 100% | 95% | #DIV/0! | 61.3395 | #DIV/0! | 31.97% | Materials calc for monthly claims | 0 | 2.5 | 0
|  | Week 2 | 44956.29 |  | 44956.29 | 100% | 30585.67 | 112.35 | 19268.79 | 0 | 19268.79 | 100% |  |  |  |  | 11316.88 | 112.35 | 11204.53 | 99.01% | 234.28 | 2.5 | 231.78 | 98.93% | 98% | -44.94 | 61.3395 | #DIV/0! | 31.97% |  |  | -2.5 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  | 0 | 0 | 0% | 100% | #DIV/0! | 0 | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 100% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 100% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
8887 | Tenancy 2 - Fisher Fit out | Start of month | 7495.54 | 0 | 7495.54 | 100% | 5659.85 | 0 | 3768.03 | 0 | 3768.03 | 100% | 0% |  |  |  | 1891.82 | 0 | 1891.82 | 100% | 37.84 | 0 | 37.84 | 100% | 0% | #DIV/0! | 48.5119 | #DIV/0! | 24.49% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 7495.54 | 0 | 7495.54 | 100% | 5659.85 | 0 | 3768.03 | 0 | 3768.03 | 100% | 0% |  |  |  | 1891.82 | 0 | 1891.82 | 100% | 37.84 | 0 | 37.84 | 100% | 0% | #DIV/0! | 48.5119 | #DIV/0! | 24.49% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 7495.54 | 0 | 7495.54 | 100% | 5659.85 | 0 | 3768.03 | 0 | 3768.03 | 100% | 0% |  |  |  | 1891.82 | 0 | 1891.82 | 100% | 37.84 | 0 | 37.84 | 100% | 0% | #DIV/0! | 48.5119 | #DIV/0! | 24.49% |  |  | 0 | 0
|  | Week 3 |  | 0 | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  | 0 | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  | 0 | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
8670 | Studio DB - tautara fit out | Start of month | 100348.26 | 91153 | 9195.26 | 9.163% | 79103.46 | 64224.89 | 62144.61 | 54357.06 | 7787.55 | 12.53% | 0% |  |  |  | 16958.85 | 9867.83 | 7091.02 | 41.81% | 340.12 | 262 | 78.12 | 22.97% | 0% | 102.779 | 62.4627 | 29.54% | 21.17% | Hours calc for monthly claims | -262 | 10 | 1582.92
|  | Week 1 | 100348.26 | 91153 | 9195.26 | 9.163% | 79103.46 | 66212.81 | 62144.61 | 55939.98 | 6204.63 | 9.984% |  |  |  |  | 16958.85 | 10272.83 | 6686.02 | 39.42% | 340.12 | 272 | 68.12 | 20.03% |  | 91.6919 | 62.4627 | 27.36% | 21.17% | Materials calc for monthly claims | -54357.06 | 44.25 | 218.2
|  | Week 2 | 100348.26 | 91153 | 9195.26 | 9.163% | 79103.46 | 68039.14 | 62144.61 | 56158.18 | 5986.43 | 9.633% |  |  |  |  | 16958.85 | 11880.96 | 5077.89 | 29.94% | 340.12 | 316.25 | 23.87 | 7.018% |  | 73.0873 | 62.4627 | 25.36% | 21.17% |  |  | -316.25 | -56158.18
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 90% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 90% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -262 | -54357.06
8907 | 35 Mania | Start of month | 98524.85 | 42682.56 | 55842.29 | 56.68% | 82927.42 | 59094.67 | 64755.29 | 50345.39 | 14409.9 | 22.25% |  |  |  |  | 18172.13 | 8749.28 | 9422.85 | 51.85% | 363.99 | 218.25 | 145.74 | 40.04% | 0% | -75.1987 | 42.8513 | -38.45% | 15.83% | Hours calc for monthly claims | -218.25 | 163.25 | 7441.38
|  | Week 1 | 98524.85 | 93329.71 | 5195.14 | 5.273% | 82927.42 | 73161.13 | 64755.29 | 57786.77 | 6968.52 | 10.76% |  |  |  |  | 18172.13 | 15374.36 | 2797.77 | 15.4% | 363.99 | 381.5 | -17.51 | -4.811% | 20% | 52.8665 | 42.8513 | 21.61% | 15.83% | Materials calc for monthly claims | -50345.39 | 2 | 728.1
|  | Week 2 | 98524.85 | 93329.71 | 5195.14 | 5.273% | 82927.42 | 73980.77 | 64755.29 | 58514.87 | 6240.42 | 9.637% |  |  |  |  | 18172.13 | 15465.9 | 2706.23 | 14.89% | 363.99 | 383.5 | -19.51 | -5.36% | 25% | 50.4536 | 42.8513 | 20.73% | 15.83% |  |  | -383.5 | -58514.87
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 5% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 2% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 25% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 10% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 95% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 10% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -218.25 | -50345.39
9065 | Cooltranz stage 4 | Start of month | 87970.61 | 48945.78 | 39024.83 | 44.36% | 68471.73 | 49900.98 | 52300.56 | 37733.03 | 14567.53 | 27.85% |  |  |  |  | 16171.17 | 12167.95 | 4003.22 | 24.76% | 323.99 | 350 | -26.01 | -8.028% |  | -2.7291 | 60.1836 | -1.952% | 22.17% | Hours calc for monthly claims | -350 | -39.5 | 321.16
|  | Week 1 | 87970.61 | 85555.47 | 2415.14 | 2.745% | 68471.73 | 50194.4 | 52300.56 | 38054.19 | 14246.37 | 27.24% |  |  |  |  | 16171.17 | 12140.21 | 4030.96 | 24.93% | 323.99 | 310.5 | 13.49 | 4.164% | 30% | 113.8843 | 60.1836 | 41.33% | 22.17% | Materials calc for monthly claims | -37733.03 | -310.5 | -38054.19
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 30% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 10% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 10% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -350 | -37733.03
9259 | Andrew Reeve Stage 2 | Start of month | 210242.4 | 14860.85 | 195381.55 | 92.93% | 188013.59 | 33639.16 | 167291.62 | 33639.16 | 133652.46 | 79.89% | 0% |  |  |  | 20721.97 | 0 | 20721.97 | 100% | 416.73 | 0 | 416.73 | 100% | 0% | #DIV/0! | 53.341 | -126.4% | 10.57% | Hours calc for monthly claims | 0 | 0 | 16474.45
|  | Week 1 | 210242.4 | 67511.23 | 142731.17 | 67.89% | 188013.59 | 50113.61 | 167291.62 | 50113.61 | 117178.01 | 70.04% | 0% |  |  |  | 20721.97 |  | 20721.97 | 100% | 416.73 | 0 | 416.73 | 100% | 0% | #DIV/0! | 53.341 | 25.77% | 10.57% | Materials calc for monthly claims | -33639.16 | 0 | 1067.7
|  | Week 2 | 210242.4 | 67511.23 | 142731.17 | 67.89% | 188013.59 | 51181.31 | 167216.61 | 51181.31 | 116035.3 | 69.39% | 0% |  |  |  | 20796.98 |  | 20796.98 | 100% | 416.73 | 0 | 416.73 | 100% | 0% | #DIV/0! | 53.341 | 24.19% | 10.57% |  |  | 0 | -51181.31
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% | [5 empty] | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | -33639.16
8352 | 5 Sanscrit Place | Start of month | 43448.62 | 19551.87 | 23896.75 | 55% | 31063.54 | 25863.55 | 16447.56 | 18255.63 | -1808.07 | -10.99% | 0% |  |  |  | 14615.98 | 7607.92 | 7008.06 | 47.95% | 292.93 | 181.5 | 111.43 | 38.04% | 0% | -34.7751 | 42.28 | -32.28% | 28.51% | Hours calc for monthly claims | -181.5 | 0 | 979.13
|  | Week 1 | 43448.62 | 34758.89 | 8689.73 | 20% | 31063.54 | 26842.68 | 16447.56 | 19234.76 | -2787.2 | -16.95% | 0% |  |  |  | 14615.98 | 7607.92 | 7008.06 | 47.95% | 292.93 | 181.5 | 111.43 | 38.04% | 0% | 43.6155 | 42.28 | 22.77% | 28.51% | Materials calc for monthly claims | -18255.63 | -181.5 | -19234.76
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -181.5 | -18255.63
8234 | Melhuish House | Start of month | 49964.93 | 25359.22 | 24605.71 | 49.25% | 43768.91 | 25556.81 | 37199.62 | 20554.23 | 16645.39 | 44.75% | 0% |  |  |  | 6569.29 | 5002.58 | 1566.71 | 23.85% | 131.78 | 113.75 | 18.03 | 13.68% | 0% | -1.7371 | 47.0179 | -0.7792% | 12.4% | Hours calc for monthly claims | -113.75 | 58 | 7824.22
|  | Week 1 | 49964.93 | 45361.39 | 4603.54 | 9.214% | 43768.91 | 35776.29 | 37199.62 | 28378.45 | 8821.17 | 23.71% |  |  |  |  | 6569.29 | 7397.84 | -828.55 | -12.61% | 131.78 | 171.75 | -39.97 | -30.33% |  | 55.8084 | 47.0179 | 21.13% | 12.4% | Materials calc for monthly claims | -20554.23 | -171.75 | -28378.45
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -113.75 | -20554.23
8214 | 6 Tiroroa Lane | Start of month | 109103.76 | 51323.57 | 57780.19 | 52.96% | 81158.83 | 40300.16 | 52391.31 | 27621.5 | 24769.81 | 47.28% | 20% |  |  |  | 28767.52 | 12678.66 | 16088.86 | 55.93% | 577.33 | 295.5 | 281.83 | 48.82% | 0% | 37.3043 | 48.4037 | 21.48% | 25.61% | Hours calc for monthly claims | -295.5 | 19.25 | 1.96
|  | Week 1 | 109103.76 | 77821.91 | 31281.85 | 28.67% | 81158.83 | 41214.74 | 52391.31 | 27623.46 | 24767.85 | 47.27% | 20% |  |  |  | 28767.52 | 13591.28 | 15176.24 | 52.75% | 577.33 | 314.75 | 262.58 | 45.48% | 0% | 116.3055 | 48.4037 | 47.04% | 25.61% | Materials calc for monthly claims | -27621.5 | -314.75 | -27623.46
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 20% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 20% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 25% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -295.5 | -27621.5
6792 | Major Hornbrook | Start of month | 27742.44 | 0 | 27742.44 | 100% | 20094.24 | 405.4 | 11429.46 | 73.74 | 11355.72 | 99.35% | 0% |  |  |  | 8664.78 | 331.66 | 8333.12 | 96.17% | 173.8 | 7.75 | 166.05 | 95.54% |  | -52.3097 | 44.0058 | #DIV/0! | 27.57% | Hours calc for monthly claims | -7.75 | 0 | -13.89
|  | Week 1 | 27861.41 | 0 | 27861.41 | 100% | 20162.08 | 392.27 | 11464.04 | 59.85 | 11404.19 | 99.48% | 0% |  |  |  | 8698.04 | 332.42 | 8365.62 | 96.18% | 174.46 | 7.75 | 166.71 | 95.56% |  | -50.6155 | 44.1324 | #DIV/0! | 27.63% | Materials calc for monthly claims | -73.74 | -7.75 | -59.85
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -7.75 | -73.74
8840 | Inline Architecture | Start of month | 21300.45 | 5515.31 | 15785.14 | 74.11% | 11275.69 | 5128.09 | 4165.39 | 815.93 | 3349.46 | 80.41% | 100% |  |  |  | 7110.3 | 1880.39 | 5229.91 | 73.55% | 142.36 | 42.25 | 100.11 | 70.32% | 100% | 66.7217 | 70.4184 | 51.11% | 47.06% | Hours calc for monthly claims | -42.25 | 14.25 | 2844.83
|  | Week 1 | 21300.45 | 10143.09 | 11157.36 | 52.38% | 11275.69 | 6237.89 | 4165.39 | 3660.76 | 504.63 | 12.11% | 100% |  |  |  | 7110.3 | 2577.13 | 4533.17 | 63.75% | 142.36 | 56.5 | 85.86 | 60.31% | 100% | 69.1186 | 70.4184 | 38.5% | 47.06% | Materials calc for monthly claims | -815.93 | -56.5 | -3660.76
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 100% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 100% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -42.25 | -815.93
8769 | Percival Bach | Start of month | 63405.46 | 0 | 63405.46 | 100% | 43553.81 | 9012.69 | 29573.66 | 8270.88 | 21302.78 | 72.03% | 0% |  |  |  | 13980.15 | 741.81 | 13238.34 | 94.69% | 279.87 | 52 | 227.87 | 81.42% | 0% | -173.321 | 70.9317 | #DIV/0! | 31.31% | Hours calc for monthly claims | -52 | 36.5 | 3381.04
|  | Week 1 | 63405.46 | 23507.97 | 39897.49 | 62.92% | 43553.81 | 15599.26 | 29573.66 | 11651.92 | 17921.74 | 60.6% | 0% |  |  |  | 13980.15 | 3947.34 | 10032.81 | 71.76% | 279.87 | 88.5 | 191.37 | 68.38% | 0% | 89.364 | 70.9317 | 33.64% | 31.31% | Materials calc for monthly claims | -8270.88 | -88.5 | -11651.92
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -52 | -8270.88
7901 | St Albans Street | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
8923 | 4 Perry St | Start of month | 47191.69 | 32679.16 | 14512.53 | 30.75% | 30406.12 | 21779.51 | 15384 | 8004.44 | 7379.56 | 47.97% | 0% |  |  |  | 15022.12 | 13775.07 | 1247.05 | 8.301% | 301.53 | 180.75 | 120.78 | 40.06% | 0% | 60.3024 | 55.668 | 33.35% | 35.57% | Hours calc for monthly claims | -180.75 | 4.5 | 5821.52
|  | Week 1 | 47191.69 | 35940.5 | 11251.19 | 23.84% | 30406.12 | 22080.06 | 15505.37 | 13825.96 | 1679.41 | 10.83% | 0% |  |  |  | 14900.75 | 8254.1 | 6646.65 | 44.61% | 301.53 | 185.25 | 116.28 | 38.56% | 0% | 74.8202 | 55.668 | 38.56% | 35.57% | Materials calc for monthly claims | -8004.44 | -185.25 | -13825.96
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -180.75 | -8004.44
7864 | Ryans House | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 473 | 0 | 473 | 100% | 0% | #DIV/0! | 0 | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
7912 | 71A Fendalton Road | Start of month | 23650.59 | 0 | 23650.59 | 100% | 15376.98 | 1628.64 | 8582.1 | 53.06 | 8529.04 | 99.38% |  |  |  |  | 6794.88 | 1575.58 | 5219.3 | 76.81% | 135.9 | 30.5 | 105.4 | 77.56% |  | -53.398 | 60.8801 | #DIV/0! | 34.98% | Hours calc for monthly claims | 73.75 | 32.25 | 377.73
|  | Week 1 | 23650.59 | 5602.1 | 18048.49 | 76.31% | 15376.98 | 3604.74 | 8582.1 | 430.79 | 8151.31 | 94.98% |  |  |  |  | 6794.88 | 3173.95 | 3620.93 | 53.29% | 135.9 | 62.75 | 73.15 | 53.83% |  | 31.8304 | 60.8801 | 35.65% | 34.98% | Materials calc for monthly claims | 3637.44 | 32 | 1239.42
|  | Week 2 | 23650.59 | 5602.1 | 18048.49 | 76.31% | 15376.98 | 6523.55 | 8582.1 | 1670.21 | 6911.89 | 80.54% |  |  |  |  | 6794.88 | 4853.34 | 1941.54 | 28.57% | 135.9 | 94.75 | 41.15 | 30.28% |  | -9.7251 | 60.8801 | -16.45% | 34.98% |  |  | 0.5 | 2020.29
|  | Week 3 | 23650.59 | 5602.1 | 18048.49 | 76.31% | 15376.98 | 8543.84 | 8582.1 | 3690.5 | 4891.6 | 57% |  |  |  |  | 6794.88 | 4853.34 | 1941.54 | 28.57% | 135.9 | 95.25 | 40.65 | 29.91% |  | -30.8844 | 60.8801 | -52.51% | 34.98% | Estimated months claim | 0 | 9 | 0
|  | Week 4 | 23650.59 | 5602.1 | 18048.49 | 76.31% | 15376.98 | 9041.54 | 8582.1 | 3690.5 | 4891.6 | 57% |  |  |  |  | 6794.88 | 5351.04 | 1443.84 | 21.25% | 135.9 | 104.25 | 31.65 | 23.29% |  | -32.9922 | 60.8801 | -61.4% | 34.98% |  |  | 0 | 0
|  | Week 5 | 23650.59 | 5602.1 | 18048.49 | 76.31% | 15376.98 | 9041.54 | 8582.1 | 3690.5 | 4891.6 | 57% |  |  |  |  | 6794.88 | 5351.04 | 1443.84 | 21.25% | 135.9 | 104.25 | 31.65 | 23.29% |  | -32.9922 | 60.8801 | -61.4% | 34.98% |  |  | 73.75 | 3637.44
8360 | Dixon House | Start of month | 29188.19 | 38245.41 | -9057.22 | -31.03% | 17590 | 36039.07 | 9253.76 | 35607.58 | -26353.82 | -284.8% |  |  |  |  | 8336.24 | 431.49 | 7904.75 | 94.82% | 166.98 | 9.75 | 157.23 | 94.16% |  | 226.2913 | 69.4586 | 5.769% | 39.74% | Hours calc for monthly claims | -9.75 | 0 | 0
|  | Week 1 | 29188.19 | 38245.41 | -9057.22 | -31.03% | 17590 | 36039.07 | 9253.76 | 35607.58 | -26353.82 | -284.8% |  |  |  |  | 8336.24 | 431.49 | 7904.75 | 94.82% | 166.98 | 9.75 | 157.23 | 94.16% |  | 226.2913 | 69.4586 | 5.769% | 39.74% | Materials calc for monthly claims | -35607.58 | 4.5 | -197.56
|  | Week 2 | 29188.19 | 38245.41 | -9057.22 | -31.03% | 17590 | 36039.07 | 9253.76 | 35410.02 | -26156.26 | -282.7% |  |  |  |  | 8336.24 | 629.05 | 7707.19 | 92.45% | 166.98 | 14.25 | 152.73 | 91.47% |  | 154.8309 | 69.4586 | 5.769% | 39.74% |  |  | 7.25 | 646.81
|  | Week 3 | 29188.19 | 38245.41 | -9057.22 | -31.03% | 17590 | 37012.71 | 9253.76 | 36056.83 | -26803.07 | -289.6% |  |  |  |  | 8336.24 | 955.88 | 7380.36 | 88.53% | 166.98 | 21.5 | 145.48 | 87.12% |  | 57.3349 | 69.4586 | 3.223% | 39.74% | Estimated months claim | 0 | -21.5 | -36056.83
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -9.75 | -35607.58
8337 | Waimak Dairys | Start of month | 15025.89 | 0 | 15025.89 | 100% | 10929.18 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 5126.09 | 0 | 5126.09 | 100% | 102.81 | 0 | 102.81 | 100% |  | #DIV/0! | 96.2922 | #DIV/0! | 27.26% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
9240 | Daves Twizel Shack | Start of month | 300839.52 | 0 | 300839.52 | 100% | 243747.98 | 70092.2 | 183229.46 | 69898.65 | 113330.81 | 61.85% |  |  |  |  | 60518.52 | 193.55 | 60324.97 | 99.68% | 1213 | 0 | 1213 | 100% |  | #DIV/0! | 47.0664 | #DIV/0! | 18.98% | Hours calc for monthly claims | 0 | 3.5 | -10.8
|  | Week 1 | 300839.52 | 93431.66 | 207407.86 | 68.94% | 243747.98 | 70081.4 | 183229.46 | 69887.85 | 113341.61 | 61.86% |  |  |  |  | 60518.52 | 193.55 | 60324.97 | 99.68% | 1213.28 | 3.5 | 1209.78 | 99.71% |  | 6671.5029 | 47.0555 | 24.99% | 18.98% | Materials calc for monthly claims | -69898.65 | -3.5 | -69887.85
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | -69898.65
7428 | FAB Pegasus Lakeside | Start of month | 58426.32 | 0 | 58426.32 | 100% | 44815.36 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 19242.55 | 0 | 19242.55 | 100% | 385.7 | 0 | 385.7 | 100% |  | #DIV/0! | 101.5913 | #DIV/0! | 23.3% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 58426.32 | 0 | 0 | 0% | 44815.36 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 19242.55 | 0 | 19242.55 | 100% | 385.7 | 0 | 385.7 | 100% |  | #DIV/0! | 101.5913 | #DIV/0! | 23.3% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
9351 | Harewood Golf Club | Start of month | 18080.64 | 0 | 18080.64 | 100% | 13540.24 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 5455.24 | 0 | 5455.24 | 100% | 109.34 | 0 | 109.34 | 100% |  | #DIV/0! | 115.4692 | #DIV/0! | 25.11% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 18080.64 | 0 | 0 | 0% | 13540.24 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 5455.24 | 0 | 5455.24 | 100% | 109.34 | 0 | 109.34 | 100% |  | #DIV/0! | 115.4692 | #DIV/0! | 25.11% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
7429 | Taggart House | Start of month | 17608.26 | 0 | 17608.26 | 100% | 14076.97 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 5790.51 | 0 | 5790.51 | 100% | 116.13 | 0 | 116.13 | 100% |  | #DIV/0! | 101.7631 | #DIV/0! | 20.05% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 17608.26 | 0 | 0 | 0% | 14076.97 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 5790.51 | 0 | 5790.51 | 100% | 116.13 | 0 | 116.13 | 100% |  | #DIV/0! | 101.7631 | #DIV/0! | 20.05% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
9508 | St Barnabas Church | Start of month | 19572.81 | 0 | 19572.81 | 100% | 11314.42 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 5290.42 | 0 | 5290.42 | 100% | 105 | 0 | 105 | 100% | 0% | #DIV/0! | 136.0228 | #DIV/0! | 42.19% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
0 | 0 | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 346 | 0 | 346 | 100% |  | #DIV/0! | 0 | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
0 | Contracting | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
8946 | Westcoast Vaults | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
8308 | Roydvale | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0

## Sheet1
340 | Allowed | Actual | % of job
Box out | 30 |  | 8.824%
pre-wire | 60 |  |  | 95.35
cut out | 100 |  |  | 102.69
fit off lights | 150 |  |  | 134.82
324.19
415