## Main Sheet
Updated Job Spreadsheet
Job Number | Job Name | Job Owner | Contract Signed & Returned. Retention % loaded correctly into Katipolt | Warranty Signed & Returned | Construction Programme Received | Into Work Calculator 2 Weekly | Temp Application Done | Mains Connection Application | POs Sent to Sub contractors | Switchboard Drawing Sent for Approval | Email Sent to QS/Builder to Confirm Order Gear | Long Lead Time Materials Ordered |  | Client Walk Through | Pre Job Meeting Completed with Staff Job Pack Made | O&M Manual underway (notes for what's needed) | QA Completed By Others |  | Job Completion Paperwork Completed | All V.Os captured | Last toolbox date
[12 empty] | Ordered | Lead Times Comm. |  |  |  | 1st Fix | 2nd Fix
7658 | Charity Hospital | Cameron | Yes |  | Yes | Yes | N/A | N/A | Yes | Yes | Yes | Yes |  |  | Yes
8142 | Fisher Developements | Cameron | Yes |  | Yes | yes | Yes | Yes | Yes | Yes |  | Yes
8824 | 3 Innovation Road | Cameron
8127 | Rolly Autowash | Cameron | Yes |  | Yes | No | Yes | Yes | N/A | Yes |  | Yes
8183 | Murney - 1 Freight Drive + 109 Iport | Cameron | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes |  | Yes
8886 | Monkey Toe - Fisher fit out | Cameron |  |  | Yes | No | N/A | Yes | Yes | Yes
8887 | Tenancy 2 - Fisher Fit out | Cameron |  |  | Yes | No | N/A | Yes | Yes | Yes
8670 | Studio DB - tautara fit out | Cameron | Yes
8907 | 35 Mania | Cameron | Yes
9065 | Cooltranz stage 4 | Cameron
9259 | Andrew Reeve Stage 2 | Cameron
8352 | 5 Sanscrit Place | Tom | Yes | N/A | Yes |  | N/A | N/A |  | N/A | Yes |  |  | Yes
8234 | Melhuish House | Tom
8214 | 6 Tiroroa Lane | Tom | Yes | N/A | [5 empty] | N/A
6792 | Major Hornbrook | Tom | Yes | N/A | Yes | 2025-11-18 | Yes | Yes | N/A | N/A | N/A |  |  | No |  | NA
8840 | Inline Architecture | Tom
8769 | Percival Bach
7901 | St Albans Street
8923 | 4 Perry St
7864 | Ryans House
7912 | 71A Fendalton Road | Tom | Yes | N/A |  | 2025-11-18 |  |  | N/A | N/A |  |  |  | No
8360 | Dixon House | Tom | Yes | N/A | Yes | 2025-11-18 | N/A | Yes | N/A | N/A | N/A | N/A |  | Yes
8337 | Waimak Dairys
9240 | Daves Twizel Shack
7428 | FAB Pegasus Lakeside | Tom | Yes | N/A | Yes | 2025-11-18 | Yes |  | N/A | N/A | N/A |  |  | No
9351 | Harewood Golf Club | Tom
7429 | Taggart House | Tom | Yes | N/A | Yes | 2025-11-18 | N/A | N/A | N/A | N/A | N/A |  |  | No
9508 | St Barnabas Church | Tom |  | N/A | Yes | 2025-11-18 | N/A | N/A | N/A | N/A | N/A |  |  | No
|  |  |  | N/A | Yes |  | N/A |  | N/A
Contracting
8946 | Westcoast Vaults | Cameron
8308 | Roydvale | Tom |  | N/A | Yes |  | N/A |  | N/A

## Deliverables Sheet
Updated Job Spreadsheet
Job Number | Job Name | Week | Quoted Price | Claim to date | Remaining to claim | % Claim remaining | Total quoted cost | Total actual cost | Quoted material cost | Actual material cost | Material cost remaining | Material % remaining | Estimated % of materials recieved | Quoted labour cost | Actual labour cost | Labour cost remaining | Labour cost % remaining | Quoted labour hours | Actual labour hours | Labour hours remaining | Labour hour % remaining | Estimated % of job complete | GP $ Per Hour | Quoted GP $ Per Hour | Margin to date | Quoted margin
[29 empty] | Hours calcs | Materials calcs
7658 | Charity Hospital | Start of month | 215046.91 | 205915.9 | 9131.01 | 4.246% | 181293.63 | 113522.99 | 155024.75 | 92952.56 | 62072.19 | 40.04% | 90% | 26268.88 | 20570.43 | 5698.45 | 21.69% | 530.95 | 418 | 112.95 | 21.27% |  | 221.0357 | 63.5715 | 44.87% | 15.7% | Hours calc for monthly claims | -418 | -418 | -92952.56
|  | Week 1 | 233882.27 | 205915.9 | 27966.37 | 11.96% | 199128.99 | 161636.57 | 172860.11 | 136958.29 | 35901.82 | 20.77% |  | 26268.88 | 24678.28 | 1590.6 | 6.055% | 530.95 | 498.25 | 32.7 | 6.159% |  | 88.8697 | 65.4549 | 21.5% | 14.86% | Materials calc for monthly claims | -92952.56
Week 2
|  | Week 3 | 233882.27 | 205915.9 | 27966.37 | 11.96% | 199128.99 | 165210.04 | 172860.11 | 137410.69 | 35449.42 | 20.51% |  | 26268.88 | 27799.35 | -1530.47 | -5.826% | 530.95 | 556.5 | -25.55 | -4.812% |  | 73.1462 | 65.4549 | 19.77% | 14.86% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -418 | -92952.56
8142 | Fisher Developements | Start of month | 95023.47 | 51156.11 | 43867.36 | 46.16% | 72292.47 | 48296.81 | 56719.74 | 45701.86 | 11017.88 | 19.43% |  | 15572.73 | 2594.95 | 12977.78 | 83.34% | 311.89 | 52.5 | 259.39 | 83.17% | 30% | 54.4629 | 72.8815 | 5.589% | 23.92% | Hours calc for monthly claims | -52.5 | -52.5 | -45701.86
|  | Week 1 | 129074.86 | 55068.11 | 74006.75 | 57.34% | 101420.72 | 54810.2 | 83645.65 | 51716.87 | 31928.78 | 38.17% |  | 17775.07 | 3093.33 | 14681.74 | 82.6% | 356.07 | 63 | 293.07 | 82.31% |  | 4.0938 | 77.6649 | 0.47% | 21.42% | Materials calc for monthly claims | -45701.86
Week 2
|  | Week 3 | 129074.86 | 55068.11 | 74006.75 | 57.34% | 101420.72 | 54087.96 | 83645.65 | 49628.88 | 34016.77 | 40.67% |  | 17775.07 | 4459.08 | 13315.99 | 74.91% | 356.07 | 90.75 | 265.32 | 74.51% |  | 10.8006 | 77.6649 | 1.78% | 21.42% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -52.5 | -45701.86
8824 | 3 Innovation Road | Start of month | 27500.32 | 6999.08 | 20501.24 | 74.55% | 19565.83 | 7621.92 | 13767.34 | 5911.24 | 7856.1 | 57.06% |  | 5798.49 | 1710.68 | 4087.81 | 70.5% | 125.39 | 34.75 | 90.64 | 72.29% | 25% | -17.9235 | 63.2785 | -8.899% | 28.85% | Hours calc for monthly claims | -34.75 | -34.75 | -5911.24
|  | Week 1 | [24 empty] | Materials calc for monthly claims | -5911.24
Week 2
|  | Week 3 | 27500.32 | 6999.08 | 20501.24 | 74.55% | 19565.83 | 7621.92 | 13767.34 | 5911.24 | 7856.1 | 57.06% |  | 5798.49 | 1710.68 | 4087.81 | 70.5% | 125.39 | 34.75 | 90.64 | 72.29% |  | -17.9235 | 63.2785 | -8.9% | 28.85% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -34.75 | -5911.24
8127 | Rolly Autowash | Start of month | 150850.82 | 111983.72 | 38867.1 | 25.77% | 102178.42 | 75718.13 | 62464.86 | 56964.81 | 5500.05 | 8.805% | 90% | 39713.56 | 18753.32 | 20960.24 | 52.78% | 795.22 | 388.25 | 406.97 | 51.18% | 60% | 93.4078 | 61.2062 | 32.38% | 32.27% | Hours calc for monthly claims | -388.25 | -388.25 | -56964.81
|  | Week 1 | 150850.82 | 111983.72 | 38867.1 | 25.77% | 102178.42 | 81033.37 | 62464.86 | 58088.59 | 4376.27 | 7.006% |  | 39713.56 | 22944.78 | 16768.78 | 42.22% | 795.22 | 472.75 | 322.47 | 40.55% |  | 65.4687 | 61.2062 | 27.64% | 32.27% | Materials calc for monthly claims | -56964.81
Week 2
|  | Week 3 | 150850.82 | 111983.72 | 38867.1 | 25.77% | 102178.42 | 84545.62 | 62464.86 | 58627.5 | 3837.36 | 6.143% |  | 39713.56 | 25918.12 | 13795.44 | 34.74% | 795.22 | 531.25 | 263.97 | 33.19% |  | 51.6482 | 61.2062 | 24.5% | 32.27% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -388.25 | -56964.81
8183 | Murney - 1 Freight Drive + 109 Iport | Start of month | 389022.03 | 176161.65 | 212860.38 | 54.72% | 320431.12 | 148939.51 | 264519.78 | 132316.71 | 132203.07 | 49.98% |  | 55911.34 | 16622.8 | 39288.54 | 70.27% | 1120.27 | 387.5 | 732.77 | 65.41% | 40% | 70.2507 | 61.2271 | 15.45% | 17.63% | Hours calc for monthly claims | -387.5 | -387.5 | -132316.71
|  | Week 1 | 396422.03 | 176161.65 | 220260.38 | 55.56% | 327431.12 | 150094.16 | 271519.78 | 132259.14 | 139260.64 | 51.29% |  | 55911.34 | 17835.02 | 38076.32 | 68.1% | 1120.27 | 416.25 | 704.02 | 62.84% |  | 62.6246 | 61.5842 | 14.8% | 17.4% | Materials calc for monthly claims | -132316.71
Week 2
|  | Week 3 | 396422.03 | 176161.65 | 220260.38 | 55.56% | 327431.12 | 150094.16 | 271519.78 | 132259.14 | 139260.64 | 51.29% |  | 55911.34 | 17835.02 | 38076.32 | 68.1% | 1120.27 | 416.25 | 704.02 | 62.84% |  | 62.6246 | 61.5842 | 14.8% | 17.4% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -387.5 | -132316.71
8886 | Monkey Toe - Fisher fit out | Start of month | 128258.5 | 36398.39 | 91860.11 | 71.62% | 94098.32 | 32521.46 | 69042.09 | 26847.46 | 42194.63 | 61.11% |  | 25056.23 | 5674 | 19382.23 | 77.35% | 501 | 112 | 389 | 77.64% | 40% | 34.6154 | 68.184 | 10.65% | 26.63% | Hours calc for monthly claims | -112 | -112 | -26847.46
|  | Week 1 | 128258.5 | 36398.39 | 91860.11 | 71.62% | 94098.32 | 35395.54 | 69042.09 | 29132.06 | 39910.03 | 57.81% |  | 25056.23 | 6263.48 | 18792.75 | 75% | 501.83 | 122.75 | 379.08 | 75.54% |  | 8.1699 | 68.0712 | 2.76% | 26.63% | Materials calc for monthly claims | -26847.46
|  | Week 2 | 128258.5 | 36398.39 | 91860.11 | 71.62% | 94098.32 | 34659.62 | 69042.09 | 28340.06 | 40702.03 | 58.95% |  | 25056.23 | 6319.56 | 18736.67 | 74.78% | 501.83 | 123.75 | 378.08 | 75.34% |  | 14.0507 | 68.0712 | 4.78% | 26.63%
|  | Week 3 | 128258.5 | 36398.39 | 91860.11 | 71.62% | 94098.32 | 34818.98 | 69042.09 | 28340.06 | 40702.03 | 58.95% |  | 25056.23 | 6478.92 | 18577.31 | 74.14% | 501.83 | 127.75 | 374.08 | 74.54% |  | 12.3633 | 68.0712 | 4.34% | 26.63% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -112 | -26847.46
8887 | Tenancy 2 - Fisher Fit out | Start of month | 64305.21 | 25322.07 | 38983.14 | 60.62% | 49749.48 | 19566.87 | 39151.4 | 15639.05 | 23512.35 | 60.05% | 0% | 10598.08 | 3927.82 | 6670.26 | 62.94% | 212.3 | 86.75 | 125.55 | 59.14% | 40% | 66.3424 | 68.5621 | 22.73% | 22.64% | Hours calc for monthly claims | -86.75 | -86.75 | -15639.05
|  | Week 1 | 65693.36 | 25322.07 | 40371.29 | 61.45% | 50582.37 | 21491.46 | 39438.99 | 16895.88 | 22543.11 | 57.16% |  | 11143.38 | 4595.58 | 6547.8 | 58.76% | 223.22 | 100.25 | 122.97 | 55.09% |  | 38.2106 | 67.6955 | 15.13% | 23% | Materials calc for monthly claims | -15639.05
|  | Week 2 | 65693.36 | 25322.07 | 40371.29 | 61.45% | 50582.37 | 25131.9 | 39438.99 | 20456.64 | 18982.35 | 48.13% |  | 11143.38 | 4675.26 | 6468.12 | 58.04% | 223.22 | 102.25 | 120.97 | 54.19% |  | 1.8599 | 67.6955 | 0.75% | 23%
|  | Week 3 | 65693.36 | 25322.07 | 40371.29 | 61.45% | 50582.37 | 25211.58 | 39438.99 | 20456.64 | 18982.35 | 48.13% |  | 11143.38 | 4754.94 | 6388.44 | 57.33% | 223.22 | 104.25 | 118.97 | 53.3% |  | 1.0599 | 67.6955 | 0.44% | 23% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -86.75 | -15639.05
8670 | Studio DB - tautara fit out | Start of month | 150152.16 | 98562.5 | 51589.66 | 34.36% | 105626.39 | 79936.19 | 72224.17 | 66399.88 | 5824.29 | 8.064% |  | 33402.22 | 13536.31 | 19865.91 | 59.47% | 668.92 | 269 | 399.92 | 59.79% | 30% | 69.2428 | 66.5637 | 18.9% | 29.65% | Hours calc for monthly claims | -269 | -269 | -66399.88
|  | Week 1 | 154527.79 | 98562.5 | 55965.29 | 36.22% | 108880.28 | 91409.03 | 74953.01 | 72957.27 | 1995.74 | 2.663% |  | 33927.27 | 18451.76 | 15475.51 | 45.61% | 679.42 | 386.5 | 292.92 | 43.11% |  | 18.5083 | 67.186 | 7.26% | 29.54% | Materials calc for monthly claims | -66399.88
|  | Week 2 | 154527.79 | 98562.5 | 55965.29 | 36.22% | 108880.28 | 90918.83 | 74953.01 | 71302.07 | 3650.94 | 4.871% |  | 33927.27 | 19616.76 | 14310.51 | 42.18% | 679.42 | 413 | 266.42 | 39.21% |  | 18.5077 | 67.186 | 7.76% | 29.54%
|  | Week 3 | 154527.79 | 98562.5 | 55965.29 | 36.22% | 108880.28 | 91257.87 | 74953.01 | 71042.07 | 3910.94 | 5.218% |  | 33927.27 | 20215.8 | 13711.47 | 40.41% | 679.42 | 427 | 252.42 | 37.15% |  | 17.1069 | 67.186 | 7.41% | 29.54% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -269 | -66399.88
8907 | 35 Mania | Start of month | 20420.56 | 16358.37 | 4062.19 | 19.89% | 15859.68 | 12193.17 | 12689.1 | 11159.14 | 1529.96 | 12.06% |  | 3170.58 | 1034.03 | 2136.55 | 67.39% | 63.5 | 26.75 | 36.75 | 57.87% | 40% | 155.7084 | 71.8249 | 25.46% | 22.33% | Hours calc for monthly claims | -26.75 | -26.75 | -11159.14
|  | Week 1 | 20420.56 | 16358.37 | 4062.19 | 19.89% | 15859.68 | 12992.52 | 12689.1 | 11685.13 | 1003.97 | 7.912% |  | 3170.58 | 1307.39 | 1863.19 | 58.76% | 63.5 | 33.25 | 30.25 | 47.64% |  | 101.2286 | 71.825 | 20.58% | 22.33% | Materials calc for monthly claims | -11159.14
|  | Week 2 | 20420.56 | 16358.37 | 4062.19 | 19.89% | 15859.68 | 13601.05 | 12689.1 | 11685.13 | 1003.97 | 7.912% |  | 3170.58 | 1915.92 | 1254.66 | 39.57% | 63.5 | 47.5 | 16 | 25.2% |  | 58.0488 | 71.825 | 16.86% | 22.33%
|  | Week 3 | 20420.56 | 16358.37 | 4062.19 | 19.89% | 15859.68 | 13642 | 12689.1 | 11685.13 | 1003.97 | 7.912% |  | 3170.58 | 1956.87 | 1213.71 | 38.28% | 63.5 | 48.25 | 15.25 | 24.02% |  | 56.2978 | 71.825 | 16.61% | 22.33% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -26.75 | -11159.14
9065 | Cooltranz stage 4 | Start of month | 46303.5 | 6131.46 | 40172.04 | 86.76% | 34612.41 | 5397.27 | 26584.53 | 5397.27 | 21187.26 | 79.7% |  | 8027.88 | 0 | 8027.88 | 100% | 160.82 | 0 | 160.82 | 100% |  |  | 72.6967 | 11.97% | 25.25% | Hours calc for monthly claims |  |  | -5397.27
|  | Week 1 | 46303.5 | 6131.46 | 40172.04 | 86.76% | 34612.41 | 9981.43 | 26584.53 | 9832.65 | 16751.88 | 63.01% |  | 8027.88 | 148.78 | 7879.1 | 98.15% | 160.82 | 2.75 | 158.07 | 98.29% |  | -1399.9891 | 72.6968 | -62.79% | 25.25% | Materials calc for monthly claims | -5397.27
Week 2
|  | Week 3 | 46303.5 | 6131.46 | 40172.04 | 86.76% | 34612.41 | 9981.43 | 26584.53 | 9832.65 | 16751.88 | 63.01% |  | 8027.88 | 148.78 | 7879.1 | 98.15% | 160.82 | 2.75 | 158.07 | 98.29% |  | -1399.9891 | 72.6968 | -62.79% | 25.25% | Estimated months claim | 0
Week 4
|  | Week 5 | [27 empty] | -5397.27
9259 | Andrew Reeve Stage 2 | Start of month |  |  | [object Object] |  |  |  | [object Object] | [object Object] | [object Object] |  |  |  |  | [object Object] |  | 470.3 |  | 470.3 | 100% | 0% |  | [object Object] |  |  | Hours calc for monthly claims
|  | Week 1 | 77166.16 | 0 | 77166.16 | 100% | 54302.66 | 12474.95 | 31383.39 | 12474.95 | 18908.44 | 60.25% |  | 22919.27 | 0 | 22919.27 | 100% | 470.62 | 0 | 470.62 | 100% |  | 0 | 48.5817 | 0% | 29.63% | Materials calc for monthly claims
|  | Week 2 | 77166.16 | 0 | 77166.16 | 100% | 54302.66 | 22353.17 | 31383.39 | 22353.17 | 9030.22 | 28.77% |  | 22919.27 | 0 | 22919.27 | 100% | 470.62 | 0 | 470.62 | 100% |  | 0 | 48.5817 | 0% | 29.63%
|  | Week 3 | 77166.16 | 0 | 77166.16 | 100% | 54302.66 | 25724.04 | 31383.39 | 25724.04 | 5659.35 | 18.03% |  | 22919.27 | 0 | 22919.27 | 100% | 470.62 | 0 | 470.62 | 100% |  | 0 | 48.5817 | 0% | 29.63% | Estimated months claim | 0
Week 4
Week 5
8352 | 5 Sanscrit Place | Start of month | 25467.84 | 19598.41 | 5869.43 | 23.05% | 16606.83 | 12921.64 | 9659.99 | 5569.48 | 4090.51 | 42.34% | 0% | 6946.84 | 7352.16 | -405.32 | -5.835% | 139.07 | 143.25 | -4.18 | -3.006% |  | 46.6092 | 63.7162 | 34.07% | 34.79% | Hours calc for monthly claims | -143.25 | -143.25 | -5569.48
|  | Week 1 | 25467.84 | 19598.41 | 5869.43 | 23.05% | 16606.83 | 12729.14 | 9659.99 | 5354.12 | 4305.87 | 44.57% |  | 6946.84 | 7375.02 | -428.18 | -6.164% | 139.07 | 143.25 | -4.18 | -3.006% |  | 47.953 | 63.7162 | 35.05% | 34.79% | Materials calc for monthly claims | -5569.48
Week 2
|  | Week 3 | 25467.84 | 19598.41 | 5869.43 | 23.05% | 16606.83 | 12729.14 | 9659.99 | 5354.12 | 4305.87 | 44.57% |  | 6946.84 | 7375.02 | -428.18 | -6.164% | 139.07 | 143.25 | -4.18 | -3.006% |  | 47.953 | 63.7162 | 35.05% | 34.79% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -143.25 | -5569.48
8234 | Melhuish House | Start of month | 37083.03 | 33023.07 | 4059.96 | 10.95% | 27002.93 | 21520.62 | 15440.32 | 14143.19 | 1297.13 | 8.401% | 0% | 11562.61 | 7377.43 | 4185.18 | 36.2% | 231.75 | 148.5 | 83.25 | 35.92% |  | 77.4576 | 43.4956 | 34.83% | 27.18% | Hours calc for monthly claims | -148.5 | -148.5 | -14143.19
|  | Week 1 | 37083.03 | 33023.07 | 4059.96 | 10.95% | 27002.93 | 25023.81 | 15440.32 | 15309.99 | 130.33 | 0.8441% |  | 11562.61 | 9713.82 | 1848.79 | 15.99% | 231.75 | 198.75 | 33 | 14.24% |  | 40.2478 | 43.4956 | 24.22% | 27.18% | Materials calc for monthly claims | -14143.19
|  | Week 2 | 37083.03 | 33023.07 | 4059.96 | 10.95% | 27002.93 | 25996.77 | 15440.32 | 15990.78 | -550.46 | -3.565% |  | 11562.61 | 10005.99 | 1556.62 | 13.46% | 231.75 | 204.75 | 27 | 11.65% |  | 34.3165 | 43.4956 | 21.28% | 27.18%
|  | Week 3 | 37083.03 | 33023.07 | 4059.96 | 10.95% | 27002.93 | 26156.33 | 15440.32 | 16043.36 | -603.04 | -3.906% |  | 11562.61 | 10112.97 | 1449.64 | 12.54% | 231.75 | 207.25 | 24.5 | 10.57% |  | 33.1326 | 43.4956 | 20.79% | 27.18% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -148.5 | -14143.19
8214 | 6 Tiroroa Lane | Start of month | 26186.14 | 5762.27 | 20423.87 | 77.99% | 19428.98 | 7925.81 | 12051.32 | 7679.91 | 4371.41 | 36.27% | 0% | 7377.66 | 245.9 | 7131.76 | 96.67% | 147.9 | 5 | 142.9 | 96.62% |  | -432.708 | 45.6874 | -37.55% | 25.8% | Hours calc for monthly claims | -5 | -5 | -7679.91
|  | Week 1 | [24 empty] | Materials calc for monthly claims | -7679.91
Week 2
|  | Week 3 | 26186.14 | 5762.27 | 20423.87 | 77.99% | 19428.98 | 7925.81 | 12051.32 | 7679.91 | 4371.41 | 36.27% |  | 7377.66 | 245.9 | 7131.76 | 96.67% | 147.9 | 5 | 142.9 | 96.62% |  | -432.708 | 45.6874 | -37.55% | 25.8% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -5 | -7679.91
6792 | Major Hornbrook | Start of month | 33188.02 | 33188.03 | -0.01 | -3.013e-05% | 23790.07 | 32303.46 | 13406.21 | 16562.52 | -3156.31 | -23.54% | 0% | 10383.86 | 15740.94 | -5357.08 | -51.59% | 208.2 | 317.25 | -109.05 | -52.38% |  | 2.7882 | 45.139 | 2.665% | 28.32% | Hours calc for monthly claims | -317.25 | -317.25 | -16562.52
|  | Week 1 | 32473.02 | 33188.03 | -715.01 | -2.202% | 23075.07 | 30946.57 | 12691.21 | 15205.63 | -2514.42 | -19.81% |  | 10383.86 | 15740.94 | -5357.08 | -51.59% | 208.2 | 317.25 | -109.05 | -52.38% |  | 7.0653 | 45.1391 | 6.75% | 28.94% | Materials calc for monthly claims | -16562.52
|  | Week 2 | 32473.02 | 33188.03 | -715.01 | -2.202% | 23075.07 | 31131.57 | 12691.21 | 15390.63 | -2699.42 | -21.27% |  | 10383.86 | 15740.94 | -5357.08 | -51.59% | 208.2 | 317.25 | -109.05 | -52.38% |  | 6.4821 | 45.1391 | 6.2% | 28.94%
|  | Week 3 | 32473.02 | 33188.03 | -715.01 | -2.202% | 23075.07 | 31131.57 | 12691.21 | 15390.63 | -2699.42 | -21.27% |  | 10383.86 | 15740.94 | -5357.08 | -51.59% | 208.2 | 317.25 | -109.05 | -52.38% |  | 6.4821 | 45.1391 | 6.2% | 28.94% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -317.25 | -16562.52
8840 | Inline Architecture | Start of month | 56556.55 | 35454.43 | 21102.12 | 37.31% | 35959.67 | 21861.72 | 20162.34 | 12155.27 | 8007.07 | 39.71% | 0% | 15797.33 | 9706.45 | 6090.88 | 38.56% | 316.34 | 204.75 | 111.59 | 35.28% | 0% | 66.3869 | 65.1099 | 38.34% | 36.42% | Hours calc for monthly claims | -204.75 | -204.75 | -12155.27
|  | Week 1 | 58902.56 | 0 | 58902.56 | 100% | 37601.88 | 34106.92 | 21415.85 | 18299.73 | 3116.12 | 14.55% |  | 16186.03 | 15807.19 | 378.84 | 2.341% | 324.19 | 342.25 | -18.06 | -5.571% |  | 3.9372 | 65.7043 | 3.8% | 36.16% | Materials calc for monthly claims | -12155.27
|  | Week 2 | 58902.56 | 0 | 58902.56 | 100% | 37601.88 | 38195.76 | 21415.85 | 19158.27 | 2257.58 | 10.54% |  | 16186.03 | 19037.49 | -2851.46 | -17.62% | 324.19 | 412.5 | -88.31 | -27.24% |  | -6.6456 | 65.7043 | -7.73% | 36.16%
|  | Week 3 | 58902.56 | 0 | 58902.56 | 100% | 37601.88 | 39781.27 | 21415.85 | 20554.53 | 861.32 | 4.022% |  | 16186.03 | 19226.74 | -3040.71 | -18.79% | 324.19 | 417 | -92.81 | -28.63% |  | -10.3761 | 65.7043 | -12.2% | 36.16% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -204.75 | -12155.27
8769 | Percival Bach | Start of month | 21404.82 | 0 | 21404.82 | 100% | 17424.66 | 0 | 13229.5 | [object Object] | 13229.5 | 100% | 0% | 4195.16 | 0 | 4195.16 | 100% | 84.03 | 0 | 84.03 | 100% | 0% |  | 47.3659 |  | 18.59% | Hours calc for monthly claims
|  | Week 1 | 21404.82 | 0 | 21404.82 | 100% | 17514.09 | 0 | 13318.88 | 0 | 13318.88 | 100% |  | 4195.21 | 0 | 4195.21 | 100% | 84.05 | 0 | 84.05 | 100% |  | 0 | 46.2906 | 0% | 18.18% | Materials calc for monthly claims
|  | Week 2 |  |  | 0
|  | Week 3 | 21404.82 | 0 | 21404.82 | 100% | 17514.09 | 0 | 13318.88 | 0 | 13318.88 | 100% |  | 4195.21 | 0 | 4195.21 | 100% | 84.05 | 0 | 84.05 | 100% |  | 0 | 46.2906 | 0% | 18.18% | Estimated months claim | 0
|  | Week 4 |  |  | 0
|  | Week 5 |  |  | 0
7901 | St Albans Street | Start of month | 96573.02 | 15366.74 | 81206.28 | 84.09% | 79663.84 | 12186.08 | 66021.95 | 12186.08 | 53835.87 | 81.54% |  | 13641.89 | 0 | 13641.89 | 100% | 273.37 | 0 | 273.37 | 100% |  |  | 61.8546 | 20.7% | 17.51% | Hours calc for monthly claims |  |  | -12186.08
|  | Week 1 | 99768.39 | 15366.74 | 84401.65 | 84.6% | 81719.58 | 15861.24 | 67238.96 | 13547.18 | 53691.78 | 79.85% |  | 14480.62 | 2314.06 | 12166.56 | 84.02% | 290.15 | 52.5 | 237.65 | 81.91% |  | -9.419 | 62.2051 | -3.22% | 18.09% | Materials calc for monthly claims | -12186.08
|  | Week 2 | 99768.39 | 15366.74 | 84401.65 | 84.6% | 81719.58 | 18551.86 | 67238.96 | 14369.1 | 52869.86 | 78.63% |  | 14480.62 | 4182.76 | 10297.86 | 71.11% | 290.15 | 91.75 | 198.4 | 68.38% |  | -34.7152 | 62.2051 | -20.73% | 18.09%
|  | Week 3 | 100987.51 | 15366.74 | 85620.77 | 84.78% | 82694.87 | 18551.86 | 68214.25 | 14369.1 | 53845.15 | 78.94% |  | 14480.62 | 4182.76 | 10297.86 | 71.11% | 290.15 | 91.75 | 198.4 | 68.38% |  | -34.7152 | 63.0455 | -20.73% | 18.11% | Estimated months claim | 0
|  | Week 4 |  |  | 0
|  | Week 5 |  |  | 0 | [24 empty] | -12186.08
8923 | 4 Perry St | Start of month | 31802.41 | 14370.83 | 17431.58 | 54.81% | 23448.14 | 11238.62 | 15632.03 | 11154.51 | 4477.52 | 28.64% |  | 7816.11 | 84.11 | 7732 | 98.92% | 157 | 2 | 155 | 98.73% | 0% | 1566.105 | 53.2119 | 21.8% | 26.27% | Hours calc for monthly claims | -2 | -2 | -11154.51
|  | Week 1 | [24 empty] | Materials calc for monthly claims | -11154.51
Week 2
|  | Week 3 | 31802.41 | 14370.83 | 17431.58 | 54.81% | 23448.14 | 11238.62 | 15632.03 | 11154.51 | 4477.52 | 28.64% |  | 7816.11 | 84.11 | 7732 | 98.92% | 156.69 | 2 | 154.69 | 98.72% |  | 1566.105 | 53.3172 | 21.8% | 26.27% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -2 | -11154.51
7864 | Ryans House | Start of month | 28626.25 | 27194.94 | 1431.31 | 5% | 21262.27 | 24965.42 | 11588.8 | 11702.32 | -113.52 | -0.9796% | 0% | 9673.47 | 13263.1 | -3589.63 | -37.11% | 193.82 | 266.75 | -72.93 | -37.63% |  | 8.3581 | 37.9939 | 8.198% | 25.72% | Hours calc for monthly claims | -266.75 | -266.75 | -11702.32
|  | Week 1 | 28626.25 | 27194.94 | 1431.31 | 5% | 21262.27 | 25301.59 | 11588.8 | 11737.47 | -148.67 | -1.283% |  | 9673.47 | 13564.12 | -3890.65 | -40.22% | 193.82 | 272.75 | -78.93 | -40.72% |  | 6.9417 | 37.9939 | 6.96% | 25.72% | Materials calc for monthly claims | -11702.32
|  | Week 2 | 30749.24 | 30749.24 | 0 | 0% | 22587.89 | 25550.31 | 12565.06 | 11750.84 | 814.22 | 6.48% |  | 10022.83 | 13799.47 | -3776.64 | -37.68% | 200.82 | 278.25 | -77.43 | -38.56% |  | 18.6844 | 40.6401 | 16.91% | 26.54%
|  | Week 3 | 30749.24 | 30749.24 | 0 | 0% | 22587.89 | 25625.28 | 12565.06 | 11825.81 | 739.25 | 5.883% |  | 10022.83 | 13799.47 | -3776.64 | -37.68% | 200.82 | 278.25 | -77.43 | -38.56% |  | 18.415 | 40.6401 | 16.66% | 26.54% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -266.75 | -11702.32
7912 | 71A Fendalton Road | Start of month | 268228.26 | 9034.53 | 259193.73 | 96.63% | 238611.58 | 6362.08 | 214154.25 | 3465.35 | 210688.9 | 98.38% |  | 24457.33 | 2896.73 | 21560.6 | 88.16% | 497.55 | 58.25 | 439.3 | 88.29% |  | 45.879 | 59.525 | 29.58% | 11.04% | Hours calc for monthly claims
|  | Week 1 | 268228.26 | 9034.53 | 259193.73 | 96.63% | 238611.58 | 6362.08 | 214154.25 | 3465.35 | 210688.9 | 98.38% |  | 24457.33 | 2896.73 | 21560.6 | 88.16% | 497.55 | 58.25 | 439.3 | 88.29% |  | 45.879 | 59.525 | 29.58% | 11.04% | Materials calc for monthly claims
Week 2
|  | Week 3 | 268228.26 | 9034.53 | 259193.73 | 96.63% | 238611.58 | 6362.08 | 214154.25 | 3465.35 | 210688.9 | 98.38% |  | 24457.33 | 2896.73 | 21560.6 | 88.16% | 497.55 | 58.25 | 439.3 | 88.29% |  | 45.879 | 59.525 | 29.58% | 11.04% | Estimated months claim | 0
Week 4
Week 5
8360 | Dixon House | Start of month | 32773.41 | 32773.41 | [object Object] | [object Object] | 22750.99 | 22238.62 | 12243.41 | 9324.41 | 2919 | 23.84% |  | 10507.58 | 12914.21 | -2406.63 | -22.9% | 210.6 | 260.75 | -50.15 | -23.81% |  | 40.4019 | 47.5898 | 32.14% | 30.58% | Hours calc for monthly claims | -260.75 | -260.75 | -9324.41
|  | Week 1 | 32773.41 | 32773.41 | 0 | 0% | 22750.99 | 22254.11 | 12243.41 | 9324.41 | 2919 | 23.84% |  | 10507.58 | 12929.7 | -2422.12 | -23.05% | 210.6 | 260.75 | -50.15 | -23.81% |  | 40.3425 | 47.5898 | 32.1% | 30.58% | Materials calc for monthly claims | -9324.41
Week 2
|  | Week 3 | 32773.41 | 32773.41 | 0 | 0% | 22750.99 | 22254.11 | 12243.41 | 9324.41 | 2919 | 23.84% |  | 10507.58 | 12929.7 | -2422.12 | -23.05% | 210.6 | 260.75 | -50.15 | -23.81% |  | 40.3425 | 47.5898 | 32.1% | 30.58% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -260.75 | -9324.41
8337 | Waimak Dairys | Start of month | 17899.33 | 0 | 17899.33 | 100% | 13919.4 | 7562.12 | 8410.93 | 5263.76 | 3147.17 | 37.42% |  | 5508.47 | 2298.36 | 3210.11 | 58.28% | 110.44 | 44.75 | 65.69 | 59.48% |  | -168.9859 | 36.037 |  | 22.24% | Hours calc for monthly claims | -44.75 | -44.75
|  | Week 1 | 17899.33 | 13424.5 | 4474.83 | 25% | 13919.4 | 10424.13 | 8410.93 | 7300.14 | 1110.79 | 13.21% |  | 5508.47 | 3123.99 | 2384.48 | 43.29% | 110.44 | 60.75 | 49.69 | 44.99% |  | 49.3888 | 36.037 | 22.35% | 22.24% | Materials calc for monthly claims
|  | Week 2 | [6 empty] | 0 | 0
|  | Week 3 | 17899.33 | 13424.5 | 4474.83 | 25% | 13919.4 | 10424.13 | 8410.93 | 7300.14 | 1110.79 | 13.21% |  | 5508.47 | 3123.99 | 2384.48 | 43.29% | 110.44 | 60.75 | 49.69 | 44.99% |  | 49.3888 | 36.037 | 22.35% | 22.24% | Estimated months claim | 0
|  | Week 4 | [6 empty] | 0 | 0
|  | Week 5 | [6 empty] | 0 | 0 | [18 empty] | -44.75
9240 | Daves Twizel Shack | Start of month | 10827.2 |  | 10827.2 | 100% | 7619.53 |  | 4388.87 | [object Object] | 4388.87 | 100% |  | 3230.66 |  | 3230.66 | 100% | 64.71 |  | 64.71 | 100% |  |  | 49.5699 |  | 29.63% | Hours calc for monthly claims
|  | Week 1 | [24 empty] | Materials calc for monthly claims
Week 2
|  | Week 3 | [24 empty] | Estimated months claim | 0
Week 4
Week 5
7428 | FAB Pegasus Lakeside | Start of month | 146237.11 | 94266.45 | 51970.66 | 35.54% | 114651.87 | 75526.07 | 82888.08 | 60408.1 | 22479.98 | 27.12% |  | 31763.79 | 15117.97 | 16645.82 | 52.41% | 659.73 | 304.75 | 354.98 | 53.81% |  | 61.4943 | 47.876 | 19.88% | 21.6% | Hours calc for monthly claims | -304.75 | -304.75
|  | Week 1 | 146237.11 | 94266.45 | 51970.66 | 35.54% | 114651.87 | 91824.39 | 82888.08 | 73131.34 | 9756.74 | 11.77% |  | 31763.79 | 18693.05 | 13070.74 | 41.15% | 659.73 | 378 | 281.73 | 42.7% |  | 6.4605 | 47.876 | 2.59% | 21.6% | Materials calc for monthly claims
|  | Week 2 | 146237.11 | 94266.45 | 51970.66 | 35.54% | 114651.87 | 95876.35 | 82888.08 | 74503.91 | 8384.17 | 10.12% |  | 31763.79 | 21372.44 | 10391.35 | 32.71% | 659.73 | 430 | 229.73 | 34.82% |  | -3.744 | 47.876 | -1.71% | 21.6%
|  | Week 3 | 146237.11 | 94266.45 | 51970.66 | 35.54% | 114651.87 | 95876.35 | 82888.08 | 74503.91 | 8384.17 | 10.12% |  | 31763.79 | 21372.44 | 10391.35 | 32.71% | 659.73 | 430 | 229.73 | 34.82% |  | -3.744 | 47.876 | -1.71% | 21.6% | Estimated months claim | 0
|  | Week 4 | [7 empty] | 0
|  | Week 5 | [7 empty] | 0 | [18 empty] | -304.75
0
9351 | Harewood Golf Club | Start of month | 16897.53 | 0 | 16897.53 | 100% | 9226.27 | 2946.15 | 2977.11 | 2298.71 | 678.4 | 22.79% |  | 6249.16 | 647.44 | 5601.72 | 89.64% | 125.17 | 11.25 | 113.92 | 91.01% |  | -261.88 | 61.2867 |  | 45.4% | Hours calc for monthly claims | -11.25 | -11.25 | -2298.71
|  | Week 1 | 16897.53 | 5491.7 | 11405.83 | 67.5% | 9226.27 | 3702.78 | 2977.11 | 2335.97 | 641.14 | 21.54% |  | 6249.16 | 1366.81 | 4882.35 | 78.13% | 125.17 | 23.75 | 101.42 | 81.03% |  | 75.3229 | 61.2867 | 32.57% | 45.4% | Materials calc for monthly claims | -2298.71
Week 2
|  | Week 3 | 16897.53 | 5491.7 | 11405.83 | 67.5% | 9226.27 | 3702.78 | 2977.11 | 2335.97 | 641.14 | 21.54% |  | 6249.16 | 1366.81 | 4882.35 | 78.13% | 125.17 | 23.75 | 101.42 | 81.03% |  | 75.3229 | 61.2867 | 32.57% | 45.4% | Estimated months claim | 0
Week 4
|  | Week 5 | [26 empty] | -11.25 | -2298.71
7429 | Taggart House | Start of month | 20992.12 | 1232.58 | 19759.54 | 94.13% | 16299.09 | 4905.28 | 9784.33 | 3461.15 | 6323.18 | 64.63% |  | 6514.76 | 1444.13 | 5070.63 | 77.83% | 130.62 | 32.25 | 98.37 | 75.31% |  | -113.8822 | 35.9289 | -298% | 22.36% | Hours calc for monthly claims | -32.25 | -32.25
|  | Week 1 | 20992.12 | 14169.68 | 6822.44 | 32.5% | 16299.09 | 9755.47 | 9784.33 | 8193.84 | 1590.49 | 16.26% |  | 6514.76 | 1561.63 | 4953.13 | 76.03% | 130.62 | 34.75 | 95.87 | 73.4% |  | 127.0276 | 35.9289 | 31.15% | 22.36% | Materials calc for monthly claims
|  | Week 2 | [7 empty] | 0
|  | Week 3 | 20992.12 | 14169.68 | 6822.44 | 32.5% | 16299.09 | 9755.47 | 9784.33 | 8193.84 | 1590.49 | 16.26% |  | 6514.76 | 1561.63 | 4953.13 | 76.03% | 130.62 | 34.75 | 95.87 | 73.4% |  | 127.0276 | 35.9289 | 31.15% | 22.36% | Estimated months claim | 0
|  | Week 4 | [7 empty] | 0
|  | Week 5 | [7 empty] | 0 | [18 empty] | -32.25
9508 | St Barnabas Church | Start of month | 23770.95 | 0 | 23770.95 | 100% | 14310.96 | 330.91 | 7389.34 | [object Object] | 7389.34 | 100% |  | 6921.62 | 330.91 | 6590.71 | 95.22% | 140.15 | 5.75 | 134.4 | 95.9% |  | -57.5496 | 67.499 |  | 39.8% | Hours calc for monthly claims
|  | Week 1 | 23770.95 | 0 | 23770.95 | 100% | 14310.96 | 7180.07 | 7389.34 | 6849.16 | 540.18 | 7.31% |  | 6921.62 | 330.91 | 6590.71 | 95.22% | 140.15 | 5.75 | 134.4 | 95.9% |  | -1248.7078 | 67.499 | 0% | 39.8% | Materials calc for monthly claims
|  | Week 2 | [7 empty] | 0
|  | Week 3 | 23770.95 | 0 | 23770.95 | 100% | 14310.96 | 7180.07 | 7389.34 | 6849.16 | 540.18 | 7.31% |  | 6921.62 | 330.91 | 6590.71 | 95.22% | 140.15 | 5.75 | 134.4 | 95.9% |  | -1248.7078 | 67.499 | 0% | 39.8% | Estimated months claim | 0
|  | Week 4 | [7 empty] | 0
|  | Week 5 | [7 empty] | 0
|  | Start of month | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | [7 empty] | Hours calc for monthly claims
|  | Week 1 | [6 empty] | 0 | 0 | [16 empty] | Materials calc for monthly claims
|  | Week 2 | [6 empty] | 0 | 0
|  | Week 3 | [6 empty] | 0 | 0 | [16 empty] | Estimated months claim | 0
|  | Week 4 | [6 empty] | 0 | 0
|  | Week 5 | [6 empty] | 0 | 0
| Contracting | Start of month | [6 empty] | 0 | 0 | [16 empty] | Hours calc for monthly claims
|  | Week 1 | [6 empty] | 0 | 0 | [16 empty] | Materials calc for monthly claims
|  | Week 2 | [6 empty] | 0 | 0
|  | Week 3 | [6 empty] | 0 | 0 | [16 empty] | Estimated months claim | 0
|  | Week 4 | [6 empty] | 0 | 0
|  | Week 5 | [6 empty] | 0 | 0
8946 | Westcoast Vaults | Start of month | 137109.56 | 0 | 137109.56 | 100% | 117394.57 | 0 | 99479.62 | [object Object] | 99479.62 | 100% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  |  | 54.9378 |  | 14.38% | Hours calc for monthly claims
|  | Week 1 | 137109.56 | 0 | 137109.56 | 100% | 117394.57 | 1749.8 | 99479.62 | 1749.8 | 97729.82 | 98.24% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  | 0 | 54.9378 | 0% | 14.38% | Materials calc for monthly claims
Week 2
|  | Week 3 | 137109.56 | 0 | 137109.56 | 100% | 117394.57 | 1749.8 | 99479.62 | 1749.8 | 97729.82 | 98.24% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  | 0 | 54.9378 | 0% | 14.38% | Estimated months claim | 0
Week 4
Week 5
8308 | Roydvale | Start of month | 389318.35 | 271388.15 | 117930.2 | 30.29% | 289549.48 | 224459.32 | 174279.98 | 176149.13 | -1869.15 | -1.072% |  | 115269.5 | 48310.19 | 66959.31 | 58.09% | 2312.68 | 1014.25 | 1298.43 | 56.14% |  | 46.2695 | 43.1399 | 17.29% | 25.63% | Hours calc for monthly claims | -1014.25 | -1014.25
|  | Week 1 | 389318.35 | 271388.15 | 117930.2 | 30.29% | 289549.48 | 228314.4 | 174279.98 | 175133.49 | -853.51 | -0.4897% |  | 115269.5 | 53180.91 | 62088.59 | 53.86% | 2312.68 | 1120.5 | 1192.18 | 51.55% |  | 38.4415 | 43.1399 | 15.87% | 25.63% | Materials calc for monthly claims
|  | Week 2 | [6 empty] | 0 | 0
|  | Week 3 | 389318.35 | 271388.15 | 117930.2 | 30.29% | 289549.48 | 227043.56 | 174279.98 | 173862.65 | 417.33 | 0.2395% |  | 115269.5 | 53180.91 | 62088.59 | 53.86% | 2312.68 | 1120.5 | 1192.18 | 51.55% |  | 39.5757 | 43.1399 | 16.34% | 25.63% | Estimated months claim | 0
|  | Week 4 | [6 empty] | 0 | 0
|  | Week 5 | [6 empty] | 0 | 0 | [18 empty] | -1014.25

## Claim Calculator By Month
Updated Job Spreadsheet
Job Number | Job Name | Claim | Costs | Profit | Retention | Margin | Quoted Margin | Hours to complete before E.O.M | Costs to come before E.O.M | Total cost to come before E.O.M | Estimated margin E.O.M | GP End of month | Hours this month | GP $ per hour this month
7658 | Charity Hospital | 0 | 51687.05 | -51687.05 | 0 | 0% | 21.49% | 50 | 5000 | 90 | 0% | -51777.05 | 20 | -2588.8525
8142 | Fisher Developements | 3912 | 5791.15 | -1879.15 | 0 | -48.04% | 23.92% | 16 | 272.6 | 912.6 | -71.36% | -2791.75 | -52.5 | 76.4863 | 14 Mirrors and 49 Downlights have been ordered
8824 | 3 Innovation Road | 0 | 0 | 0 |  | 0% | 28.85% | 16 |  | 640 | 0% | -640 | -34.75 | 34.1333
8127 | Rolly Autowash | 0 | 8827.49 | -8827.49 | 0 | 0% | 32.27% | 48 | 3000 | 4920 | 0% | -13747.49 | -388.25 | 40.4041
8183 | Murney Custodian - 1 Freight Drive | 0 | 1154.65 | -1154.65 |  | 0% | 17.63% | 16 | 2000 | 2640 | 0% | -3794.65 | 53 | -54.9949 | Couldnt get this rite because of ers but they re claiming 30%
8886 | Monkey Toe - Fisher fit out | 0 | 2297.52 | -2297.52 | 0 | 0% | 26.63% | 0 | 3000 | 3000 | 0% | -5297.52 | -112 | 47.2993
8887 | Tenancy 2 - Fisher Fit out | 0 | 5644.71 | -5644.71 |  | 0% | 22.64% | 0 | 3000 | 3000 | 0% | -8644.71 | -86.75 | 99.6508
8670 | Studio DB - tautara fit out | 0 | 11321.68 | -11321.68 | 0 | 0% | 29.65% | 80 | 5000 | 8200 | 0% | -19521.68 | -269 | 103.2893 | 48 Hours need to be made non Billable
8907 | 35 Mania | 0 | 1448.83 | -1448.83 |  | 0% | 22.33% |  |  | 0 | 0% | -1448.83 |  | 0
9065 | Cooltranz stage 4 | 0 | 4584.16 | -4584.16 | 0 | 0% | 25.25% |  |  | 0 | 0% | -4584.16 |  | 0
9259 | Andrew Reeve Stage 2 | 0 | 25724.04 | -25724.04 |  | 0% |  |  |  | 0 | 0% | -25724.04 |  | 0
8352 | 5 Sanscrit Place | 0 | -192.5 | 192.5 | 0 | 0% | 34.79% |  | 0 | 0 | 0% | 192.5 | -143.25 | -1.3438
8234 | Melhuish House | 0 | 4635.71 | -4635.71 | 0 | 0% | 27.18% |  |  | 0 | 0% | -4635.71 | -148.5 | 31.2169
8214 | 6 Tiroroa Lane | 0 | 0 | 0 | 0 | 0% | 25.8% |  |  | 0 | 0% | 0 | -5 | 0
6792 | Major Hornbrook | 0 | -1171.89 | 1171.89 | 0 | 0% | 28.32% | 64 | 0 | 2560 | 0% | -1388.11 | -317.25 | 5.4812
8840 | Inline Architecture | -35454.43 | 17919.55 | -53373.98 | 0 | 150.5% | 36.42% |  | 0 | 0 | 150.5% | -53373.98 | -204.75 | 260.6788
8769 | Percival Bach | 0 | 0 | 0 | 0 | 0% |  | 80 | 0 | 3200 | 0% | -3200 |  | -40
7901 | St Albans Street | 0 | 6365.78 | -6365.78 | 0 | 0% | 17.51% |  |  | 0 | 0% | -6365.78 |  | 0
8923 | 4 Perry St | 0 | 0 | 0 | 0 | 0% | 26.27% |  | 0 | 0 | 0% | 0 | -2 | 0
7864 | Ryans House | 3554.3 | 659.86 | 2894.44 |  | 81.43% | 25.72% | 0 |  | 0 | 81.43% | 2894.44 | -266.75 | -10.8508
7912 | 71A Fendalton Road | 0 | 0 | 0 |  | 0% |  |  |  | 0 | 0% | 0 |  | 0
8360 | Dixon House | 0 | 15.49 | -15.49 |  | 0% | 30.58% |  |  | 0 | 0% | -15.49 | -260.75 | 0.059406
8337 | Waimak Dairys | 13424.5 | 2862.01 | 10562.49 |  | 78.68% | 22.24% |  | 2530 | 2530 | 59.83% | 8032.49 | -44.75 | -179.497
9240 | Daves Twizel Shack | 0 | 0 | 0 |  | 0% |  | 0 |  | 0 | 0% | 0 |  | 0 | $18627.12 from Sharp Electrical
7428 | FAB Pegasus Lakeside | 0 | 20350.28 | -20350.28 |  | 0% | 21.6% | 32 | 0 | 1280 | 0% | -21630.28 | -304.75 | 79.3044
9351 | Harewood Golf Club | 5491.7 | 756.63 | 4735.07 |  | 86.22% | 45.4% | 16 | 0 | 640 | 74.57% | 4095.07 | -11.25 | 862.12
7429 | Taggart House | 12937.1 | 4850.19 | 8086.91 |  | 62.51% | 22.36% | 10 | 5000 | 5400 | 20.77% | 2686.91 | -32.25 | -120.76
9508 | St Barnabas Church | 0 | 6849.16 | -6849.16 |  | 0% |  |  |  | 0 | 0% | -6849.16 |  | 0
| Contracting | [6 empty] | 0
8946 | Westcoast Vaults | 0 | 1749.8 | -1749.8 |  | 0% | 14.38% |  | 1750 | 1750 | 0% | -3499.8 |  | 0
8308 | Roydvale | 0 | 2584.24 | -2584.24 |  | 0% | 25.63% | 80 | 0 | 3200 | 0% | -5784.24 | -1014.25 | 6.1913
Totals | Total | 3865.17 | 186715.59 | -182850.42 | GP% | -4731% | E.O.M GP% | -5868%
| Residential | -22865.6 | 32774.04 | -55639.64 |  | 243.3% | E.O.M GP% | 268.5%

## Upcoming Work Calculator
Updated Job Spreadsheet
| Job | Quoted Hours | Hours Used | Hours Remaining | January | February | March | April | May | June | July | August | September | October | November | December
Servicing | Servicing work any job under 30 hours |  |  |  | 500 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 500
7658 | Charity Hospital | 530.95 | 556.5 | -25.55 | [7 empty] | 80 |  |  |  |  | Programme Checked 24/03/26
8142 | Fisher Developements | 356.07 | 90.75 | 265.32 | [8 empty] | 80 |  |  |  | Cant find a Programme for this.
8824 | 3 Innovation Road | 125.39 | 34.75 | 90.64 | [8 empty] | 90 |  |  |  | Programme Checked 24/03/26
8127 | Rolly Autowash | 795.22 | 531.25 | 263.97 | [7 empty] | 200 | 80 |  |  |  | Programme Checked 24/03/26
8183 | Murney Custodian - 1 Freight Drive | 1120.27 | 416.25 | 704.02 | [7 empty] | 160 | 320 | 80 |  |  | Programme Checked 24/03/26
8886 | Monkey Toe - Fisher fit out | 501.83 | 127.75 | 374.08 | [6 empty] | 0 | 80 | 300 |  |  |  | Programme Checked 24/03/26
8887 | Tenancy 2 - Fisher Fit out | 223.22 | 104.25 | 118.97 | [7 empty] | 16 | 110
8670 | Studio DB - tautara fit out | 679.42 | 427 | 252.42 | [7 empty] | 240 | 160
8907 | 35 Mania | 63.5 | 48.25 | 15.25 | [7 empty] | 36
9065 | Cooltranz stage 4 | 160.82 | 2.75 | 158.07 | [7 empty] | 20 | 80 | 60
9259 | Andrew Reeve Stage 2 | 470.62 | 0 | 470.62 | [7 empty] | 188 | 282
8352 | 5 Sanscrit Place | 139.07 | 143.25 | -4.18 | [7 empty] | 48
8234 | Melhuish House | 231.75 | 207.25 | 24.5 | [7 empty] | 32
8214 | 6 Tiroroa Lane | 147.9 | 5 | 142.9 | [8 empty] | 48 | 16 | 64
6792 | Major Hornbrook | 208.2 | 317.25 | -109.05
8840 | Inline Architecture | 324.19 | 417 | -92.81 | [7 empty] | 130
8769 | Percival Bach | 84.05 | 0 | 84.05 | [7 empty] | 30 | 50
7901 | St Albans Street | 290.15 | 91.75 | 198.4 | [7 empty] | 80 | 40 | 160
8923 | 4 Perry St | 156.69 | 2 | 154.69 | 60 | 15 | 90
7864 | Ryans House | 200.82 | 278.25 | -77.43
7912 | 71A Fendalton Road | 497.55 | 58.25 | 439.3 | 80 | [7 empty] | 40 | 300 | 150 | 150
8360 | Dixon House | 210.6 | 260.75 | -50.15
8337 | Waimak Dairys | 110.44 | 60.75 | 49.69 | [7 empty] | 16 | 32
9240 | Daves Twizel Shack | 64.71 | 0 | 64.71 | [7 empty] | 16 | 40
7428 | FAB Pegasus Lakeside | 659.73 | 430 | 229.73 | [7 empty] | 80 | 80 | 180
9351 | Harewood Golf Club | 125.17 | 23.75 | 101.42 | [6 empty] | 16 | 32 | 65
7429 | Taggart House | 130.62 | 34.75 | 95.87 | [7 empty] | 16 | 70
9508 | St Barnabas Church | 140.15 | 5.75 | 134.4 | [9 empty] | 52 | 13 | 69
Contracting
8946 | Westcoast Vaults | 358.86 | 0 | 358.86 | [8 empty] | 143 |  | 215
8308 | Roydvale | 2312.68 | 1120.5 | 1192.18 | [7 empty] | 320 | 250 | 250 | 240 | 80
| Total Hours |  |  |  | 640 | 715 | 790 | 700 | 700 | 700 | 716 | 2520 | 3060 | 1316 | 914 | 650
| Residential Hours |  |  |  | 140 | 15 | 90 |  |  |  | 16 | 800 | 858 | 476 | 214 | 150
| Commercial Hours | 4490.26 | [9 empty] | 1020 | 1502 | 140
| Hours Available |  |  |  | 1488 | 2112 | 1984 | 1884.8 | 1948.8 | 2083.2 | 2604.8 | 2486.4 | 2604.8 | 2217.6 | 2112 | 1478.4
| Balance Hours |  |  |  | -848 | -1397 | -1194 | -1184.8 | -1248.8 | -1383.2 | -1888.8 | 33.6 | 455.2 | -901.6 | -1198 | -828.4
| Working Days In Month | Check Staff Numbers |  |  | 15 | 20 | 20 | 19 | 21 | 21 | 22 | 21 | 22 | 21 | 20 | 14
| No - Staff On Tools |  |  |  | 15.5 | 16.5 | 15.5 | 15.5 | 14.5 | 15.5 | 18.5 | 18.5 | 18.5 | 16.5 | 16.5 | 16.5
| Staff | [9 empty] | 2 x PPLguys here for July and August
| Turbo | 1
| Sean | 1
| Jacob | 1
| Hayden | 1
| Doug | 1
| Kyle | 0.5
| Jack | 1
| Andy | 1
| Ben Ruffles | 1
| Ben Dyer | 0
| Jake | 1
0
0
0
0
0
0
0
| Ethan | 1
| Rhod | 1
| George | 1
| Jasper | 1
| Logan | 1
| Quin | 1
| Regan | 1
| Total Staff (enter in above spreadsheet) | 16.5

## Note Cam (To Do)
Cams Notes
Koawa:
New job meeting set up for 8am wednesday - Tim, Dylan, VD, Cam - Perhaps bring in Jacob once back from leave??
Tray shop drawings into engineers - waiting on geoff to send back multidraw drawings.
DB dates for sites (livening 11 July)
Confirm Warrenties agreement
Go to tech submissions meeting on Wednesday 12th March
Start getting orders in, (so far PDL gear ordered through rads) need to look at lights beign ordered that we can - confirm process.
Tru Hire:
Temp should be on Monday morning 14.04.25
Craig would like an export/list for me please mate that captures all of the costs to date from you guys and ILS?
Riccarton High:
1x pits to repair
Follow up VO’s (Light pole to loop off date TBC,
Arrange PS3 & PS4 (PS3 filled in)
Start O&M manuals early - started; PS3 and board schedule in.
Check Strawberry sound hardware in swbd – report back to pete
From southbase deliverables register - Provide lifting handles for pits,
Missing 3x J lights (external wall lights)
EM's only have lights no drivers/batteries?
Strip light for under cabinets 2520mm
Spare light pole and head on site,was deleted from scope when landscaping changed
Gills:
Follow up sensor return/outcome (waiting to hear back)
Lunns:
Tidy up mains/ conduits coming out building
finish external lights (tuesday 15.04.25)
Unit 2 roller door no limits (V.O)
Rosiez unhappy with level of tidy up and removal of old cables, need to clarify what we actually scoped to what we did.
Kingsford Smith Drive
Main 100A unit 1 approved, ready for livening date. - Had a phone call from genesis regarding wheather this would need CT's?
Mains 2nd application is on hold until we get load breakdown for 160A - probably need to sort this asap.
Confirm start date with Wolfy, and order materials lifter
Te Aratai
Ellesmere College (Temp power)
Live
Cooltranz
Confirm correct data logger, depending on incoming size 1500A or 6kA then confirm price with cooltranz for hire rates etc.
Other:
Comes up with hours tracking solution

## Note Tom (To Do)
Tom's Notes:
Other:
Comes up with hours tracking solution

## Deliverables_RR_Test_Sheet (2)
Updated Job Spreadsheet
Job Number | Job Name | Week | Quoted Price | Claim to date | Remaining to claim | % Claim remaining | Total quoted cost | Total actual cost | Quoted material cost | Actual material cost | Material cost remaining | Material % remaining | Estimated % of materials recieved | Contractor Quoted Cost | Contractor Actual Cost | Contractor Balance | Quoted labour cost | Actual labour cost | Labour cost remaining | Labour cost % remaining | Quoted labour hours | Actual labour hours | Labour hours remaining | Labour hour % remaining | Estimated % of job complete | GP $ Per Hour | Quoted GP $ Per Hour | Margin to date | Quoted margin
[32 empty] | Hours calcs | Materials calcs
7658 | Charity Hospital | Start of month | 1914143.52 | 1667392.4 | 246751.12 | 12.89% | 1675577.99 | 1406264.78 | 1511021.45 | 1215391.45 | 295630 | 19.56% |  | 5 | 4 | 1 | 164551.54 | 190869.33 | -26317.79 | -15.99% | 3296.1 | 4599 | -1302.9 | -39.53% |  | 56.7801 | 72.3796 | 15.66% | 12.46% | Hours calc for monthly claims | -4599 | 415.49 | 48650.89
|  | Week 1 | 1922479.92 | 1667392.4 | 255087.52 | 13.27% | 1681960.61 | 1474477.14 | 1516687.43 | 1264042.34 | 252645.09 | 16.66% |  |  |  |  | 165273.18 | 210434.8 | -45161.62 | -27.33% | 3312.1 | 5014.49 | -1702.39 | -51.4% |  | 38.4716 | 72.6184 | 11.57% | 12.51% | Materials calc for monthly claims | -1215391.45 | 134.5 | 24752.67
|  | Week 2 | 1922479.92 | 1667392.4 | 255087.52 | 13.27% | 1681960.61 | 1505572.21 | 1516687.43 | 1288795.01 | 227892.42 | 15.03% | 90% |  |  |  | 165273.18 | 216777.2 | -51504.02 | -31.16% | 3312.1 | 5148.99 | -1836.89 | -55.46% | 90% | 31.4276 | 72.6184 | 9.705% | 12.51% |  |  | -5148.99 | -1288795.01
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -4599 | -1215391.45
8142 | Fisher Developements | Start of month | 381671.63 | 144223.4 | 237448.23 | 62.21% | 329257.09 | 168819.17 | 288248.16 | 158648.53 | 129599.63 | 44.96% |  |  |  |  | 41008.93 | 10170.64 | 30838.29 | 75.2% | 821.2 | 241 | 580.2 | 70.65% |  | -102.0571 | 63.8268 | -17.05% | 13.73% | Hours calc for monthly claims | -241 | 96.25 | 30474.42
|  | Week 1 | 382219.49 | 240065.55 | 142153.94 | 37.19% | 329585.81 | 202828.2 | 288352.94 | 189122.95 | 99229.99 | 34.41% |  |  |  |  | 41232.87 | 13705.25 | 27527.62 | 66.76% | 825.68 | 337.25 | 488.43 | 59.15% |  | 110.4147 | 63.7459 | 15.51% | 13.77% | Materials calc for monthly claims | -158648.53 | 101.75 | 7119.32
|  | Week 2 | 382219.49 | 240065.55 | 142153.94 | 37.19% | 329585.81 | 213730.54 | 288352.94 | 196242.27 | 92110.67 | 31.94% |  |  |  |  | 41232.87 | 17488.27 | 23744.6 | 57.59% | 825.68 | 439 | 386.68 | 46.83% |  | 59.9886 | 63.7459 | 10.97% | 13.77% |  |  | -439 | 23228
|  | Week 3 | 383409.63 | 240065.55 | 143344.08 | 37.39% | 330537 | 246817.11 | 289155.03 | 219470.27 | 69684.76 | 24.1% | 75% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 8.579% | 13.79% | Estimated months claim | 0 | 0 | -219470.27
|  | Week 4 | 383409.63 |  | 383409.63 | 100% |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% |  |  | 0 | 0
|  | Week 5 | 383409.63 |  | 383409.63 | 100% |  |  | 0 | 0 | 0 | #DIV/0! | 55% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 35% | #DIV/0! | #REF! | #DIV/0! | #REF! |  |  | -241 | -158648.53
7104 | 3 Innovation Road | Start of month | 449818.08 | 246538.95 | 203279.13 | 45.19% | 329858.1 | 251921.97 | 255282.19 | 219103.38 | 36178.81 | 14.17% | 0% |  |  |  | 74575.91 | 32818.59 | 41757.32 | 55.99% | 1493.36 | 799.5 | 693.86 | 46.46% | 0% | -6.733 | 80.3289 | -2.183% | 26.67% | Hours calc for monthly claims | -799.5 | 57.75 | -918.26
|  | Week 1 | 449818.08 | 364039.73 | 85778.35 | 19.07% | 329858.1 | 253347.64 | 255282.19 | 218185.12 | 37097.07 | 14.53% |  |  |  |  | 74575.91 | 35162.52 | 39413.39 | 52.85% | 1493.36 | 857.25 | 636.11 | 42.6% | 10% | 129.1246 | 80.3289 | 30.41% | 26.67% | Materials calc for monthly claims | -219103.38 | 93.75 | 5813.69
|  | Week 2 | 449818.08 | 364039.73 | 85778.35 | 19.07% | 329858.1 | 262942.02 | 255282.19 | 223998.81 | 31283.38 | 12.25% |  |  |  |  | 74575.91 | 38943.21 | 35632.7 | 47.78% | 1493.36 | 951 | 542.36 | 36.32% | 15% | 106.3067 | 80.3289 | 27.77% | 26.67% |  |  | -951 | -223998.81
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 3% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 3% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 90% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 65% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -799.5 | -219103.38
8127 | Rolly Autowash | Start of month | 38856.96 | 0 | 38856.96 | 100% | 27050.88 | 1129.12 | 16492.08 | 1129.12 | 15362.96 | 93.15% | 0% |  |  |  | 10558.8 | 0 | 10558.8 | 100% | 213 | 0 | 213 | 100% | 0% | #DIV/0! | 55.4276 | #DIV/0! | 30.38% | Hours calc for monthly claims | 0 | 9.25 | 5779.58
|  | Week 1 | 38856.96 | 0 | 38856.96 | 100% | 27050.88 | 7293.59 | 16492.08 | 6908.7 | 9583.38 | 58.11% | 0% |  |  |  | 10558.8 | 384.89 | 10173.91 | 96.35% | 213.13 | 9.25 | 203.88 | 95.66% | 0% | -788.4962 | 55.3938 | #DIV/0! | 30.38% | Materials calc for monthly claims | -1129.12 | 101.75 | 6796.13
|  | Week 2 | 38856.96 | 0 | 38856.96 | 100% | 27050.88 | 18431.21 | 16492.08 | 13704.83 | 2787.25 | 16.9% | 0% |  |  |  | 10558.8 | 4726.38 | 5832.42 | 55.24% | 213.13 | 111 | 102.13 | 47.92% | 0% | -166.0469 | 55.3938 | #DIV/0! | 30.38% |  |  | -111 | -13704.83
|  | Week 3 |  | 0 | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  | 0 | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  | 0 | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | -1129.12
8183 | Murney - 1 Freight Drive + 109 Iport | Start of month | 69191.71 | 0 | 69191.71 | 100% | 53243.87 | 641.28 | 41588.94 | 171.84 | 41417.1 | 99.59% |  |  |  |  | 11654.93 | 469.44 | 11185.49 | 95.97% | 233.59 | 12.5 | 221.09 | 94.65% | 0% | -51.3024 | 68.2728 | #DIV/0! | 23.05% | Hours calc for monthly claims | -12.5 | 4.5 | 13.95
|  | Week 1 | 69191.71 | 1364.78 | 67826.93 | 98.03% | 53243.87 | 844.77 | 41588.94 | 185.79 | 41403.15 | 99.55% |  |  |  |  | 11654.93 | 658.98 | 10995.95 | 94.35% | 233.59 | 17 | 216.59 | 92.72% |  | 30.5888 | 68.2728 | 38.1% | 23.05% | Materials calc for monthly claims | -171.84 | 3 | 3907.37
|  | Week 2 | 69191.71 | 1364.78 | 67826.93 | 98.03% | 53243.87 | 4850.24 | 41588.94 | 4093.16 | 37495.78 | 90.16% |  |  |  |  | 11654.93 | 757.08 | 10897.85 | 93.5% | 233.59 | 20 | 213.59 | 91.44% |  | -174.273 | 68.2728 | -255.4% | 23.05% |  |  | -20 | -4093.16
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -12.5 | -171.84
8886 | Monkey Toe - Fisher fit out | Start of month | 44956.29 |  | 44956.29 | 100% | 30585.67 | 0 | 19268.79 | 0 | 19268.79 | 100% |  |  |  |  | 11316.88 |  | 11316.88 | 100% | 234.28 | 0 | 234.28 | 100% | 80% | #DIV/0! | 61.3395 | #DIV/0! | 31.97% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 44956.29 |  | 44956.29 | 100% | 30585.67 |  | 19268.79 | 0 | 19268.79 | 100% |  |  |  |  | 11316.88 |  | 11316.88 | 100% | 234.28 | 0 | 234.28 | 100% | 95% | #DIV/0! | 61.3395 | #DIV/0! | 31.97% | Materials calc for monthly claims | 0 | 2.5 | 0
|  | Week 2 | 44956.29 |  | 44956.29 | 100% | 30585.67 | 112.35 | 19268.79 | 0 | 19268.79 | 100% |  |  |  |  | 11316.88 | 112.35 | 11204.53 | 99.01% | 234.28 | 2.5 | 231.78 | 98.93% | 98% | -44.94 | 61.3395 | #DIV/0! | 31.97% |  |  | -2.5 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  | 0 | 0 | 0% | 100% | #DIV/0! | 0 | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 100% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 100% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
8887 | Tenancy 2 - Fisher Fit out | Start of month | 7495.54 | 0 | 7495.54 | 100% | 5659.85 | 0 | 3768.03 | 0 | 3768.03 | 100% | 0% |  |  |  | 1891.82 | 0 | 1891.82 | 100% | 37.84 | 0 | 37.84 | 100% | 0% | #DIV/0! | 48.5119 | #DIV/0! | 24.49% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 7495.54 | 0 | 7495.54 | 100% | 5659.85 | 0 | 3768.03 | 0 | 3768.03 | 100% | 0% |  |  |  | 1891.82 | 0 | 1891.82 | 100% | 37.84 | 0 | 37.84 | 100% | 0% | #DIV/0! | 48.5119 | #DIV/0! | 24.49% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 7495.54 | 0 | 7495.54 | 100% | 5659.85 | 0 | 3768.03 | 0 | 3768.03 | 100% | 0% |  |  |  | 1891.82 | 0 | 1891.82 | 100% | 37.84 | 0 | 37.84 | 100% | 0% | #DIV/0! | 48.5119 | #DIV/0! | 24.49% |  |  | 0 | 0
|  | Week 3 |  | 0 | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  | 0 | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  | 0 | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
8670 | Studio DB - tautara fit out | Start of month | 100348.26 | 91153 | 9195.26 | 9.163% | 79103.46 | 64224.89 | 62144.61 | 54357.06 | 7787.55 | 12.53% | 0% |  |  |  | 16958.85 | 9867.83 | 7091.02 | 41.81% | 340.12 | 262 | 78.12 | 22.97% | 0% | 102.779 | 62.4627 | 29.54% | 21.17% | Hours calc for monthly claims | -262 | 10 | 1582.92
|  | Week 1 | 100348.26 | 91153 | 9195.26 | 9.163% | 79103.46 | 66212.81 | 62144.61 | 55939.98 | 6204.63 | 9.984% |  |  |  |  | 16958.85 | 10272.83 | 6686.02 | 39.42% | 340.12 | 272 | 68.12 | 20.03% |  | 91.6919 | 62.4627 | 27.36% | 21.17% | Materials calc for monthly claims | -54357.06 | 44.25 | 218.2
|  | Week 2 | 100348.26 | 91153 | 9195.26 | 9.163% | 79103.46 | 68039.14 | 62144.61 | 56158.18 | 5986.43 | 9.633% |  |  |  |  | 16958.85 | 11880.96 | 5077.89 | 29.94% | 340.12 | 316.25 | 23.87 | 7.018% |  | 73.0873 | 62.4627 | 25.36% | 21.17% |  |  | -316.25 | -56158.18
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 90% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 90% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -262 | -54357.06
8907 | 35 Mania | Start of month | 98524.85 | 42682.56 | 55842.29 | 56.68% | 82927.42 | 59094.67 | 64755.29 | 50345.39 | 14409.9 | 22.25% |  |  |  |  | 18172.13 | 8749.28 | 9422.85 | 51.85% | 363.99 | 218.25 | 145.74 | 40.04% | 0% | -75.1987 | 42.8513 | -38.45% | 15.83% | Hours calc for monthly claims | -218.25 | 163.25 | 7441.38
|  | Week 1 | 98524.85 | 93329.71 | 5195.14 | 5.273% | 82927.42 | 73161.13 | 64755.29 | 57786.77 | 6968.52 | 10.76% |  |  |  |  | 18172.13 | 15374.36 | 2797.77 | 15.4% | 363.99 | 381.5 | -17.51 | -4.811% | 20% | 52.8665 | 42.8513 | 21.61% | 15.83% | Materials calc for monthly claims | -50345.39 | 2 | 728.1
|  | Week 2 | 98524.85 | 93329.71 | 5195.14 | 5.273% | 82927.42 | 73980.77 | 64755.29 | 58514.87 | 6240.42 | 9.637% |  |  |  |  | 18172.13 | 15465.9 | 2706.23 | 14.89% | 363.99 | 383.5 | -19.51 | -5.36% | 25% | 50.4536 | 42.8513 | 20.73% | 15.83% |  |  | -383.5 | -58514.87
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 5% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 2% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 25% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 10% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 95% | [5 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 10% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -218.25 | -50345.39
9065 | Cooltranz stage 4 | Start of month | 87970.61 | 48945.78 | 39024.83 | 44.36% | 68471.73 | 49900.98 | 52300.56 | 37733.03 | 14567.53 | 27.85% |  |  |  |  | 16171.17 | 12167.95 | 4003.22 | 24.76% | 323.99 | 350 | -26.01 | -8.028% |  | -2.7291 | 60.1836 | -1.952% | 22.17% | Hours calc for monthly claims | -350 | -39.5 | 321.16
|  | Week 1 | 87970.61 | 85555.47 | 2415.14 | 2.745% | 68471.73 | 50194.4 | 52300.56 | 38054.19 | 14246.37 | 27.24% |  |  |  |  | 16171.17 | 12140.21 | 4030.96 | 24.93% | 323.99 | 310.5 | 13.49 | 4.164% | 30% | 113.8843 | 60.1836 | 41.33% | 22.17% | Materials calc for monthly claims | -37733.03 | -310.5 | -38054.19
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 30% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 10% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 10% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -350 | -37733.03
9259 | Andrew Reeve Stage 2 | Start of month | 210242.4 | 14860.85 | 195381.55 | 92.93% | 188013.59 | 33639.16 | 167291.62 | 33639.16 | 133652.46 | 79.89% | 0% |  |  |  | 20721.97 | 0 | 20721.97 | 100% | 416.73 | 0 | 416.73 | 100% | 0% | #DIV/0! | 53.341 | -126.4% | 10.57% | Hours calc for monthly claims | 0 | 0 | 16474.45
|  | Week 1 | 210242.4 | 67511.23 | 142731.17 | 67.89% | 188013.59 | 50113.61 | 167291.62 | 50113.61 | 117178.01 | 70.04% | 0% |  |  |  | 20721.97 |  | 20721.97 | 100% | 416.73 | 0 | 416.73 | 100% | 0% | #DIV/0! | 53.341 | 25.77% | 10.57% | Materials calc for monthly claims | -33639.16 | 0 | 1067.7
|  | Week 2 | 210242.4 | 67511.23 | 142731.17 | 67.89% | 188013.59 | 51181.31 | 167216.61 | 51181.31 | 116035.3 | 69.39% | 0% |  |  |  | 20796.98 |  | 20796.98 | 100% | 416.73 | 0 | 416.73 | 100% | 0% | #DIV/0! | 53.341 | 24.19% | 10.57% |  |  | 0 | -51181.31
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% | [5 empty] | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  |  | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | -33639.16
8352 | 5 Sanscrit Place | Start of month | 43448.62 | 19551.87 | 23896.75 | 55% | 31063.54 | 25863.55 | 16447.56 | 18255.63 | -1808.07 | -10.99% | 0% |  |  |  | 14615.98 | 7607.92 | 7008.06 | 47.95% | 292.93 | 181.5 | 111.43 | 38.04% | 0% | -34.7751 | 42.28 | -32.28% | 28.51% | Hours calc for monthly claims | -181.5 | 0 | 979.13
|  | Week 1 | 43448.62 | 34758.89 | 8689.73 | 20% | 31063.54 | 26842.68 | 16447.56 | 19234.76 | -2787.2 | -16.95% | 0% |  |  |  | 14615.98 | 7607.92 | 7008.06 | 47.95% | 292.93 | 181.5 | 111.43 | 38.04% | 0% | 43.6155 | 42.28 | 22.77% | 28.51% | Materials calc for monthly claims | -18255.63 | -181.5 | -19234.76
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -181.5 | -18255.63
8234 | Melhuish House | Start of month | 49964.93 | 25359.22 | 24605.71 | 49.25% | 43768.91 | 25556.81 | 37199.62 | 20554.23 | 16645.39 | 44.75% | 0% |  |  |  | 6569.29 | 5002.58 | 1566.71 | 23.85% | 131.78 | 113.75 | 18.03 | 13.68% | 0% | -1.7371 | 47.0179 | -0.7792% | 12.4% | Hours calc for monthly claims | -113.75 | 58 | 7824.22
|  | Week 1 | 49964.93 | 45361.39 | 4603.54 | 9.214% | 43768.91 | 35776.29 | 37199.62 | 28378.45 | 8821.17 | 23.71% |  |  |  |  | 6569.29 | 7397.84 | -828.55 | -12.61% | 131.78 | 171.75 | -39.97 | -30.33% |  | 55.8084 | 47.0179 | 21.13% | 12.4% | Materials calc for monthly claims | -20554.23 | -171.75 | -28378.45
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -113.75 | -20554.23
8214 | 6 Tiroroa Lane | Start of month | 109103.76 | 51323.57 | 57780.19 | 52.96% | 81158.83 | 40300.16 | 52391.31 | 27621.5 | 24769.81 | 47.28% | 20% |  |  |  | 28767.52 | 12678.66 | 16088.86 | 55.93% | 577.33 | 295.5 | 281.83 | 48.82% | 0% | 37.3043 | 48.4037 | 21.48% | 25.61% | Hours calc for monthly claims | -295.5 | 19.25 | 1.96
|  | Week 1 | 109103.76 | 77821.91 | 31281.85 | 28.67% | 81158.83 | 41214.74 | 52391.31 | 27623.46 | 24767.85 | 47.27% | 20% |  |  |  | 28767.52 | 13591.28 | 15176.24 | 52.75% | 577.33 | 314.75 | 262.58 | 45.48% | 0% | 116.3055 | 48.4037 | 47.04% | 25.61% | Materials calc for monthly claims | -27621.5 | -314.75 | -27623.46
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 20% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 20% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 25% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -295.5 | -27621.5
6792 | Major Hornbrook | Start of month | 27742.44 | 0 | 27742.44 | 100% | 20094.24 | 405.4 | 11429.46 | 73.74 | 11355.72 | 99.35% | 0% |  |  |  | 8664.78 | 331.66 | 8333.12 | 96.17% | 173.8 | 7.75 | 166.05 | 95.54% |  | -52.3097 | 44.0058 | #DIV/0! | 27.57% | Hours calc for monthly claims | -7.75 | 0 | -13.89
|  | Week 1 | 27861.41 | 0 | 27861.41 | 100% | 20162.08 | 392.27 | 11464.04 | 59.85 | 11404.19 | 99.48% | 0% |  |  |  | 8698.04 | 332.42 | 8365.62 | 96.18% | 174.46 | 7.75 | 166.71 | 95.56% |  | -50.6155 | 44.1324 | #DIV/0! | 27.63% | Materials calc for monthly claims | -73.74 | -7.75 | -59.85
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -7.75 | -73.74
8840 | Inline Architecture | Start of month | 21300.45 | 5515.31 | 15785.14 | 74.11% | 11275.69 | 5128.09 | 4165.39 | 815.93 | 3349.46 | 80.41% | 100% |  |  |  | 7110.3 | 1880.39 | 5229.91 | 73.55% | 142.36 | 42.25 | 100.11 | 70.32% | 100% | 66.7217 | 70.4184 | 51.11% | 47.06% | Hours calc for monthly claims | -42.25 | 14.25 | 2844.83
|  | Week 1 | 21300.45 | 10143.09 | 11157.36 | 52.38% | 11275.69 | 6237.89 | 4165.39 | 3660.76 | 504.63 | 12.11% | 100% |  |  |  | 7110.3 | 2577.13 | 4533.17 | 63.75% | 142.36 | 56.5 | 85.86 | 60.31% | 100% | 69.1186 | 70.4184 | 38.5% | 47.06% | Materials calc for monthly claims | -815.93 | -56.5 | -3660.76
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 100% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 100% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -42.25 | -815.93
8769 | Percival Bach | Start of month | 63405.46 | 0 | 63405.46 | 100% | 43553.81 | 9012.69 | 29573.66 | 8270.88 | 21302.78 | 72.03% | 0% |  |  |  | 13980.15 | 741.81 | 13238.34 | 94.69% | 279.87 | 52 | 227.87 | 81.42% | 0% | -173.321 | 70.9317 | #DIV/0! | 31.31% | Hours calc for monthly claims | -52 | 36.5 | 3381.04
|  | Week 1 | 63405.46 | 23507.97 | 39897.49 | 62.92% | 43553.81 | 15599.26 | 29573.66 | 11651.92 | 17921.74 | 60.6% | 0% |  |  |  | 13980.15 | 3947.34 | 10032.81 | 71.76% | 279.87 | 88.5 | 191.37 | 68.38% | 0% | 89.364 | 70.9317 | 33.64% | 31.31% | Materials calc for monthly claims | -8270.88 | -88.5 | -11651.92
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -52 | -8270.88
7901 | St Albans Street | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
8923 | 4 Perry St | Start of month | 47191.69 | 32679.16 | 14512.53 | 30.75% | 30406.12 | 21779.51 | 15384 | 8004.44 | 7379.56 | 47.97% | 0% |  |  |  | 15022.12 | 13775.07 | 1247.05 | 8.301% | 301.53 | 180.75 | 120.78 | 40.06% | 0% | 60.3024 | 55.668 | 33.35% | 35.57% | Hours calc for monthly claims | -180.75 | 4.5 | 5821.52
|  | Week 1 | 47191.69 | 35940.5 | 11251.19 | 23.84% | 30406.12 | 22080.06 | 15505.37 | 13825.96 | 1679.41 | 10.83% | 0% |  |  |  | 14900.75 | 8254.1 | 6646.65 | 44.61% | 301.53 | 185.25 | 116.28 | 38.56% | 0% | 74.8202 | 55.668 | 38.56% | 35.57% | Materials calc for monthly claims | -8004.44 | -185.25 | -13825.96
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -180.75 | -8004.44
7864 | Ryans House | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 0 | 0 | 0 | #DIV/0! | 473 | 0 | 473 | 100% | 0% | #DIV/0! | 0 | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
7912 | 71A Fendalton Road | Start of month | 23650.59 | 0 | 23650.59 | 100% | 15376.98 | 1628.64 | 8582.1 | 53.06 | 8529.04 | 99.38% |  |  |  |  | 6794.88 | 1575.58 | 5219.3 | 76.81% | 135.9 | 30.5 | 105.4 | 77.56% |  | -53.398 | 60.8801 | #DIV/0! | 34.98% | Hours calc for monthly claims | 73.75 | 32.25 | 377.73
|  | Week 1 | 23650.59 | 5602.1 | 18048.49 | 76.31% | 15376.98 | 3604.74 | 8582.1 | 430.79 | 8151.31 | 94.98% |  |  |  |  | 6794.88 | 3173.95 | 3620.93 | 53.29% | 135.9 | 62.75 | 73.15 | 53.83% |  | 31.8304 | 60.8801 | 35.65% | 34.98% | Materials calc for monthly claims | 3637.44 | 32 | 1239.42
|  | Week 2 | 23650.59 | 5602.1 | 18048.49 | 76.31% | 15376.98 | 6523.55 | 8582.1 | 1670.21 | 6911.89 | 80.54% |  |  |  |  | 6794.88 | 4853.34 | 1941.54 | 28.57% | 135.9 | 94.75 | 41.15 | 30.28% |  | -9.7251 | 60.8801 | -16.45% | 34.98% |  |  | 0.5 | 2020.29
|  | Week 3 | 23650.59 | 5602.1 | 18048.49 | 76.31% | 15376.98 | 8543.84 | 8582.1 | 3690.5 | 4891.6 | 57% |  |  |  |  | 6794.88 | 4853.34 | 1941.54 | 28.57% | 135.9 | 95.25 | 40.65 | 29.91% |  | -30.8844 | 60.8801 | -52.51% | 34.98% | Estimated months claim | 0 | 9 | 0
|  | Week 4 | 23650.59 | 5602.1 | 18048.49 | 76.31% | 15376.98 | 9041.54 | 8582.1 | 3690.5 | 4891.6 | 57% |  |  |  |  | 6794.88 | 5351.04 | 1443.84 | 21.25% | 135.9 | 104.25 | 31.65 | 23.29% |  | -32.9922 | 60.8801 | -61.4% | 34.98% |  |  | 0 | 0
|  | Week 5 | 23650.59 | 5602.1 | 18048.49 | 76.31% | 15376.98 | 9041.54 | 8582.1 | 3690.5 | 4891.6 | 57% |  |  |  |  | 6794.88 | 5351.04 | 1443.84 | 21.25% | 135.9 | 104.25 | 31.65 | 23.29% |  | -32.9922 | 60.8801 | -61.4% | 34.98% |  |  | 73.75 | 3637.44
8360 | Dixon House | Start of month | 29188.19 | 38245.41 | -9057.22 | -31.03% | 17590 | 36039.07 | 9253.76 | 35607.58 | -26353.82 | -284.8% |  |  |  |  | 8336.24 | 431.49 | 7904.75 | 94.82% | 166.98 | 9.75 | 157.23 | 94.16% |  | 226.2913 | 69.4586 | 5.769% | 39.74% | Hours calc for monthly claims | -9.75 | 0 | 0
|  | Week 1 | 29188.19 | 38245.41 | -9057.22 | -31.03% | 17590 | 36039.07 | 9253.76 | 35607.58 | -26353.82 | -284.8% |  |  |  |  | 8336.24 | 431.49 | 7904.75 | 94.82% | 166.98 | 9.75 | 157.23 | 94.16% |  | 226.2913 | 69.4586 | 5.769% | 39.74% | Materials calc for monthly claims | -35607.58 | 4.5 | -197.56
|  | Week 2 | 29188.19 | 38245.41 | -9057.22 | -31.03% | 17590 | 36039.07 | 9253.76 | 35410.02 | -26156.26 | -282.7% |  |  |  |  | 8336.24 | 629.05 | 7707.19 | 92.45% | 166.98 | 14.25 | 152.73 | 91.47% |  | 154.8309 | 69.4586 | 5.769% | 39.74% |  |  | 7.25 | 646.81
|  | Week 3 | 29188.19 | 38245.41 | -9057.22 | -31.03% | 17590 | 37012.71 | 9253.76 | 36056.83 | -26803.07 | -289.6% |  |  |  |  | 8336.24 | 955.88 | 7380.36 | 88.53% | 166.98 | 21.5 | 145.48 | 87.12% |  | 57.3349 | 69.4586 | 3.223% | 39.74% | Estimated months claim | 0 | -21.5 | -36056.83
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -9.75 | -35607.58
8337 | Waimak Dairys | Start of month | 15025.89 | 0 | 15025.89 | 100% | 10929.18 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 5126.09 | 0 | 5126.09 | 100% | 102.81 | 0 | 102.81 | 100% |  | #DIV/0! | 96.2922 | #DIV/0! | 27.26% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
9240 | Daves Twizel Shack | Start of month | 300839.52 | 0 | 300839.52 | 100% | 243747.98 | 70092.2 | 183229.46 | 69898.65 | 113330.81 | 61.85% |  |  |  |  | 60518.52 | 193.55 | 60324.97 | 99.68% | 1213 | 0 | 1213 | 100% |  | #DIV/0! | 47.0664 | #DIV/0! | 18.98% | Hours calc for monthly claims | 0 | 3.5 | -10.8
|  | Week 1 | 300839.52 | 93431.66 | 207407.86 | 68.94% | 243747.98 | 70081.4 | 183229.46 | 69887.85 | 113341.61 | 61.86% |  |  |  |  | 60518.52 | 193.55 | 60324.97 | 99.68% | 1213.28 | 3.5 | 1209.78 | 99.71% |  | 6671.5029 | 47.0555 | 24.99% | 18.98% | Materials calc for monthly claims | -69898.65 | -3.5 | -69887.85
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | -69898.65
7428 | FAB Pegasus Lakeside | Start of month | 58426.32 | 0 | 58426.32 | 100% | 44815.36 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 19242.55 | 0 | 19242.55 | 100% | 385.7 | 0 | 385.7 | 100% |  | #DIV/0! | 101.5913 | #DIV/0! | 23.3% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 58426.32 | 0 | 0 | 0% | 44815.36 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 19242.55 | 0 | 19242.55 | 100% | 385.7 | 0 | 385.7 | 100% |  | #DIV/0! | 101.5913 | #DIV/0! | 23.3% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
9351 | Harewood Golf Club | Start of month | 18080.64 | 0 | 18080.64 | 100% | 13540.24 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 5455.24 | 0 | 5455.24 | 100% | 109.34 | 0 | 109.34 | 100% |  | #DIV/0! | 115.4692 | #DIV/0! | 25.11% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 18080.64 | 0 | 0 | 0% | 13540.24 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 5455.24 | 0 | 5455.24 | 100% | 109.34 | 0 | 109.34 | 100% |  | #DIV/0! | 115.4692 | #DIV/0! | 25.11% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
7429 | Taggart House | Start of month | 17608.26 | 0 | 17608.26 | 100% | 14076.97 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 5790.51 | 0 | 5790.51 | 100% | 116.13 | 0 | 116.13 | 100% |  | #DIV/0! | 101.7631 | #DIV/0! | 20.05% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 17608.26 | 0 | 0 | 0% | 14076.97 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 5790.51 | 0 | 5790.51 | 100% | 116.13 | 0 | 116.13 | 100% |  | #DIV/0! | 101.7631 | #DIV/0! | 20.05% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
9508 | St Barnabas Church | Start of month | 19572.81 | 0 | 19572.81 | 100% | 11314.42 | 0 | 0 | 0 | 0 | #DIV/0! | 0% |  |  |  | 5290.42 | 0 | 5290.42 | 100% | 105 | 0 | 105 | 100% | 0% | #DIV/0! | 136.0228 | #DIV/0! | 42.19% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
0 | 0 | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 346 | 0 | 346 | 100% |  | #DIV/0! | 0 | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
0 | Contracting | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
8946 | Westcoast Vaults | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
8308 | Roydvale | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! | [6 empty] | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0

## Sheet1
340 | Allowed | Actual | % of job
Box out | 30 |  | 8.824%
pre-wire | 60 |  |  | 95.35
cut out | 100 |  |  | 102.69
fit off lights | 150 |  |  | 134.82
324.19
415