## Sheet1
Updated Job Spreadsheet
Job Number | Job Name | Week | Quoted Price | Claim to date | Remaining to claim | % Claim remaining | Total quoted cost | Total actual cost | Quoted material cost | Actual material cost | Material cost remaining | Material % remaining | Estimated % of materials recieved | Quoted labour cost | Actual labour cost | Labour cost remaining | Labour cost % remaining | Quoted labour hours | Actual labour hours | Labour hours remaining | Labour hour % remaining | Estimated % of job complete | GP $ Per Hour | Quoted GP $ Per Hour | Margin to date | Quoted margin
[29 empty] | Hours calcs | Materials calcs
7658 | Charity Hospital | Start of month | 151187.84 | 84036.95 | 67150.89 | 44.42% | 123244.87 | 83080.14 | 99869.39 | 71217.91 | 28651.48 | 28.69% | 20% | 23375.48 | 11862.23 | 11513.25 | 49.25% | 473 | 247.75 | 225.25 | 47.62% |  | 3.862 | 59.076 | 1.139% | 18.48% | Hours calc for monthly claims | 170.25 | 55 | 4159.19
|  | Week 1 | 151187.84 | 84036.95 | 67150.89 | 44.42% | 123244.87 | 90009.08 | 99869.39 | 75377.1 | 24492.29 | 24.52% | 20% | 23375.48 | 14631.98 | 8743.5 | 37.4% | 473 | 302.75 | 170.25 | 35.99% |  | -19.7263 | 59.076 | -7.107% | 18.48% | Materials calc for monthly claims | 21734.65 | 0 | 0
|  | Week 2 | 151187.84 | 84036.95 | 67150.89 | 44.42% | 123244.87 | 90009.08 | 99869.39 | 75377.1 | 24492.29 | 24.52% | 80% | 23375.48 | 14631.98 | 8743.5 | 37.4% | 473 | 302.75 | 170.25 | 35.99% |  | -19.7263 | 59.076 | -7.107% | 18.48% |  |  | 0 | 0
|  | Week 3 | 151187.84 | 84036.95 | 67150.89 | 44.42% | 123244.87 | 90009.08 | 99869.39 | 75377.1 | 24492.29 | 24.52% | 80% | 23375.48 | 14631.98 | 8743.5 | 37.4% | 473 | 302.75 | 170.25 | 35.99% |  | -19.7263 | 59.076 | -7.107% | 18.48% | Estimated months claim | 0 | 52.75 | 9611.12
|  | Week 4 | 211177.4 | 205915.9 | 5261.5 | 2.492% | 179035.16 | 102494.5 | 153862.87 | 84988.22 | 68874.65 | 44.76% | 80% | 25172.29 | 17506.28 | 7666.01 | 30.45% | 509 | 355.5 | 153.5 | 30.16% |  | 290.9181 | 63.1478 | 50.23% | 15.22% |  |  | 62.5 | 7964.34
|  | Week 5 | 215046.91 | 205915.9 | 9131.01 | 4.246% | 181293.63 | 113522.99 | 155024.75 | 92952.56 | 62072.19 | 40.04% | 90% | 26268.88 | 20570.43 | 5698.45 | 21.69% | 530.95 | 418 | 112.95 | 21.27% |  | 221.0357 | 63.5715 | 44.87% | 15.7% |  |  | 170.25 | 21734.65
8142 | Fisher Developements | Start of month | 95023.47 | 51156.11 | 43867.36 | 46.16% | 72292.47 | 46015.25 | 56719.74 | 43985.17 | 12734.57 | 22.45% | 50% | 15572.73 | 2030.08 | 13542.65 | 86.96% | 311.89 | 45.5 | 266.39 | 85.41% | 10% | 112.9859 | 72.8815 | 10.05% | 23.92% | Hours calc for monthly claims | 7 | 7 | -178.96
|  | Week 1 | 95023.47 | 51156.11 | 43867.36 | 46.16% | 72292.47 | 46401.16 | 56719.74 | 43806.21 | 12913.53 | 22.77% | 50% | 15572.73 | 2594.95 | 12977.78 | 83.34% | 311.89 | 52.5 | 259.39 | 83.17% |  | 90.5705 | 72.8815 | 9.295% | 23.92% | Materials calc for monthly claims | 1716.69 | 0 | 0
|  | Week 2 | 95023.47 | 51156.11 | 43867.36 | 46.16% | 72292.47 | 46401.16 | 56719.74 | 43806.21 | 12913.53 | 22.77% |  | 15572.73 | 2594.95 | 12977.78 | 83.34% | 311.89 | 52.5 | 259.39 | 83.17% |  | 90.5705 | 72.8815 | 9.295% | 23.92% |  |  | 0 | 0
|  | Week 3 | 95023.47 | 51156.11 | 43867.36 | 46.16% | 72292.47 | 46401.16 | 56719.74 | 43806.21 | 12913.53 | 22.77% |  | 15572.73 | 2594.95 | 12977.78 | 83.34% | 311.89 | 52.5 | 259.39 | 83.17% |  | 90.5705 | 72.8815 | 9.295% | 23.92% | Estimated months claim | 0 | 0 | 1880.95
|  | Week 4 | 95023.47 | 51156.11 | 43867.36 | 46.16% | 72292.47 | 48282.11 | 56719.74 | 45687.16 | 11032.58 | 19.45% |  | 15572.73 | 2594.95 | 12977.78 | 83.34% | 311.89 | 52.5 | 259.39 | 83.17% |  | 54.7429 | 72.8815 | 5.618% | 23.92% |  |  | 0 | 14.7
|  | Week 5 | 95023.47 | 51156.11 | 43867.36 | 46.16% | 72292.47 | 48296.81 | 56719.74 | 45701.86 | 11017.88 | 19.43% |  | 15572.73 | 2594.95 | 12977.78 | 83.34% | 311.89 | 52.5 | 259.39 | 83.17% | 30% | 54.4629 | 72.8815 | 5.589% | 23.92% |  |  | 7 | 1716.69
8824 | 3 Innovation Road | Start of month | 27500.32 | 0 | 27500.32 | 100% | 19565.83 | 4619.18 | 13767.34 | 3061.24 | 10706.1 | 77.76% |  | 5798.49 | 1557.94 | 4240.55 | 73.13% | 125.39 | 31.75 | 93.64 | 74.68% | 25% | -145.486 | 63.2785 | #DIV/0! | 28.85% | Hours calc for monthly claims | 3 | 0 | 0
|  | Week 1 | 27500.32 |  | 27500.32 | 100% | 19565.83 | 4619.18 | 13767.34 | 3061.24 | 10706.1 | 77.76% |  | 5798.49 | 1557.94 | 4240.55 | 73.13% | 125.39 | 31.75 | 93.64 | 74.68% | 25% | -145.486 | 63.2785 | #DIV/0! | 28.85% | Materials calc for monthly claims | 2850 | 3 | -4.5475e-13
|  | Week 2 | 27500.32 |  | 27500.32 | 100% | 19565.83 | 4771.92 | 13767.34 | 3061.24 | 10706.1 | 77.76% |  | 5798.49 | 1710.68 | 4087.81 | 70.5% | 125.39 | 34.75 | 90.64 | 72.29% |  | -137.3214 | 63.2785 | #DIV/0! | 28.85% |  |  | 0 | 0
|  | Week 3 | 27500.32 |  | 27500.32 | 100% | 19565.83 | 4771.92 | 13767.34 | 3061.24 | 10706.1 | 77.76% |  | 5798.49 | 1710.68 | 4087.81 | 70.5% | 125.39 | 34.75 | 90.64 | 72.29% |  | -137.3214 | 63.2785 | #DIV/0! | 28.85% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 27500.32 |  | 27500.32 | 100% | 19565.83 | 4771.92 | 13767.34 | 3061.24 | 10706.1 | 77.76% |  | 5798.49 | 1710.68 | 4087.81 | 70.5% | 125.39 | 34.75 | 90.64 | 72.29% |  | -137.3214 | 63.2785 | #DIV/0! | 28.85% |  |  | 0 | 2850
|  | Week 5 | 27500.32 | 6999.08 | 20501.24 | 74.55% | 19565.83 | 7621.92 | 13767.34 | 5911.24 | 7856.1 | 57.06% |  | 5798.49 | 1710.68 | 4087.81 | 70.5% | 125.39 | 34.75 | 90.64 | 72.29% | 25% | -17.9235 | 63.2785 | -8.899% | 28.85% |  |  | 3 | 2850
8127 | Rolly Autowash | Start of month | 150850.82 | 58752.41 | 92098.41 | 61.05% | 102178.42 | 53395.44 | 63160.67 | 46046.12 | 17114.55 | 27.1% | 0% | 39017.75 | 7349.32 | 31668.43 | 81.16% | 795.22 | 160.75 | 634.47 | 79.79% | 5% | 33.3249 | 61.2062 | 9.118% | 32.27% | Hours calc for monthly claims | 227.5 | 0 | 15900.86
|  | Week 1 | 150850.82 | 58752.41 | 92098.41 | 61.05% | 102178.42 | 75741.83 | 62464.86 | 61946.98 | 517.88 | 0.8291% | 0% | 39713.56 | 13794.85 | 25918.71 | 65.26% | 795.22 | 160.75 | 634.47 | 79.79% |  | -105.6885 | 61.2062 | -28.92% | 32.27% | Materials calc for monthly claims | 10918.69 | 0 | 0
|  | Week 2 | 150850.82 | 58752.41 | 92098.41 | 61.05% | 102178.42 | 75741.83 | 62464.86 | 61946.98 | 517.88 | 0.8291% | 0% | 39713.56 | 13794.85 | 25918.71 | 65.26% | 795.22 | 160.75 | 634.47 | 79.79% |  | -105.6885 | 61.2062 | -28.92% | 32.27% |  |  | 0 | 0
|  | Week 3 | 150850.82 | 58752.41 | 92098.41 | 61.05% | 102178.42 | 75741.83 | 62464.86 | 61946.98 | 517.88 | 0.8291% | 0% | 39713.56 | 13794.85 | 25918.71 | 65.26% | 795.22 | 160.75 | 634.47 | 79.79% |  | -105.6885 | 61.2062 | -28.92% | 32.27% | Estimated months claim | 0 | 182.25 | 957.45
|  | Week 4 | 150850.82 | 58752.41 | 92098.41 | 61.05% | 102178.42 | 79494.07 | 62464.86 | 62904.43 | -439.57 | -0.7037% | 0% | 39713.56 | 16589.64 | 23123.92 | 58.23% | 795.22 | 343 | 452.22 | 56.87% |  | -60.4713 | 61.2062 | -35.3% | 32.27% |  |  | 45.25 | -5939.62
|  | Week 5 | 150850.82 | 111983.72 | 38867.1 | 25.77% | 102178.42 | 75718.13 | 62464.86 | 56964.81 | 5500.05 | 8.805% | 90% | 39713.56 | 18753.32 | 20960.24 | 52.78% | 795.22 | 388.25 | 406.97 | 51.18% | 60% | 93.4078 | 61.2062 | 32.38% | 32.27% |  |  | 227.5 | 10918.69
8183 | Murney - 1 Freight Drive + 109 Iport | Start of month | 387361.22 | 129848.32 | 257512.9 | 66.48% | 319185.51 | 115165.8 | 263544.78 | 106200.69 | 157344.09 | 59.7% | 25% | 55640.73 | 8965.11 | 46675.62 | 83.89% | 1114.27 | 223.25 | 891.02 | 79.96% | 15% | 65.7672 | 61.1842 | 11.31% | 17.6% | Hours calc for monthly claims | 164.25 | 117.5 | 6796.8
|  | Week 1 | 387361.22 | 129848.32 | 257512.9 | 66.48% | 319185.51 | 127651.08 | 263544.78 | 112997.49 | 150547.29 | 57.12% | 25% | 55640.73 | 14653.59 | 40987.14 | 73.66% | 1114.27 | 340.75 | 773.52 | 69.42% |  | 6.4482 | 61.1842 | 1.692% | 17.6% | Materials calc for monthly claims | 26116.02 | 0 | 0
|  | Week 2 | 387361.22 | 129848.32 | 257512.9 | 66.48% | 319185.51 | 127651.08 | 263544.78 | 112997.49 | 150547.29 | 57.12% |  | 55640.73 | 14653.59 | 40987.14 | 73.66% | 1114.27 | 340.75 | 773.52 | 69.42% |  | 6.4482 | 61.1842 | 1.692% | 17.6% |  |  | 0 | 0
|  | Week 3 | 387361.22 | 129848.32 | 257512.9 | 66.48% | 319185.51 | 127651.08 | 263544.78 | 112997.49 | 150547.29 | 57.12% |  | 55640.73 | 14653.59 | 40987.14 | 73.66% | 1114.27 | 340.75 | 773.52 | 69.42% |  | 6.4482 | 61.1842 | 1.692% | 17.6% | Estimated months claim | 0 | 34.75 | -1881.67
|  | Week 4 | 389022.03 | 129848.32 | 259173.71 | 66.62% | 320431.12 | 127233.96 | 264519.78 | 111115.82 | 153403.96 | 57.99% |  | 55911.34 | 16118.14 | 39793.2 | 71.17% | 1120.27 | 375.5 | 744.77 | 66.48% |  | 6.9623 | 61.2271 | 2.013% | 17.63% |  |  | 12 | 21200.89
|  | Week 5 | 389022.03 | 176161.65 | 212860.38 | 54.72% | 320431.12 | 148939.51 | 264519.78 | 132316.71 | 132203.07 | 49.98% |  | 55911.34 | 16622.8 | 39288.54 | 70.27% | 1120.27 | 387.5 | 732.77 | 65.41% | 40% | 70.2507 | 61.2271 | 15.45% | 17.63% |  |  | 164.25 | 26116.02
8886 | Monkey Toe - Fisher fit out | Start of month | 128258.5 | 25608.7 | 102649.8 | 80.03% | 94098.32 | 21372.82 | 69042.09 | 20997.98 | 48044.11 | 69.59% | 0% | 25056.23 | 374.84 | 24681.39 | 98.5% | 501.83 | 8 | 493.83 | 98.41% | 1% | 529.485 | 68.0712 | 16.54% | 26.63% | Hours calc for monthly claims | 104 | 60.75 | 537.26
|  | Week 1 | 128258.5 | 25608.7 | 102649.8 | 80.03% | 94098.32 | 24859.04 | 69042.09 | 21535.24 | 47506.85 | 68.81% |  | 25056.23 | 3323.8 | 21732.43 | 86.73% | 501.83 | 68.75 | 433.08 | 86.3% | 30% | 10.9041 | 68.0712 | 2.927% | 26.63% | Materials calc for monthly claims | 5849.48 | 0 | 0
|  | Week 2 | 128258.5 | 25608.7 | 102649.8 | 80.03% | 94098.32 | 24859.04 | 69042.09 | 21535.24 | 47506.85 | 68.81% |  | 25056.23 | 3323.8 | 21732.43 | 86.73% | 501.83 | 68.75 | 433.08 | 86.3% |  | 10.9041 | 68.0712 | 2.927% | 26.63% |  |  | 0 | 0
|  | Week 3 | 128258.5 | 25608.7 | 102649.8 | 80.03% | 94098.32 | 24859.04 | 69042.09 | 21535.24 | 47506.85 | 68.81% |  | 25056.23 | 3323.8 | 21732.43 | 86.73% | 501.83 | 68.75 | 433.08 | 86.3% |  | 10.9041 | 68.0712 | 2.927% | 26.63% | Estimated months claim | 0 | 19.5 | -3.638e-12
|  | Week 4 | 128258.5 | 25608.7 | 102649.8 | 80.03% | 94098.32 | 25952.6 | 69042.09 | 21535.24 | 47506.85 | 68.81% |  | 25056.23 | 4417.36 | 20638.87 | 82.37% | 501.83 | 88.25 | 413.58 | 82.41% |  | -3.8969 | 68.0712 | -1.343% | 26.63% |  |  | 23.75 | 5312.22
|  | Week 5 | 128258.5 | 36398.39 | 91860.11 | 71.62% | 94098.32 | 32521.46 | 69042.09 | 26847.46 | 42194.63 | 61.11% |  | 25056.23 | 5674 | 19382.23 | 77.35% | 501 | 112 | 389 | 77.64% | 40% | 34.6154 | 68.184 | 10.65% | 26.63% |  |  | 104 | 5849.48
8887 | Tenancy 2 - Fisher Fit out | Start of month | 64305.21 | 14477.41 | 49827.8 | 77.49% | 49749.48 | 13531.4 | 39151.4 | 13232.43 | 25918.97 | 66.2% | 0% | 10598.08 | 298.97 | 10299.11 | 97.18% | 212.3 | 6.5 | 205.8 | 96.94% | 1% | 145.54 | 68.5621 | 6.534% | 22.64% | Hours calc for monthly claims | 80.25 | 15.75 | 1065.19
|  | Week 1 | 64305.21 | 14477.41 | 49827.8 | 77.49% | 49749.48 | 15402 | 39151.4 | 14297.62 | 24853.78 | 63.48% | 0% | 10598.08 | 1104.38 | 9493.7 | 89.58% | 212.3 | 22.25 | 190.05 | 89.52% | 20% | -41.5546 | 68.5621 | -6.386% | 22.64% | Materials calc for monthly claims | 2406.62 | 0 | 0
|  | Week 2 | 64305.21 | 14477.41 | 49827.8 | 77.49% | 49749.48 | 15402 | 39151.4 | 14297.62 | 24853.78 | 63.48% | 0% | 10598.08 | 1104.38 | 9493.7 | 89.58% | 212.3 | 22.25 | 190.05 | 89.52% |  | -41.5546 | 68.5621 | -6.386% | 22.64% |  |  | 0 | 0
|  | Week 3 | 64305.21 | 14477.41 | 49827.8 | 77.49% | 49749.48 | 15402 | 39151.4 | 14297.62 | 24853.78 | 63.48% | 0% | 10598.08 | 1104.38 | 9493.7 | 89.58% | 212.3 | 22.25 | 190.05 | 89.52% |  | -41.5546 | 68.5621 | -6.386% | 22.64% | Estimated months claim | 0 | 64.75 | 159.67
|  | Week 4 | 64305.21 | 14477.41 | 49827.8 | 77.49% | 49749.48 | 16010.31 | 39151.4 | 14457.29 | 24694.11 | 63.07% | 0% | 10598.08 | 1553.02 | 9045.06 | 85.35% | 212.3 | 87 | 125.3 | 59.02% |  | -17.6195 | 68.5621 | -10.59% | 22.64% |  |  | -0.25 | 1181.76
|  | Week 5 | 64305.21 | 25322.07 | 38983.14 | 60.62% | 49749.48 | 19566.87 | 39151.4 | 15639.05 | 23512.35 | 60.05% | 0% | 10598.08 | 3927.82 | 6670.26 | 62.94% | 212.3 | 86.75 | 125.55 | 59.14% | 40% | 66.3424 | 68.5621 | 22.73% | 22.64% |  |  | 80.25 | 2406.62
8670 | Studio DB - tautara fit out | Start of month | 146005.55 | 61401.4 | 84604.15 | 57.95% | 103345.75 | 52398.84 | 71390.14 | 50454.38 | 20935.76 | 29.33% |  | 31955.61 | 1944.46 | 30011.15 | 93.92% | 639.95 | 38 | 601.95 | 94.06% | 0% | 236.9095 | 66.6611 | 14.66% | 29.22% | Hours calc for monthly claims | 231 | 132.5 | 8559.08
|  | Week 1 | 146005.55 | 61401.4 | 84604.15 | 57.95% | 103345.75 | 67982.01 | 71390.14 | 59013.46 | 12376.68 | 17.34% |  | 31955.61 | 8968.55 | 22987.06 | 71.93% | 639.95 | 170.5 | 469.45 | 73.36% | 25% | -38.596 | 66.6611 | -10.72% | 29.22% | Materials calc for monthly claims | 15945.5 | 0 | 0
|  | Week 2 | 146005.55 | 61401.4 | 84604.15 | 57.95% | 103345.75 | 67982.01 | 71390.14 | 59013.46 | 12376.68 | 17.34% |  | 31955.61 | 8968.55 | 22987.06 | 71.93% | 639.95 | 170.5 | 469.45 | 73.36% |  | -38.596 | 66.6611 | -10.72% | 29.22% |  |  | 0 | 0
|  | Week 3 | 146005.55 | 61401.4 | 84604.15 | 57.95% | 103345.75 | 67982.01 | 71390.14 | 59013.46 | 12376.68 | 17.34% |  | 31955.61 | 8968.55 | 22987.06 | 71.93% | 639.95 | 170.5 | 469.45 | 73.36% |  | -38.596 | 66.6611 | -10.72% | 29.22% | Estimated months claim | 0 | 72.25 | 4493.62
|  | Week 4 | 150152.16 | 61401.4 | 88750.76 | 59.11% | 105626.39 | 75607.83 | 72224.17 | 63507.08 | 8717.09 | 12.07% |  | 33402.22 | 12100.75 | 21301.47 | 63.77% | 668.92 | 242.75 | 426.17 | 63.71% |  | -58.5229 | 66.5637 | -23.14% | 29.65% |  |  | 26.25 | 2892.8
|  | Week 5 | 150152.16 | 98562.5 | 51589.66 | 34.36% | 105626.39 | 79936.19 | 72224.17 | 66399.88 | 5824.29 | 8.064% |  | 33402.22 | 13536.31 | 19865.91 | 59.47% | 668.92 | 269 | 399.92 | 59.79% | 30% | 69.2428 | 66.5637 | 18.9% | 29.65% |  |  | 231 | 15945.5
8907 | 35 Mania | Start of month | 20420.56 |  | 20420.56 | 100% | 15859.68 | 0 | 12689.1 | 0 | 12689.1 | 100% |  | 3170.58 | 0 | 3170.58 | 100% | 63.5 | 0 | 63.5 | 100% |  | #DIV/0! | 71.8249 | #DIV/0! | 22.33% | Hours calc for monthly claims | 26.75 | 26.75 | 1454.98
|  | Week 1 | 20420.56 |  | 20420.56 | 100% | 15859.68 | 2489.01 | 12689.1 | 1454.98 | 11234.12 | 88.53% |  | 3170.58 | 1034.03 | 2136.55 | 67.39% | 63.5 | 26.75 | 36.75 | 57.87% | 38% | -93.0471 | 71.8249 | #DIV/0! | 22.33% | Materials calc for monthly claims | 11159.14 | 0 | 0
|  | Week 2 | 20420.56 |  | 20420.56 | 100% | 15859.68 | 2489.01 | 12689.1 | 1454.98 | 11234.12 | 88.53% |  | 3170.58 | 1034.03 | 2136.55 | 67.39% | 63.5 | 26.75 | 36.75 | 57.87% |  | -93.0471 | 71.8249 | #DIV/0! | 22.33% |  |  | 0 | 0
|  | Week 3 | 20420.56 |  | 20420.56 | 100% | 15859.68 | 2489.01 | 12689.1 | 1454.98 | 11234.12 | 88.53% |  | 3170.58 | 1034.03 | 2136.55 | 67.39% | 63.5 | 26.75 | 36.75 | 57.87% |  | -93.0471 | 71.8249 | #DIV/0! | 22.33% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 20420.56 |  | 20420.56 | 100% | 15859.68 | 2489.01 | 12689.1 | 1454.98 | 11234.12 | 88.53% |  | 3170.58 | 1034.03 | 2136.55 | 67.39% | 63.5 | 26.75 | 36.75 | 57.87% |  | -93.0471 | 71.8249 | #DIV/0! | 22.33% |  |  | 0 | 9704.16
|  | Week 5 | 20420.56 | 16358.37 | 4062.19 | 19.89% | 15859.68 | 12193.17 | 12689.1 | 11159.14 | 1529.96 | 12.06% |  | 3170.58 | 1034.03 | 2136.55 | 67.39% | 63.5 | 26.75 | 36.75 | 57.87% | 40% | 155.7084 | 71.8249 | 25.46% | 22.33% |  |  | 26.75 | 11159.14
9065 | Cooltranz stage 4 | Start of month | 46303.5 | 6131.46 | 40172.04 | 86.76% | 34612.41 | 5397.27 | 26584.53 | 5397.27 | 21187.26 | 79.7% |  | 8027.88 | 0 | 8027.88 | 100% | 160.82 | 0 | 160.82 | 100% |  | #DIV/0! | 72.6967 | 11.97% | 25.25% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 46303.5 | 6131.46 | 40172.04 | 86.76% | 34612.41 | 5397.27 | 26584.53 | 5397.27 | 21187.26 | 79.7% |  | 8027.88 | 0 | 8027.88 | 100% | 160.82 | 0 | 160.82 | 100% |  | #DIV/0! | 72.6967 | 11.97% | 25.25% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 46303.5 | 6131.46 | 40172.04 | 86.76% | 34612.41 | 5397.27 | 26584.53 | 5397.27 | 21187.26 | 79.7% |  | 8027.88 | 0 | 8027.88 | 100% | 160.82 | 0 | 160.82 | 100% |  | #DIV/0! | 72.6967 | 11.97% | 25.25% |  |  | 0 | 0
|  | Week 3 | 46303.5 | 6131.46 | 40172.04 | 86.76% | 34612.41 | 5397.27 | 26584.53 | 5397.27 | 21187.26 | 79.7% |  | 8027.88 | 0 | 8027.88 | 100% | 160.82 | 0 | 160.82 | 100% |  | #DIV/0! | 72.6967 | 11.97% | 25.25% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 46303.5 | 6131.46 | 40172.04 | 86.76% | 34612.41 | 5397.27 | 26584.53 | 5397.27 | 21187.26 | 79.7% |  | 8027.88 | 0 | 8027.88 | 100% | 160.82 | 0 | 160.82 | 100% |  | #DIV/0! | 72.6967 | 11.97% | 25.25% |  |  | 0 | 0
|  | Week 5 | 46303.5 | 6131.46 | 40172.04 | 86.76% | 34612.41 | 5397.27 | 26584.53 | 5397.27 | 21187.26 | 79.7% |  | 8027.88 | 0 | 8027.88 | 100% | 160.82 | 0 | 160.82 | 100% |  | #DIV/0! | 72.6967 | 11.97% | 25.25% |  |  | 0 | 0
9259 | Andrew Reeve Stage 2 | Start of month |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! | 470.3 |  | 470.3 | 100% | 0% | #DIV/0! | 0 | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
8352 | 5 Sanscrit Place | Start of month | 25467.84 | 13740.86 | 11726.98 | 46.05% | 16606.83 | 11056.14 | 9659.99 | 6525.89 | 3134.1 | 32.44% | 0% | 6946.84 | 4530.25 | 2416.59 | 34.79% | 139.07 | 89 | 50.07 | 36% | 0% | 30.1654 | 63.7162 | 19.54% | 34.79% | Hours calc for monthly claims | 54.25 | 22.5 | 113.97
|  | Week 1 | 25467.84 | 19598.41 | 5869.43 | 23.05% | 16606.83 | 12315.59 | 9659.99 | 6639.86 | 3020.13 | 31.26% | 0% | 6946.84 | 5675.73 | 1271.11 | 18.3% | 139.07 | 111.5 | 27.57 | 19.82% | 0% | 65.3168 | 63.7162 | 37.16% | 34.79% | Materials calc for monthly claims | -956.41 | 23.5 | -1113.13
|  | Week 2 | 25467.84 | 19598.41 | 5869.43 | 23.05% | 16606.83 | 12459.77 | 9659.99 | 5526.73 | 4133.26 | 42.79% | 0% | 6946.84 | 6933.04 | 13.8 | 0.1987% | 139.07 | 135 | 4.07 | 2.927% | 0% | 52.8788 | 63.7162 | 36.42% | 34.79% |  |  | 0 | 0
|  | Week 3 | 25467.84 | 19598.41 | 5869.43 | 23.05% | 16606.83 | 12459.77 | 9659.99 | 5526.73 | 4133.26 | 42.79% | 0% | 6946.84 | 6933.04 | 13.8 | 0.1987% | 139.07 | 135 | 4.07 | 2.927% | 0% | 52.8788 | 63.7162 | 36.42% | 34.79% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 25467.84 | 19598.41 | 5869.43 | 23.05% | 16606.83 | 12459.77 | 9659.99 | 5526.73 | 4133.26 | 42.79% | 0% | 6946.84 | 6933.04 | 13.8 | 0.1987% | 139.07 | 135 | 4.07 | 2.927% |  | 52.8788 | 63.7162 | 36.42% | 34.79% |  |  | 8.25 | 42.75
|  | Week 5 | 25467.84 | 19598.41 | 5869.43 | 23.05% | 16606.83 | 12921.64 | 9659.99 | 5569.48 | 4090.51 | 42.34% | 0% | 6946.84 | 7352.16 | -405.32 | -5.835% | 139.07 | 143.25 | -4.18 | -3.006% |  | 46.6092 | 63.7162 | 34.07% | 34.79% |  |  | 54.25 | -956.41
8234 | Melhuish House | Start of month | 37083.03 | 19660.4 | 17422.63 | 46.98% | 27002.93 | 14076.05 | 15440.32 | 10218.13 | 5222.19 | 33.82% | 0% | 11562.61 | 3857.92 | 7704.69 | 66.63% | 231.75 | 78.5 | 153.25 | 66.13% | 0% | 71.1382 | 43.4956 | 28.4% | 27.18% | Hours calc for monthly claims | 70 | 32.25 | 1005.75
|  | Week 1 | 37083.03 | 26341.73 | 10741.3 | 28.97% | 27002.93 | 16757.06 | 15440.32 | 11223.88 | 4216.44 | 27.31% | 0% | 11562.61 | 5533.18 | 6029.43 | 52.15% | 231.75 | 110.75 | 121 | 52.21% |  | 86.5433 | 43.4956 | 36.39% | 27.18% | Materials calc for monthly claims | 3925.06 | 29.75 | 2919.31
|  | Week 2 | 37083.03 | 26341.73 | 10741.3 | 28.97% | 27002.93 | 21120.62 | 15440.32 | 14143.19 | 1297.13 | 8.401% | 0% | 11562.61 | 6977.43 | 4585.18 | 39.66% | 231.75 | 140.5 | 91.25 | 39.37% |  | 37.1609 | 43.4956 | 19.82% | 27.18% |  |  | 0 | 0
|  | Week 3 | 37083.03 | 26341.73 | 10741.3 | 28.97% | 27002.93 | 21120.62 | 15440.32 | 14143.19 | 1297.13 | 8.401% | 0% | 11562.61 | 6977.43 | 4585.18 | 39.66% | 231.75 | 140.5 | 91.25 | 39.37% |  | 37.1609 | 43.4956 | 19.82% | 27.18% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 37083.03 | 26341.73 | 10741.3 | 28.97% | 27002.93 | 21120.62 | 15440.32 | 14143.19 | 1297.13 | 8.401% | 0% | 11562.61 | 6977.43 | 4585.18 | 39.66% | 231.75 | 140.5 | 91.25 | 39.37% |  | 37.1609 | 43.4956 | 19.82% | 27.18% |  |  | 8 | 0
|  | Week 5 | 37083.03 | 33023.07 | 4059.96 | 10.95% | 27002.93 | 21520.62 | 15440.32 | 14143.19 | 1297.13 | 8.401% | 0% | 11562.61 | 7377.43 | 4185.18 | 36.2% | 231.75 | 148.5 | 83.25 | 35.92% |  | 77.4576 | 43.4956 | 34.83% | 27.18% |  |  | 70 | 3925.06
8214 | 6 Tiroroa Lane | Start of month | 26186.14 | 5762.27 | 20423.87 | 77.99% | 19428.98 | 7925.81 | 12051.35 | 7679.91 | 4371.44 | 36.27% | 0% | 7377.63 | 245.9 | 7131.73 | 96.67% | 147.9 | 5 | 142.9 | 96.62% | 0% | -432.708 | 45.6874 | -37.55% | 25.8% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 26186.14 | 5762.27 | 20423.87 | 77.99% | 19428.98 | 7925.81 | 12051.35 | 7679.91 | 4371.44 | 36.27% | 0% | 7377.63 | 245.9 | 7131.73 | 96.67% | 147.9 | 5 | 142.9 | 96.62% | 0% | -432.708 | 45.6874 | -37.55% | 25.8% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 26186.14 | 5762.27 | 20423.87 | 77.99% | 19428.98 | 7925.81 | 12051.35 | 7679.91 | 4371.44 | 36.27% | 0% | 7377.63 | 245.9 | 7131.73 | 96.67% | 147.9 | 5 | 142.9 | 96.62% | 20% | -432.708 | 45.6874 | -37.55% | 25.8% |  |  | 0 | 0
|  | Week 3 | 26186.14 | 5762.27 | 20423.87 | 77.99% | 19428.98 | 7925.81 | 12051.35 | 7679.91 | 4371.44 | 36.27% | 0% | 7377.63 | 245.9 | 7131.73 | 96.67% | 147.9 | 5 | 142.9 | 96.62% | 25% | -432.708 | 45.6874 | -37.55% | 25.8% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 26186.14 | 5762.27 | 20423.87 | 77.99% | 19428.98 | 7925.81 | 12051.35 | 7679.91 | 4371.44 | 36.27% | 0% | 7377.63 | 245.9 | 7131.73 | 96.67% | 147.9 | 5 | 142.9 | 96.62% |  | -432.708 | 45.6874 | -37.55% | 25.8% |  |  | 0 | 0
|  | Week 5 | 26186.14 | 5762.27 | 20423.87 | 77.99% | 19428.98 | 7925.81 | 12051.32 | 7679.91 | 4371.41 | 36.27% | 0% | 7377.66 | 245.9 | 7131.76 | 96.67% | 147.9 | 5 | 142.9 | 96.62% |  | -432.708 | 45.6874 | -37.55% | 25.8% |  |  | 0 | 0
6792 | Major Hornbrook | Start of month | 33188.02 | 32192.38 | 995.64 | 3% | 23790.07 | 28358.52 | 13406.21 | 15975.39 | -2569.18 | -19.16% | 0% | 10383.86 | 12383.13 | -1999.27 | -19.25% | 208.2 | 248.75 | -40.55 | -19.48% |  | 15.4125 | 45.139 | 11.91% | 28.32% | Hours calc for monthly claims | 68.5 | 0 | 0
|  | Week 1 | 33188.02 | 32192.38 | 995.64 | 3% | 23790.07 | 28358.52 | 13406.21 | 15975.39 | -2569.18 | -19.16% | 0% | 10383.86 | 12383.13 | -1999.27 | -19.25% | 208.2 | 248.75 | -40.55 | -19.48% |  | 15.4125 | 45.139 | 11.91% | 28.32% | Materials calc for monthly claims | 587.13 | 40.5 | 587.13
|  | Week 2 | 33188.02 | 32192.38 | 995.64 | 3% | 23790.07 | 30917.81 | 13406.21 | 16562.52 | -3156.31 | -23.54% | 0% | 10383.86 | 14355.29 | -3971.43 | -38.25% | 208.2 | 289.25 | -81.05 | -38.93% |  | 4.4065 | 45.139 | 3.959% | 28.32% |  |  | 0 | 0
|  | Week 3 | 33188.02 | 32192.38 | 995.64 | 3% | 23790.07 | 30917.81 | 13406.21 | 16562.52 | -3156.31 | -23.54% | 0% | 10383.86 | 14355.29 | -3971.43 | -38.25% | 208.2 | 289.25 | -81.05 | -38.93% |  | 4.4065 | 45.139 | 3.959% | 28.32% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 33188.02 | 32192.38 | 995.64 | 3% | 23790.07 | 30917.81 | 13406.21 | 16562.52 | -3156.31 | -23.54% | 0% | 10383.86 | 14355.29 | -3971.43 | -38.25% | 208.2 | 289.25 | -81.05 | -38.93% |  | 4.4065 | 45.139 | 3.959% | 28.32% |  |  | 28 | -3.638e-12
|  | Week 5 | 33188.02 | 33188.03 | -0.01 | -3.013e-05% | 23790.07 | 32303.46 | 13406.21 | 16562.52 | -3156.31 | -23.54% | 0% | 10383.86 | 15740.94 | -5357.08 | -51.59% | 208.2 | 317.25 | -109.05 | -52.38% |  | 2.7882 | 45.139 | 2.665% | 28.32% |  |  | 68.5 | 587.13
8840 | Inline Architecture | Start of month | 54687.94 | 6042.41 | 48645.53 | 88.95% | 34464.78 | 9939.86 | 18667.45 | 4193.31 | 14474.14 | 77.54% | 100% | 15797.33 | 5746.55 | 10050.78 | 63.62% | 316.34 | 127.25 | 189.09 | 59.77% | 100% | -30.6283 | 63.9286 | -64.5% | 36.98% | Hours calc for monthly claims | 77.5 | 45 | 4993.36
|  | Week 1 | 54687.94 | 25591.11 | 29096.83 | 53.21% | 34464.78 | 17182.92 | 18667.45 | 9186.67 | 9480.78 | 50.79% | 100% | 15797.33 | 7996.25 | 7801.08 | 49.38% | 316.34 | 172.25 | 144.09 | 45.55% | 100% | 48.8139 | 63.9286 | 32.86% | 36.98% | Materials calc for monthly claims | 7961.96 | 13.25 | 2633.11
|  | Week 2 | 56556.55 | 25591.11 | 30965.44 | 54.75% | 35959.67 | 20682.54 | 20162.34 | 11819.78 | 8342.56 | 41.38% | 100% | 15797.33 | 8862.76 | 6934.57 | 43.9% | 316.34 | 185.5 | 130.84 | 41.36% | 100% | 26.4613 | 65.1099 | 19.18% | 36.42% |  |  | 0 | 0
|  | Week 3 | 56556.55 | 25591.11 | 30965.44 | 54.75% | 35959.67 | 20682.54 | 20162.34 | 11819.78 | 8342.56 | 41.38% | 0% | 15797.33 | 8862.76 | 6934.57 | 43.9% | 316.34 | 185.5 | 130.84 | 41.36% | 0% | 26.4613 | 65.1099 | 19.18% | 36.42% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 56556.55 | 25591.11 | 30965.44 | 54.75% | 35959.67 | 20682.54 | 20162.34 | 11819.78 | 8342.56 | 41.38% | 0% | 15797.33 | 8862.76 | 6934.57 | 43.9% | 316.34 | 185.5 | 130.84 | 41.36% | 0% | 26.4613 | 65.1099 | 19.18% | 36.42% |  |  | 19.25 | 335.49
|  | Week 5 | 56556.55 | 35454.43 | 21102.12 | 37.31% | 35959.67 | 21861.72 | 20162.34 | 12155.27 | 8007.07 | 39.71% | 0% | 15797.33 | 9706.45 | 6090.88 | 38.56% | 316.34 | 204.75 | 111.59 | 35.28% | 0% | 66.3869 | 65.1099 | 38.34% | 36.42% |  |  | 77.5 | 7961.96
8769 | Percival Bach | Start of month | 21404.82 | 0 | 0 | 0% | 17424.66 | 0 | 13229.5 | 0 | 13229.5 | 100% | 0% | 4195.16 | 0 | 4195.16 | 100% | 84.03 | 0 | 84.03 | 100% | 0% | #DIV/0! | 47.3659 | #DIV/0! | 18.59% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 21404.82 | 0 | 21404.82 | 100% | 17424.66 | 0 | 13229.5 | 0 | 13229.5 | 100% | 0% | 4195.16 | 0 | 4195.16 | 100% | 84.03 | 0 | 84.03 | 100% | 0% | #DIV/0! | 47.3659 | #DIV/0! | 18.59% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
7901 | St Albans Street | Start of month | 96573.02 | 11044.85 | 0 | 0% | 79663.86 | 9198.12 | 66022 | 9198.12 | 56823.88 | 86.07% | 0% | 13641.86 | 0 | 13641.86 | 100% | 273.37 | 0 | 273.37 | 100% | 0% | #DIV/0! | 61.8545 | 16.72% | 17.51% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 96573.02 | 11044.85 | 85528.17 | 88.56% | 79663.86 | 9198.12 | 66022 | 9198.12 | 56823.88 | 86.07% | 0% | 13641.86 | 0 | 13641.86 | 100% | 273.37 | 0 | 273.37 | 100% | 0% | #DIV/0! | 61.8545 | 16.72% | 17.51% | Materials calc for monthly claims | 2987.96 | 0 | 2987.96
|  | Week 2 | 96573.02 | 11044.85 | 85528.17 | 88.56% | 79663.86 | 12186.08 | 66022 | 12186.08 | 53835.92 | 81.54% | 0% | 13641.86 | 0 | 13641.86 | 100% | 273.37 | 0 | 273.37 | 100% |  | #DIV/0! | 61.8545 | -10.33% | 17.51% |  |  | 0 | 0
|  | Week 3 | 96573.02 | 11044.85 | 85528.17 | 88.56% | 79663.86 | 12186.08 | 66022 | 12186.08 | 53835.92 | 81.54% |  | 13641.86 | 0 | 13641.86 | 100% | 273.37 | 0 | 273.37 | 100% |  | #DIV/0! | 61.8545 | -10.33% | 17.51% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 96573.02 | 11044.85 | 85528.17 | 88.56% | 79663.86 | 12186.08 | 66022 | 12186.08 | 53835.92 | 81.54% |  | 13641.86 | 0 | 13641.86 | 100% | 273.37 | 0 | 273.37 | 100% |  | #DIV/0! | 61.8545 | -10.33% | 17.51% |  |  | 0 | 0
|  | Week 5 | 96573.02 | 15366.74 | 81206.28 | 84.09% | 79663.84 | 12186.08 | 66021.95 | 12186.08 | 53835.87 | 81.54% |  | 13641.89 | 0 | 13641.89 | 100% | 273.37 | 0 | 273.37 | 100% |  | #DIV/0! | 61.8546 | 20.7% | 17.51% |  |  | 0 | 2987.96
8923 | 4 Perry St | Start of month | 31802.41 | 14370.83 | 17431.58 | 54.81% | 23448.14 | 11232.72 | 15632.03 | 11154.51 | 4477.52 | 28.64% | 0% | 7816.11 | 78.21 | 7737.9 | 99% | 157 | 2 | 155 | 98.73% | 0% | 1569.055 | 53.2119 | 21.84% | 26.27% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 31802.41 | 14370.83 | 17431.58 | 54.81% | 23448.14 | 11232.72 | 15632.03 | 11154.51 | 4477.52 | 28.64% | 0% | 7816.11 | 78.21 | 7737.9 | 99% | 157 | 2 | 155 | 98.73% | 0% | 1569.055 | 53.2119 | 21.84% | 26.27% | Materials calc for monthly claims | 0 | 0 | -5.9
|  | Week 2 | 31802.41 | 14370.83 | 17431.58 | 54.81% | 23448.14 | 11232.72 | 15632.03 | 11148.61 | 4483.42 | 28.68% |  | 7816.11 | 84.11 | 7732 | 98.92% | 157 | 2 | 155 | 98.73% | 0% | 1569.055 | 53.2119 | 21.84% | 26.27% |  |  | 0 | 0
|  | Week 3 | 31802.41 | 14370.83 | 17431.58 | 54.81% | 23448.14 | 11232.72 | 15632.03 | 11148.61 | 4483.42 | 28.68% |  | 7816.11 | 84.11 | 7732 | 98.92% | 157 | 2 | 155 | 98.73% | 0% | 1569.055 | 53.2119 | 21.84% | 26.27% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 31802.41 | 14370.83 | 17431.58 | 54.81% | 23448.14 | 11232.72 | 15632.03 | 11148.61 | 4483.42 | 28.68% |  | 7816.11 | 84.11 | 7732 | 98.92% | 157 | 2 | 155 | 98.73% | 0% | 1569.055 | 53.2119 | 21.84% | 26.27% |  |  | 0 | 5.9
|  | Week 5 | 31802.41 | 14370.83 | 17431.58 | 54.81% | 23448.14 | 11238.62 | 15632.03 | 11154.51 | 4477.52 | 28.64% |  | 7816.11 | 84.11 | 7732 | 98.92% | 157 | 2 | 155 | 98.73% | 0% | 1566.105 | 53.2119 | 21.8% | 26.27% |  |  | 0 | 0
7864 | Ryans House | Start of month | 28626.25 | 20486.24 | 8140.01 | 28.44% | 21262.27 | 21984.81 | 11588.8 | 12933.62 | -1344.82 | -11.6% | 0% | 9673.47 | 9051.19 | 622.28 | 6.433% | 193.82 | 185 | 8.82 | 4.551% | 0% | -8.1004 | 37.9939 | -7.315% | 25.72% | Hours calc for monthly claims | 81.75 | 4 | 462.72
|  | Week 1 | 28626.25 | 27194.94 | 1431.31 | 5% | 21262.27 | 22665.93 | 11588.8 | 13396.34 | -1807.54 | -15.6% | 0% | 9673.47 | 9269.59 | 403.88 | 4.175% | 193.82 | 189 | 4.82 | 2.487% |  | 23.963 | 37.9939 | 16.65% | 25.72% | Materials calc for monthly claims | -1231.3 | 77.75 | -1694.02
|  | Week 2 | 28626.25 | 27194.94 | 1431.31 | 5% | 21262.27 | 24965.42 | 11588.8 | 11702.32 | -113.52 | -0.9796% | 0% | 9673.47 | 13263.1 | -3589.63 | -37.11% | 193.82 | 266.75 | -72.93 | -37.63% |  | 8.3581 | 37.9939 | 8.198% | 25.72% |  |  | 0 | 0
|  | Week 3 | 28626.25 | 27194.94 | 1431.31 | 5% | 21262.27 | 24965.42 | 11588.8 | 11702.32 | -113.52 | -0.9796% | 0% | 9673.47 | 13263.1 | -3589.63 | -37.11% | 193.82 | 266.75 | -72.93 | -37.63% |  | 8.3581 | 37.9939 | 8.198% | 25.72% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 28626.25 | 27194.94 | 1431.31 | 5% | 21262.27 | 24965.42 | 11588.8 | 11702.32 | -113.52 | -0.9796% | 0% | 9673.47 | 13263.1 | -3589.63 | -37.11% | 193.82 | 266.75 | -72.93 | -37.63% |  | 8.3581 | 37.9939 | 8.198% | 25.72% |  |  | 0 | 0
|  | Week 5 | 28626.25 | 27194.94 | 1431.31 | 5% | 21262.27 | 24965.42 | 11588.8 | 11702.32 | -113.52 | -0.9796% | 0% | 9673.47 | 13263.1 | -3589.63 | -37.11% | 193.82 | 266.75 | -72.93 | -37.63% |  | 8.3581 | 37.9939 | 8.198% | 25.72% |  |  | 81.75 | -1231.3
7912 | 71A Fendalton Road | Start of month | 268228.26 | 9034.53 | 259193.73 | 96.63% | 238611.58 | 6362.08 | 214154.26 | 3465.35 | 210688.91 | 98.38% |  | 24457.32 | 2896.73 | 21560.59 | 88.16% | 497.55 | 49.25 | 448.3 | 90.1% |  | 54.2629 | 59.525 | 29.58% | 11.04% | Hours calc for monthly claims | -49.25 | 9 | 0
|  | Week 1 | 268228.26 | 9034.53 | 259193.73 | 96.63% | 238611.58 | 6362.08 | 214154.25 | 3465.35 | 210688.9 | 98.38% |  | 24457.33 | 2896.73 | 21560.6 | 88.16% | 497.55 | 58.25 | 439.3 | 88.29% |  | 45.879 | 59.525 | 29.58% | 11.04% | Materials calc for monthly claims | -3465.35 | -58.25 | -3465.35
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | 0 | 0 | #DIV/0! |  | 0 |  | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | 0 | 0 | #DIV/0! |  | 0 |  | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | -49.25 | -3465.35
8360 | Dixon House | Start of month | 32773.41 | 25502.96 | 7270.45 | 22.18% | 22750.99 | 21846.04 | 12243.41 | 10619.9 | 1623.51 | 13.26% |  | 10507.58 | 11226.14 | -718.56 | -6.838% | 210.6 | 226.5 | -15.9 | -7.55% |  | 16.1453 | 47.5898 | 14.34% | 30.58% | Hours calc for monthly claims | 34.25 | 0 | 0
|  | Week 1 | 32773.41 | 30592.27 | 2181.14 | 6.655% | 22750.99 | 21846.04 | 12243.41 | 10619.9 | 1623.51 | 13.26% |  | 10507.58 | 11226.14 | -718.56 | -6.838% | 210.6 | 226.5 | -15.9 | -7.55% |  | 38.6147 | 47.5898 | 28.59% | 30.58% | Materials calc for monthly claims | -1295.49 | 34.25 | -1295.49
|  | Week 2 | 32773.41 | 32773.41 | 0 | 0% | 22750.99 | 22238.62 | 12243.41 | 9324.41 | 2919 | 23.84% |  | 10507.58 | 12914.21 | -2406.63 | -22.9% | 210.6 | 260.75 | -50.15 | -23.81% |  | 40.4019 | 47.5898 | 32.14% | 30.58% |  |  | 0 | 0
|  | Week 3 | 32773.41 | 32773.41 | 0 | 0% | 22750.99 | 22238.62 | 12243.41 | 9324.41 | 2919 | 23.84% |  | 10507.58 | 12914.21 | -2406.63 | -22.9% | 210.6 | 260.75 | -50.15 | -23.81% |  | 40.4019 | 47.5898 | 32.14% | 30.58% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 32773.41 | 32773.41 | 0 | 0% | 22750.99 | 22238.62 | 12243.41 | 9324.41 | 2919 | 23.84% |  | 10507.58 | 12914.21 | -2406.63 | -22.9% | 210.6 | 260.75 | -50.15 | -23.81% |  | 40.4019 | 47.5898 | 32.14% | 30.58% |  |  | 0 | 0
|  | Week 5 | 32773.41 | 32773.41 | 0 | 0% | 22750.99 | 22238.62 | 12243.41 | 9324.41 | 2919 | 23.84% |  | 10507.58 | 12914.21 | -2406.63 | -22.9% | 210.6 | 260.75 | -50.15 | -23.81% |  | 40.4019 | 47.5898 | 32.14% | 30.58% |  |  | 34.25 | -1295.49
8337 | Waimak Dairys | Start of month | 17899.33 | 0 | 17899.33 | 100% | 13691.44 | 7562.12 | 0 | 0 | 0 | #DIV/0! |  | 5458.47 | 2298.36 | 3160.11 | 57.89% | 109 | 0 | 109 | 100% |  | #DIV/0! | 114.1363 | #DIV/0! | 23.51% | Hours calc for monthly claims | 44.75 | 0 | 0
|  | Week 1 | 17899.33 | 0 | 17899.33 | 100% | 13691.44 | 7562.12 | 0 | 0 | 0 | #DIV/0! |  | 5508.47 | 2298.36 | 3210.11 | 58.28% | 110.44 | 0 | 110.44 | 100% |  | #DIV/0! | 112.1954 | #DIV/0! | 23.51% | Materials calc for monthly claims | 5263.76 | 0 | 5263.76
|  | Week 2 | 17899.33 | 0 | 17899.33 | 100% | 13919.4 | 7562.12 | 8410.93 | 5263.76 | 3147.17 | 37.42% |  | 5508.47 | 2298.36 | 3210.11 | 58.28% | 110.44 | 0 | 110.44 | 100% |  | #DIV/0! | 36.037 | #DIV/0! | 22.24% |  |  | 44.75 | 0
|  | Week 3 | 17899.33 | 0 | 17899.33 | 100% | 13919.4 | 7562.12 | 8410.93 | 5263.76 | 3147.17 | 37.42% |  | 5508.47 | 2298.36 | 3210.11 | 58.28% | 110.44 | 44.75 | 65.69 | 59.48% |  | -168.9859 | 36.037 | #DIV/0! | 22.24% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 17899.33 | 0 | 17899.33 | 100% | 13919.4 | 7562.12 | 8410.93 | 5263.76 | 3147.17 | 37.42% |  | 5508.47 | 2298.36 | 3210.11 | 58.28% | 110.44 | 44.75 | 65.69 | 59.48% |  | -168.9859 | 36.037 | #DIV/0! | 22.24% |  |  | 0 | 0
|  | Week 5 | 17899.33 | 0 | 17899.33 | 100% | 13919.4 | 7562.12 | 8410.93 | 5263.76 | 3147.17 | 37.42% |  | 5508.47 | 2298.36 | 3210.11 | 58.28% | 110.44 | 44.75 | 65.69 | 59.48% |  | -168.9859 | 36.037 | #DIV/0! | 22.24% |  |  | 44.75 | 5263.76
9240 | Daves Twizel Shack | Start of month | 10827.2 |  | 10827.2 | 100% | 7619.53 |  | 4388.87 | 0 | 4388.87 | 100% |  | 3230.66 |  | 3230.66 | 100% | 64.71 |  | 64.71 | 100% |  | #DIV/0! | 49.5699 | #DIV/0! | 29.63% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 10827.2 |  | 10827.2 | 100% | 7619.53 |  | 4388.87 | 0 | 4388.87 | 100% |  | 3230.66 |  | 3230.66 | 100% | 64.71 |  | 64.71 | 100% |  | #DIV/0! | 49.5699 | #DIV/0! | 29.63% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
7428 | FAB Pegasus Lakeside | Start of month | 146237.11 | 70638.78 | 75598.33 | 51.7% | 114651.89 | 71934.44 | 82888.16 | 0 | 82888.16 | 100% |  | 31763.73 | 12578.31 | 19185.42 | 60.4% | 659.73 | 245.25 | 414.48 | 62.83% |  | 236.7399 | 47.876 | 82.19% | 21.6% | Hours calc for monthly claims | 59.5 | 32 | 0
|  | Week 1 | 146237.11 | 89564.3 | 0 | 0% | 114651.89 | 73564.17 | 82888.16 | 0 | 82888.16 | 100% |  | 31763.73 | 13766.73 | 17997 | 56.66% | 659.73 | 277.25 | 382.48 | 57.98% |  | 273.3907 | 47.876 | 84.63% | 21.6% | Materials calc for monthly claims | 60408.1 | 0.5 | 59720.63
|  | Week 2 | 146237.11 | 89564.3 | 56672.81 | 38.75% | 114651.89 | 73523.83 | 82888.16 | 59720.63 | 23167.53 | 27.95% |  | 31763.73 | 13803.2 | 17960.53 | 56.54% | 659.73 | 277.75 | 381.98 | 57.9% |  | 57.7515 | 47.876 | 17.91% | 21.6% |  |  | 0 | 0
|  | Week 3 | 146237.11 | 89564.3 | 56672.81 | 38.75% | 114651.89 | 73523.83 | 82888.16 | 59720.63 | 23167.53 | 27.95% |  | 31763.73 | 13803.2 | 17960.53 | 56.54% | 659.73 | 277.75 | 381.98 | 57.9% |  | 57.7515 | 47.876 | 17.91% | 21.6% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 146237.11 | 89564.3 | 56672.81 | 38.75% | 114651.89 | 73523.83 | 82888.16 | 59720.63 | 23167.53 | 27.95% |  | 31763.73 | 13803.2 | 17960.53 | 56.54% | 659.73 | 277.75 | 381.98 | 57.9% |  | 57.7515 | 47.876 | 17.91% | 21.6% |  |  | 27 | 687.47
|  | Week 5 | 146237.11 | 94266.45 | 51970.66 | 35.54% | 114651.87 | 75526.07 | 82888.08 | 60408.1 | 22479.98 | 27.12% |  | 31763.79 | 15117.97 | 16645.82 | 52.41% | 659.73 | 304.75 | 354.98 | 53.81% |  | 61.4943 | 47.876 | 19.88% | 21.6% |  |  | 59.5 | 60408.1
0
9351 | Harewood Golf Club | Start of month | 22013.44 | 0 | 22013.44 | 100% | 11868.76 | 2282.63 | 3458.6 | 2282.63 | 1175.97 | 34% |  | 8410.16 | 0 | 8410.16 | 100% | 168.44 | 0 | 168.44 | 100% |  | #DIV/0! | 60.2273 | #DIV/0! | 46.08% | Hours calc for monthly claims | 11.25 | 11.25 | 16.08
|  | Week 1 | 22013.44 | 4953.02 | 17060.42 | 77.5% | 11868.76 | 2946.15 | 3458.6 | 2298.71 | 1159.89 | 33.54% |  | 8410.16 | 647.44 | 7762.72 | 92.3% | 168.44 | 11.25 | 157.19 | 93.32% |  | 178.3884 | 60.2273 | 40.52% | 46.08% | Materials calc for monthly claims | 16.08 | 0 | 0
|  | Week 2 | 16897.53 | 0 | 16897.53 | 100% | 9226.27 | 2946.15 | 2977.11 | 2298.71 | 678.4 | 22.79% |  | 6249.16 | 647.44 | 5601.72 | 89.64% | 125.17 | 11.25 | 113.92 | 91.01% |  | -261.88 | 61.2867 | #DIV/0! | 45.4% |  |  | 0 | 0
|  | Week 3 | 16897.53 | 0 | 16897.53 | 100% | 9226.27 | 2946.15 | 2977.11 | 2298.71 | 678.4 | 22.79% |  | 6249.16 | 647.44 | 5601.72 | 89.64% | 125.17 | 11.25 | 113.92 | 91.01% |  | -261.88 | 61.2867 | #DIV/0! | 45.4% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 16897.53 | 0 | 16897.53 | 100% | 9226.27 | 2946.15 | 2977.11 | 2298.71 | 678.4 | 22.79% |  | 6249.16 | 647.44 | 5601.72 | 89.64% | 125.17 | 11.25 | 113.92 | 91.01% |  | -261.88 | 61.2867 | #DIV/0! | 45.4% |  |  | 0 | 0
|  | Week 5 | 16897.53 | 0 | 16897.53 | 100% | 9226.27 | 2946.15 | 2977.11 | 2298.71 | 678.4 | 22.79% |  | 6249.16 | 647.44 | 5601.72 | 89.64% | 125.17 | 11.25 | 113.92 | 91.01% |  | -261.88 | 61.2867 | #DIV/0! | 45.4% |  |  | 11.25 | 16.08
7429 | Taggart House | Start of month | 17608.26 | 1232.58 | 16375.68 | 93% | 14076.97 | 1028 | 8286.46 | 0 | 8286.46 | 100% |  | 5790.51 | 0 | 5790.51 | 100% | 116.13 | 0 | 116.13 | 100% |  | #DIV/0! | 30.4081 | 100% | 20.05% | Hours calc for monthly claims | 32.25 | 0 | 0
|  | Week 1 | 17608.26 | 1232.58 | 16375.68 | 93% | 14077.05 | 1028 | 8286.54 | 0 | 8286.54 | 100% |  | 5790.51 | 0 | 5790.51 | 100% | 116.13 | 0 | 116.13 | 100% |  | #DIV/0! | 30.4074 | 100% | 20.05% | Materials calc for monthly claims | 3461.15 | 32.25 | 3461.15
|  | Week 2 | 20992.12 | 1232.58 | 19759.54 | 94.13% | 16299.09 | 4905.28 | 9784.33 | 3461.15 | 6323.18 | 64.63% |  | 6514.76 | 1444.13 | 5070.63 | 77.83% | 130.62 | 32.25 | 98.37 | 75.31% |  | -113.8822 | 35.9289 | -298% | 22.36% |  |  | 0 | 0
|  | Week 3 | 20992.12 | 1232.58 | 19759.54 | 94.13% | 16299.09 | 4905.28 | 9784.33 | 3461.15 | 6323.18 | 64.63% |  | 6514.76 | 1444.13 | 5070.63 | 77.83% | 130.62 | 32.25 | 98.37 | 75.31% |  | -113.8822 | 35.9289 | -298% | 22.36% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 20992.12 | 1232.58 | 19759.54 | 94.13% | 16299.09 | 4905.28 | 9784.33 | 3461.15 | 6323.18 | 64.63% |  | 6514.76 | 1444.13 | 5070.63 | 77.83% | 130.62 | 32.25 | 98.37 | 75.31% |  | -113.8822 | 35.9289 | -298% | 22.36% |  |  | 0 | 0
|  | Week 5 | 20992.12 | 1232.58 | 19759.54 | 94.13% | 16299.09 | 4905.28 | 9784.33 | 3461.15 | 6323.18 | 64.63% |  | 6514.76 | 1444.13 | 5070.63 | 77.83% | 130.62 | 32.25 | 98.37 | 75.31% |  | -113.8822 | 35.9289 | -298% | 22.36% |  |  | 32.25 | 3461.15
9508 | St Barnabas Church | Start of month | 39559.62 | 0 | 39559.62 | 100% | 29401.08 | 0 | 22999.49 | 0 | 22999.49 | 100% | 0% | 6401.59 | 0 | 6401.59 | 100% | 129.75 | 0 | 129.75 | 100% | 0% | #DIV/0! | 78.2932 | #DIV/0! | 25.68% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 39559.62 | 0 | 39559.62 | 100% | 29401.08 | 0 | 22999.49 | 0 | 22999.49 | 100% |  | 6401.59 | 0 | 6401.59 | 100% | 129.75 | 0 | 129.75 | 100% |  | #DIV/0! | 78.2932 | #DIV/0! | 25.68% | Materials calc for monthly claims | 0 | 5.75 | 0
|  | Week 2 | 23770.95 | 0 | 23770.95 | 100% | 14310.96 | 330.91 | 7389.34 | 0 | 7389.34 | 100% |  | 6921.62 | 330.91 | 6590.71 | 95.22% | 140.15 | 5.75 | 134.4 | 95.9% |  | -57.5496 | 67.499 | #DIV/0! | 39.8% |  |  | 0 | 0
|  | Week 3 | 23770.95 | 0 | 23770.95 | 100% | 14310.96 | 330.91 | 7389.34 | 0 | 7389.34 | 100% |  | 6921.62 | 330.91 | 6590.71 | 95.22% | 140.15 | 5.75 | 134.4 | 95.9% |  | -57.5496 | 67.499 | #DIV/0! | 39.8% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 23770.95 | 0 | 23770.95 | 100% | 14310.96 | 330.91 | 7389.34 | 0 | 7389.34 | 100% |  | 6921.62 | 330.91 | 6590.71 | 95.22% | 140.15 | 5.75 | 134.4 | 95.9% |  | -57.5496 | 67.499 | #DIV/0! | 39.8% |  |  | -5.75 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
0 | 0 | Start of month | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
0 | Contracting | Start of month |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 3 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Estimated months claim | 0 | 0 | 0
|  | Week 4 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
|  | Week 5 |  |  | 0 | #DIV/0! |  |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 0 | 0
8946 | Westcoast Vaults | Start of month | 137109.56 | 0 | 137109.56 | 100% | 117394.57 | 0 | 99479.62 | 0 | 99479.62 | 100% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  | #DIV/0! | 54.9378 | #DIV/0! | 14.38% | Hours calc for monthly claims | 0 | 0 | 0
|  | Week 1 | 137109.56 | 0 | 137109.56 | 100% | 117394.57 | 0 | 99479.62 | 0 | 99479.62 | 100% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  | #DIV/0! | 54.9378 | #DIV/0! | 14.38% | Materials calc for monthly claims | 0 | 0 | 0
|  | Week 2 | 137109.56 | 0 | 137109.56 | 100% | 117394.57 | 0 | 99479.62 | 0 | 99479.62 | 100% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  | #DIV/0! | 54.9378 | #DIV/0! | 14.38% |  |  | 0 | 0
|  | Week 3 | 137109.56 | 0 | 137109.56 | 100% | 117394.57 | 0 | 99479.62 | 0 | 99479.62 | 100% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  | #DIV/0! | 54.9378 | #DIV/0! | 14.38% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 137109.56 | 0 | 137109.56 | 100% | 117394.57 | 0 | 99479.62 | 0 | 99479.62 | 100% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  | #DIV/0! | 54.9378 | #DIV/0! | 14.38% |  |  | 0 | 0
|  | Week 5 | 137109.56 | 0 | 137109.56 | 100% | 117394.57 | 0 | 99479.62 | 0 | 99479.62 | 100% |  | 17914.95 | 0 | 17914.95 | 100% | 358.86 | 0 | 358.86 | 100% |  | #DIV/0! | 54.9378 | #DIV/0! | 14.38% |  |  | 0 | 0
8308 | Roydvale | Start of month | 389318.35 | 206944.06 | 182374.29 | 46.84% | 289549.48 | 176095.03 | 0 | 0 | 0 | #DIV/0! |  | 115269.5 | 19280.83 | 95988.67 | 83.27% | 2312.68 | 414.25 | 1898.43 | 82.09% |  | 453.0193 | 118.4984 | 90.68% | 25.63% | Hours calc for monthly claims | 600 | 299.5 | 0
|  | Week 1 | 389318.35 | 240563.46 | 0 | 0% | 289549.48 | 197795.69 | 0 | 0 | 0 | #DIV/0! |  | 115269.5 | 33338.39 | 81931.11 | 71.08% | 2312.68 | 713.75 | 1598.93 | 69.14% |  | 290.3328 | 118.4984 | 86.14% | 25.63% | Materials calc for monthly claims | 176149.13 | 193.25 | 174116.21
|  | Week 2 | 389318.35 | 240563.46 | 148754.89 | 38.21% | 289549.48 | 217432.96 | 174279.98 | 174116.21 | 163.77 | 0.09397% |  | 115269.5 | 43316.75 | 71952.75 | 62.42% | 2312.68 | 907 | 1405.68 | 60.78% |  | 25.5022 | 43.1399 | 9.615% | 25.63% |  |  | 0 | 0
|  | Week 3 | 389318.35 | 240563.46 | 148754.89 | 38.21% | 289549.48 | 217432.96 | 174279.98 | 174116.21 | 163.77 | 0.09397% |  | 115269.5 | 43316.75 | 71952.75 | 62.42% | 2312.68 | 907 | 1405.68 | 60.78% |  | 25.5022 | 43.1399 | 9.615% | 25.63% | Estimated months claim | 0 | 0 | 0
|  | Week 4 | 389318.35 | 240563.46 | 148754.89 | 38.21% | 289549.48 | 217432.96 | 174279.98 | 174116.21 | 163.77 | 0.09397% |  | 115269.5 | 43316.75 | 71952.75 | 62.42% | 2312.68 | 907 | 1405.68 | 60.78% |  | 25.5022 | 43.1399 | 9.615% | 25.63% |  |  | 107.25 | 2032.92
|  | Week 5 | 389318.35 | 271388.15 | 117930.2 | 30.29% | 289549.48 | 224459.32 | 174279.98 | 176149.13 | -1869.15 | -1.072% |  | 115269.5 | 48310.19 | 66959.31 | 58.09% | 2312.68 | 1014.25 | 1298.43 | 56.14% |  | 46.2695 | 43.1399 | 17.29% | 25.63% |  |  | 600 | 176149.13